## Schedule
Tasks | Activity ID | Summary Tasks | Activity Name | Ori Dur | Start | Finish | Total Float | Predecessor Details | Successor Details | Calendar | Proposed Changes | Assumptions | Risk | Mitigation
| Total |  |  | 852 | 2020-01-02 | 2023-05-08 | 0
| Local Funding |  |  | 509 | 2020-01-02 | 2021-12-31 | 343 |  |  | Standard
| Execute Participation Agreement 1B (complete prior to Sept 1) |  |  | 95 | 2020-01-23 | 2020-06-04 | 70 |  |  | Standard
Local.Part1B | PA-010 | Fin | Amend Task Orders | 26 | 2020-01-23 | 2020-02-27 | 28 | RCB-20-018: FS | PA-020: FS, PA-030: SS, PA-00-1B: SS | Standard
Local.Part1B | PA-020 | Fin | Final Participation Agreement Amendment 1B | 15 | 2020-03-18 | 2020-04-08 | 70 | PA-010: FS, RCB-20-040: FF -4 | PA-040: FF | Standard
Local.Part1B | PA-030 | Fin | Engineering Task Orders (HC, HR) | 30 | 2020-01-23 | 2020-03-04 | 28 | PA-010: SS | ENG-110: FS | Standard
Local.Part1B | PA-040 | Fin | Amendment 1B Exhibit B | 5 | 2020-04-01 | 2020-04-08 | 70 | PA-020: FF | PA-050: FS 41 | Standard
Local.Part1B | PA-050 | Fin | Executed 1B | 0 |  | 2020-06-04 | 70 | PA-040: FS 41 | PA-00-1B: FF, PA-160: FS | Standard
| Execute Participation Agreement 2 |  |  | 114 | 2020-03-18 | 2020-08-26 | 12 |  |  | Standard
Local.Part2A | PA-120 | Fin | Draft Participation Agreement Amend 2 for Home Board Review | 15 | 2020-03-18 | 2020-04-08 | 15 | RCB-20-040: FF -4 | PA-130: FS, PA-00-2A: SS | Standard
Local.Part2A | PA-130 | Fin | Home Board Review - Determine Participation Level | 44 | 2020-04-17 | 2020-06-18 | 8 | PA-120: FS, RCB-20-044: FS | PA-140: FS | Standard
Local.Part2A | PA-140 | Fin | Rebalance Participation | 8 | 2020-06-19 | 2020-06-30 | 8 | PA-130: FS | PA-150: FS | Standard
Local.Part2A | PA-150 | Fin | Final Participation Agreement Amend 2 with Exhibits | 0 |  | 2020-06-30 | 8 | PA-140: FS | PA-160: FS, RCB-20-070: FS | Standard
Local.Part2A | PA-160 | Fin | Execute Amendment 2 | 0 |  | 2020-08-26 | 12 | PA-150: FS, RCB-20-084: FS 4, PA-050: FS | PA-00-2A: FF, WP-130: FS | Standard
| Execute Successor Participation Agreement 2 |  |  | 106 | 2021-08-02 | 2021-12-31 | 343 |  |  | Standard
Local.Part2 | A1000 | Fin | Execute Successor Agreement | 106 | 02-Aug-21* | 2021-12-31 | 343 |  |  | Standard
| Work Plan Amend 1B (complete prior to Sept 1) |  |  | 40 | 2020-01-02 | 2020-02-26 | 89 |  |  | Standard
Local.WP1B | WP-005 | WP | Incorporate Comments from Dec Res Comm Mtg | 9 | 02-Jan-20* | 2020-01-14 | 0 |  | WP-015: FS, RCB-20-010: FS, WP-00-1B: SS | Standard
Local.WP1B | WP-015 | WP | Prepare Final Work Plan | 14 | 2020-01-15 | 2020-02-03 | 6 | WP-005: FS | OB-022: FS, RCB-20-020: FS, WP-020: FS | Standard
Local.WP1B | WP-020 | WP | Budget & Finance Work Group Review | 5 | 2020-02-04 | 2020-02-10 | 6 | WP-015: FS | RCB-20-020: FS, WP-025: FS, WP-035: FS, PDE-20: FS, PDE-25: FS, PDE-30: FS, PDE-35: FS, PDE-10: FS, EIR-001: FS, 404-003: FS | Standard
Local.WP1B | WP-025 | WP | Work Plan 1B Approved | 0 |  | 2020-02-26 | 89 | WP-020: FS, RCB-20-028: FF | WP-00-1B: FF, WP-110: FS | Standard
| Work Plan Amend 2 |  |  | 150 | 2020-01-28 | 2020-08-26 | 12 |  |  | Standard
| Develop Schedule |  |  | 29 | 2020-01-28 | 2020-03-06 | 1 |  |  | Standard
Local.WP2A.01w) | WP-040 | WP | Develop Draft Schedule thru Dec 31, 2021 | 13 | 2020-01-28 | 2020-02-13 | 3 | RCB-20-018: FS 3 | WP-00-2A: SS, WP-060: FS, RCB-20-020: FF, WP-050: SS | Standard
Local.WP2A.01w) | WP-060 | WP | Develop Final Schedule through Dec 2021 | 10 | 2020-02-24 | 2020-03-06 | 1 | WP-040: FS, RCB-20-024: FS | WP-095: FS | Standard
| Work Plan Scope Document |  |  | 29 | 2020-01-28 | 2020-03-06 | 1 |  |  | Standard
Local.WP2A.02 | WP-050 | WP | Draft Work Plan Task List | 13 | 2020-01-28 | 2020-02-13 | 7 | WP-040: SS | WP-070: FS | Standard
Local.WP2A.02 | WP-070 | WP | Final Work Plan Scope Document | 10 | 2020-02-24 | 2020-03-06 | 1 | WP-050: FS, RCB-20-024: FS | WP-095: FS | Standard
| Work Plan Budget |  |  | 29 | 2020-01-28 | 2020-03-06 | 1 |  |  | Standard
Local.WP2A.03 | WP-035 | WP | Budget Scenarios and Assumptions | 2 | 2020-02-11 | 2020-02-12 | 8 | WP-020: FS | WP-055: FF | Standard
Local.WP2A.03 | WP-055 | WP | Draft Work Plan Budget | 13 | 2020-01-28 | 2020-02-13 | 7 | RCB-20-018: FS 3, WP-035: FF | WP-090: FS | Standard
Local.WP2A.03 | WP-090 | WP | Final Work Plan Budget | 10 | 2020-02-24 | 2020-03-06 | 1 | WP-055: FS, RCB-20-024: FS | WP-095: FS | Standard
| Amendment 2 |  |  | 121 | 2020-03-09 | 2020-08-26 | 12 |  |  | Standard
Local.WP2A.am | WP-095 | WP | Final Amendment 2 Work Plan | 5 | 2020-03-09 | 2020-03-13 | 1 | WP-090: FS, WP-070: FS, WP-060: FS | WP-120: FS, WP-110: FS, RCB-20-030: FS | Standard
Local.WP2A.am | WP-110 | WP | Develop Task Orders (Sep 2020 to Dec 2021) | 51 | 2020-03-16 | 2020-05-26 | 77 | WP-095: FS, RCB-20-030: FS, WP-025: FS | WP-120: FS | Standard
Local.WP2A.am | WP-120 | WP | Work Plan 2 Approved | 0 |  | 2020-06-18 | 60 | WP-095: FS, WP-110: FS, RCB-20-064: FF | EIR-020: FS, WP-00-2A: FF, EIR-019: FS, WP-130: FS | Standard
Local.WP2A.am | WP-130 | WP | Start of Amend 2 | 0 |  | 2020-08-26 | 12 | WP-120: FS, PA-160: FS | BA-001: FS, ENG-400: FS, ENG-410: FS, ENG-420: FS, ENG-404: FS, ENG-406: FS, 401-130: FS, EIR-019: FS, GSR-010: FS, WR-005: FS | Standard
| Value Planning |  |  | 73 | 2020-01-02 | 2020-04-13 | 0 |  |  | Standard
| Value Planning Analysis |  |  | 44 | 2020-01-02 | 2020-03-03 | 8 |  |  | Standard
Val Pl.VPA | VP-001 | Eng | Refine Value Planning Options | 3 | 2020-01-02 | 2020-01-06 | 4 |  | VP-002: FS, FAA-005: FS 5, VP-00-1B: SS | Standard
Val Pl.VPA | VP-002 | Eng | Screen Value Planning Options | 20 | 2020-01-07 | 2020-02-03 | 4 | VP-001: FS | VP-020: FS, VP-013: FS | Standard
Val Pl.VPA | VP-006 | Permit | Qualitative Permit Screening | 37 | 2020-01-02 | 2020-02-21 | 15 |  | VP-025: FF | Standard
Val Pl.VPA | VP-007 | Env | Qualitative Env Screening | 37 | 2020-01-02 | 2020-02-21 | 15 |  | VP-025: FF | Standard
Val Pl.VPA | VP-008 | Ops | Qualitative Ops Screening | 37 | 2020-01-02 | 2020-02-21 | 15 |  | VP-025: FF | Standard
Val Pl.VPA | VP-013 | Eng | Prepare Costs For Value Planning Alternatives | 15 | 2020-02-04 | 2020-02-24 | 4 | VP-002: FS | VP-025: FF, RA-005: FS, VP-020: FS, VP-014: FS | Standard
Val Pl.VPA | VP-014 | Fin | Affordability Analysis | 4 | 2020-02-25 | 2020-02-28 | 4 | VP-013: FS, OP-005: FS | VP-015: FS, VP-025: FF | Standard
Val Pl.VPA | VP-015 | Eng | Screen Alternatives | 2 | 2020-03-02 | 2020-03-03 | 4 | VP-014: FS | VP-020: FS | Standard
Val Pl.VPA | VP-020 | Eng | Recommend Preferred Option | 0 |  | 2020-03-03 | 4 | VP-002: FS, VP-013: FS, VP-015: FS | VP-025: FF 4 | Standard
| Value Planning Report |  |  | 42 | 2020-02-14 | 2020-04-13 | 0 |  |  | Standard
Val Pl.Rep | VP-025 | Eng | Value Planning Draft Report | 21 | 2020-02-14 | 2020-03-13 | 0 | VP-013: FF, VP-006: FF, VP-007: FF, VP-008: FF, VP-020: FF 4, OP-005: FS -6, OP-007: FS -6, OP-010: FS -6, VP-014: FF | VP-070: FS, RCB-20-030: FS, PDE-40: FS | Standard
Val Pl.Rep | VP-070 | Eng | Preferred Project | 21 | 2020-03-16 | 2020-04-13 | 0 | VP-025: FS | VP-090: FF, VP-095: FS, BA-024: FS, 404-003: FS, 404-001: FS, 408-005: FS | Standard
Val Pl.Rep | VP-090 | Eng | Value Planning Final Report | 17 | 2020-03-20 | 2020-04-13 | 0 | VP-070: FF | VP-095: FS, PDE-50: FS, PDE-55: FS, RCB-20-040: FF | Standard
| Preferred Project |  |  | 0 | 2020-04-13 | 2020-04-13 | 0 |  |  | Standard
Val Pl.Due | VP-095 | Eng | Approve Preferred Project | 0 |  | 2020-04-13 | 0 | VP-070: FS, VP-090: FS | PDE-50: FS, VP-00-1B: FF, PDE-10: FF 10, BA-019: FS, BA-025: FS, BA-010: FS, BA-015: FS, CES-030: FS, CES-210: FS, ENG-130: FS, CES-015: FS, RCB-20-040: FS, PDE-45: FS, PDE-46: FS, PDE-47: FS | Standard
| Project Description |  |  | 141 | 2020-02-11 | 2020-08-27 | 683 |  |  | Standard
| Determine Needs |  |  | 56 | 2020-02-11 | 2020-04-28 | 9 |  |  | Standard
Prj Des.Needs | PDE-10 | Env | Environmental Planning Needs | 56 | 2020-02-11 | 2020-04-28 | 9 | VP-095: FF 10, WP-020: FS | PDE-50: FS, PDE-00-00: SS | Standard
Prj Des.Needs | PDE-20 | Permit | Permitting Needs | 56 | 2020-02-11 | 2020-04-28 | 9 | WP-020: FS | PDE-50: FS | Standard
Prj Des.Needs | PDE-25 | Eng | Engineering Needs | 46 | 2020-02-11 | 2020-04-14 | 19 | WP-020: FS | PDE-50: FS | Standard
Prj Des.Needs | PDE-30 | Ops | Operations Needs | 10 | 2020-02-11 | 2020-02-24 | 55 | WP-020: FS | PDE-50: FS | Standard
Prj Des.Needs | PDE-35 | Permit | Water Rights Needs (Reg Items/Study) | 46 | 2020-02-11 | 2020-04-14 | 19 | WP-020: FS | PDE-50: FS | Standard
| Components |  |  | 65 | 2020-04-14 | 2020-07-15 | 714 |  |  | Standard
Prj Des.Eng | PDE-40 | Env | Identify Alternatives for EIR/EIS | 30 | 2020-04-21 | 2020-06-02 | 4 | VP-025: FS, ENG-130: FS | PDE-42: FS, EIR-019: FS, EIR-010: FS, ENG-233: FS, ENG-236: FS | Standard
Prj Des.Eng | PDE-42 | Eng | Determine Preliminary Project Construction Sequencing | 30 | 2020-06-03 | 2020-07-15 | 42 | PDE-40: FS | EIR-019: FS | Standard
Prj Des.Eng | PDE-45 | Env | Identify Project-Level vs Program Components (Planning) | 47 | 2020-04-14 | 2020-06-18 | 60 | VP-095: FS | EIR-019: FS | Standard
Prj Des.Eng | PDE-46 | Eng | Identify Program-Level vs Program Components (Planning) | 47 | 2020-04-14 | 2020-06-18 | 732 | VP-095: FS |  | Standard
Prj Des.Eng | PDE-47 | Permit | Identify Project-Level vs Program Components (Permitting) | 47 | 2020-04-14 | 2020-06-18 | 60 | VP-095: FS | EIR-019: FS | Standard
| Develop Project Description |  |  | 85 | 2020-04-29 | 2020-08-27 | 9 |  |  | Standard
Prj Des.Ops | PDE-50 | Env | Develop Project Description Construction | 85 | 2020-04-29 | 2020-08-27 | 9 | PDE-20: FS, PDE-30: FS, PDE-10: FS, VP-095: FS, PDE-25: FS, PDE-35: FS, VP-090: FS | PDE-60: FF, BA-024: FS | Standard
Prj Des.Ops | PDE-55 | Ops | Project Description Operations Criteria | 0 |  | 2020-06-12 | 62 | VP-090: FS, OP-220: FS | EIR-020: FS, PDE-60: FS | Standard
| Project Description Complete |  |  | 0 | 2020-08-27 | 2020-08-27 | 9 |  |  | Standard
Prj Des.del | PDE-60 | Env | Project Description | 0 |  | 2020-08-27 | 9 | PDE-50: FF, ENG-190: FS, ENG-200: FS, PDE-55: FS | EIR-019: FS, BA-001: FS, 106-001: FS, PDE-00-00: FF, WR-025: FS, ENG-250: FF | Standard
| Operations |  |  | 486 | 2020-01-02 | 2021-11-29 | 10 |  |  | Standard
| Value Planning Operations |  |  | 71 | 2020-01-02 | 2020-04-10 | 0 |  |  | Standard
Ops Pl.OpPkg | OP-005 | Ops | Value Planning Model | 37 | 2020-01-02 | 2020-02-21 | 0 |  | OP-00-1B: SS, ENG-140: FS, EB-00-00: SS, VP-025: FS -6, VP-014: FS | Standard
Ops Pl.OpPkg | OP-007 | Ops | Stony Creek Evaluation | 37 | 2020-01-02 | 2020-02-21 | 0 |  | VP-025: FS -6 | Standard
Ops Pl.OpPkg | OP-010 | Ops | Shasta Exchanges Post-Processing and Draft TM | 37 | 2020-01-02 | 2020-02-21 | 0 |  | OP-015: SS 22, OP-00-00: SS, VP-025: FS -6 | Standard
Ops Pl.OpPkg | OP-015 | Ops | Value Planning TM/Document | 20 | 2020-02-03 | 2020-02-28 | 6 | OP-010: SS 22 | OP-020: SS 5 | Standard
Ops Pl.OpPkg | OP-020 | Ops | Storage to Release Ratios Table | 15 | 2020-02-10 | 2020-02-28 | 6 | OP-015: SS 5 | RCB-20-070: FS, OP-00-1B: FF, OP-110: SS | Standard
Ops Pl.OpPkg | OP-070 | Ops | Reclamation Feasibility Complete (Milestone) | 0 |  | 10-Apr-20* | 0 |  | ENG-399: FS, ENG-250: FS | Standard
| Refine Operational Parameters |  |  | 89 | 2020-02-10 | 2020-06-12 | 6 |  |  | Standard
Ops Pl.Para | OP-110 | Ops | Notched Fremont Weir | 44 | 2020-02-10 | 2020-04-09 | 6 | OP-020: SS | OP-120: FS, OP-130: SS, OP-150: SS, OP-160: SS, OP-170: SS, OP-180: SS, OP-190: SS, OP-200: SS, OP-210: FS, OP-140: SS | Standard | Add a new task to reflect PMP/iterative process to develop env criteria into modeling | Assumes iterative operations analysis to evaluate CDFW Scenarios is completed in this phase of operations | Not meeting schedule for EIR/S and permitting | PMP to include conflict resolution timeframes to meet schedule
Ops Pl.Para | OP-120 | Ops | Model Reclamation with No-Storage | 44 | 2020-04-10 | 2020-06-11 | 6 | OP-110: FS | OP-210: FF | Standard
Ops Pl.Para | OP-130 | Ops | Confirm Shasta Exchange | 44 | 2020-02-10 | 2020-04-09 | 6 | OP-110: SS | OP-210: FS | Standard
Ops Pl.Para | OP-140 | Ops | Confirm Sutter Bypass | 44 | 2020-02-10 | 2020-04-09 | 6 | OP-110: SS | OP-210: FS | Standard
Ops Pl.Para | OP-150 | Ops | Confirm Voluntary Agreement Weir Notching | 44 | 2020-02-10 | 2020-04-09 | 6 | OP-110: SS | OP-210: FS | Standard
Ops Pl.Para | OP-160 | Ops | Confirm Delta Water Quality | 44 | 2020-02-10 | 2020-04-09 | 6 | OP-110: SS | OP-210: FS | Standard
Ops Pl.Para | OP-170 | Ops | Confirm Sacramento River Mortality | 44 | 2020-02-10 | 2020-04-09 | 6 | OP-110: SS | OP-210: FS | Standard
Ops Pl.Para | OP-180 | Ops | Determine Baseline | 44 | 2020-02-10 | 2020-04-09 | 6 | OP-110: SS | OP-210: FS | Standard | Recommend that this is moved up in the process so that this phase of the modeling effort uses the new baseline to refine parameters | Need to run modeling with new baseline to identify criteria issues | Not identifying criteria which results in not meeting schedule for EIR/S and permitting | Make baseline a higher priority
Ops Pl.Para | OP-190 | Ops | Confirm CVP/SWP Integration | 44 | 2020-02-10 | 2020-04-09 | 6 | OP-110: SS | OP-210: FS | Standard
Ops Pl.Para | OP-200 | Ops | Confirm Participation Demands Updated | 44 | 2020-02-10 | 2020-04-09 | 6 | OP-110: SS | OP-210: FS | Standard
Ops Pl.Para | OP-210 | Ops | Confirm Refinements | 44 | 2020-04-10 | 2020-06-11 | 6 | OP-200: FS, OP-110: FS, OP-130: FS, OP-140: FS, OP-150: FS, OP-160: FS, OP-170: FS, OP-180: FS, OP-190: FS, OP-120: FF | OP-230: FS, OP-240: FS, OP-250: FS, OP-260: FS, OP-280: FS, OP-290: FS, OP-310: FS, OP-270: FS, OP-300: FS, OP-315: FS, OP-00-00: FF, OP-220: FF 1 | Standard
Ops Pl.Para | OP-220 | Ops | Finalize Operational Criteria | 0 |  | 2020-06-12 | 6 | OP-210: FF 1 | OP-230: FS, OP-240: FS, OP-250: FS, OP-260: FS, OP-270: FS, OP-280: FS, OP-290: FS, OP-300: FS, OP-310: FS, OP-315: FS, PDE-55: FS | Standard
| Full Operations Analysis |  |  | 104 | 2020-06-15 | 2020-11-09 | 40 |  |  | Standard
Ops Pl.Ana | OP-230 | Ops | CalSim | 104 | 2020-06-15 | 2020-11-09 | 6 | OP-210: FS, OP-220: FS | OP-320: FS, OP-330: SS 20, OP-340: FS, OP-350: FS, OP-360: FS, CES-180: FF, OP-00-AN: SS, EIR-020: FS | Standard
Ops Pl.Ana | OP-240 | Ops | DSM2-Hydro | 104 | 2020-06-15 | 2020-11-09 | 40 | OP-210: FS, OP-220: FS | OP-320: FS, EIR-020: FS | Standard
Ops Pl.Ana | OP-250 | Ops | USRWQM | 104 | 2020-06-15 | 2020-11-09 | 40 | OP-210: FS, OP-220: FS | OP-320: FS, EIR-020: FS | Standard
Ops Pl.Ana | OP-260 | Ops | SALMOD | 104 | 2020-06-15 | 2020-11-09 | 40 | OP-210: FS, OP-220: FS | OP-320: FS, EIR-020: FS | Standard
Ops Pl.Ana | OP-270 | Ops | IOS | 104 | 2020-06-15 | 2020-11-09 | 40 | OP-220: FS, OP-210: FS | OP-320: FS, EIR-020: FS | Standard
Ops Pl.Ana | OP-280 | Ops | DSM2-Qual | 104 | 2020-06-15 | 2020-11-09 | 40 | OP-210: FS, OP-220: FS | OP-320: FS, EIR-020: FS | Standard
Ops Pl.Ana | OP-290 | Ops | OBAN | 104 | 2020-06-15 | 2020-11-09 | 9 | OP-210: FS, OP-220: FS | OP-320: FS, BA-022: FF, EIR-020: FS, CES-180: FF, BA-025: FS | Standard
Ops Pl.Ana | OP-300 | Ops | Fish Mortality Models | 104 | 2020-06-15 | 2020-11-09 | 9 | OP-220: FS, OP-210: FS | OP-320: FS, BA-022: FF, EIR-020: FS, CES-180: FF, BA-025: FS | Standard
Ops Pl.Ana | OP-310 | Ops | Power | 104 | 2020-06-15 | 2020-11-09 | 40 | OP-210: FS, OP-220: FS | OP-320: FS, EIR-020: FS | Standard
Ops Pl.Ana | OP-315 | Ops | Economics | 104 | 2020-06-15 | 2020-11-09 | 13 | OP-210: FS, OP-220: FS | OP-320: FS, ENG-260: FF, OP-00-AN: FF, EIR-020: FS | Standard
| Coordination |  |  | 350 | 2020-07-14 | 2021-11-29 | 10 |  |  | Standard
Ops Pl.Coor | OP-320 | Ops | Documentation for EIR/EIS and BA/ITP | 40 | 2020-11-10 | 2021-01-08 | 65 | OP-230: FS, OP-240: FS, OP-260: FS, OP-270: FS, OP-280: FS, OP-290: FS, OP-300: FS, OP-310: FS, OP-315: FS, OP-250: FS | EIR-030: FS, EIR-020: FF | Standard
Ops Pl.Coor | OP-330 | Ops | Ongoing Support to EPP, Engineering, & Financial | 350 | 2020-07-14 | 2021-11-29 | 10 | OP-230: SS 20 | ENG-399: FS | Standard
Ops Pl.Coor | OP-340 | Ops | Cumulative and Climate Change | 62 | 2020-11-10 | 2021-02-09 | 23 | OP-230: FS | EIR-025: FS | Standard
Ops Pl.Coor | OP-350 | Ops | Bridging Simulation | 126 | 2020-11-10 | 2021-05-10 | 40 | OP-230: FS | ENG-390: FF | Standard
Ops Pl.Coor | OP-360 | Ops | Ops Support for Local Feasibility - Water Commission | 160 | 2020-11-10 | 2021-06-28 | 6 | OP-230: FS | ENG-390: FF | Standard
| EIR/EIS |  |  | 524 | 2020-02-11 | 2022-03-03 | 185
| Work Plan & Outline |  |  | 148 | 2020-02-11 | 2020-09-08 | 4 |  |  | Standard
EIR.Out | EIR-001 | Env | Prepare EIR/EIS Work Plan | 46 | 2020-02-11 | 2020-04-14 | 38 | WP-020: FS | EIR-00-00: SS, EIR-010: FS | Standard | Schedule doesn’t reflect ICF/Sites/Laurie's changes | in email | in email | in email
EIR.Out | EIR-010 | Env | Prepare Annotated Outline | 68 | 2020-06-03 | 2020-09-08 | 4 | EIR-001: FS, PDE-40: FS | EIR-019: FS | Standard | Add VP-095
| Draft EIR/EIS |  |  | 213 | 2020-09-09 | 2021-07-12 | 2
EIR.Draft | EIR-019 | Env | Prepare Revised Draft EIR/S (Construction) | 80 | 2020-09-09 | 2021-01-04 | 4 | PDE-40: FS, PDE-60: FS, PDE-45: FS, PDE-42: FS, EIR-010: FS, WP-120: FS, ENG-220: FF, WP-130: FS, PDE-47: FS | EIR-020: FS, EIR-030: FS | Standard
EIR.Draft | EIR-020 | Env | Prepare Revised Draft EIR (Operations) | 65 | 2021-01-05 | 2021-04-05 | 4 | WP-120: FS, EIR-019: FS, OP-230: FS, OP-315: FS, OP-240: FS, OP-250: FS, OP-260: FS, OP-270: FS, OP-280: FS, OP-290: FS, OP-300: FS, OP-310: FS, PDE-55: FS, EB-00-00: FS, OP-320: FF | EIR-030: FS | Standard
EIR.Draft | EIR-025 | Env | Prepare Cumulative and Climate Change Sections | 20 | 2021-02-10 | 2021-03-09 | 23 | OP-340: FS | EIR-030: FS | Standard
EIR.Draft | EIR-030 | Env | Authority/Reclamation/Integration Review of Admin Draft EIR | 10 | 2021-04-06 | 2021-04-19 | 4 | EIR-020: FS, EIR-025: FS, EIR-019: FS, OP-320: FS | EIR-040: FS | Standard |  | Reclamation can adhere to review cycles needed to meet CWC deadlines | If they need more time risk missing CWC deadline | Decouple joint document and have EIS be on a separate schedule/path
EIR.Draft | EIR-040 | Env | Revise Draft EIR | 20 | 2021-04-20 | 2021-05-17 | 4 | EIR-030: FS | EIR-050: FS | Standard
EIR.Draft | EIR-050 | Env | Work Group & Legal Review of Revised Draft EIR | 30 | 2021-05-18 | 2021-06-16 | 4 | EIR-040: FS | EIR-060: FS | 7-Day Workweek
EIR.Draft | EIR-060 | Env | Resolve Work Group Comments | 15 | 2021-06-16 | 2021-07-08 | 2 | EIR-050: FS | EIR-070: FS | Standard
EIR.Draft | EIR-070 | Env | Authority Approval of Revised Draft EIR | 1 | 2021-07-08 | 2021-07-09 | 2 | EIR-060: FS | EIR-080: FS 1, WR-025: FS | Standard
EIR.Draft | EIR-080 | Env | Submit Revised Draft EIR | 0 |  | 2021-07-12 | 2 | EIR-070: FS 1 | EIR-090: FS, EIR-00-00: FF, ENG-395: FS | Standard
| Public Review |  |  | 90 | 2021-07-13 | 2021-10-10 | 15 |  |  | 7-Day Workweek
EIR.Pub | EIR-090 | Env | Public Review Period | 90 | 2021-07-13 | 2021-10-10 | 15 | EIR-080: FS | EIR-130: FS -20, EIR-100: FS | 7-Day Workweek
| Summary Report |  |  | 33 | 2021-10-11 | 2021-11-24 | 11 |  |  | Standard
EIR.Final | EIR-100 | Env | Approach to Response to Comments | 10 | 2021-10-11 | 2021-10-22 | 11 | EIR-090: FS | EIR-110: FS, EIR-130: FS | Standard |  | Schedule is sufficient to review and categorize all comments. Past practice suggests most come in on last day | summary report may not fully consider all comments & corresponding strategy | Re-evaluate strategy for summary report depending on comments received
EIR.Final | EIR-110 | Env | Prepare Summary Report | 22 | 2021-10-25 | 2021-11-23 | 11 | EIR-100: FS | EIR-120: FS 1 | Standard
EIR.Final | EIR-120 | Env | Draft EIR Summary Report Submittal to CWC | 0 |  | 2021-11-24 | 11 | EIR-110: FS 1 | ENG-399: FS | Standard
| Response to Comments |  |  | 90 | 2021-10-25 | 2022-03-03 | 185 |  |  | Standard
EIR.Com | EIR-130 | Env | Response to Comments | 90 | 2021-10-25 | 2022-03-03 | 185 | EIR-090: FS -20, EIR-100: FS | WR-125: FS | Standard
| Permitting |  |  | 852 | 2020-01-02 | 2023-05-08 | 0
| Biological Assessment |  |  | 369 | 2020-01-02 | 2021-06-14 | 34
PER.BA | BA-001 | Permit | Initial Desktop Analysis | 60 | 2020-09-29 | 2020-12-23 | 22 | PDE-60: FS, WP-130: FS, ENG-220: FS, BA-019: FS | BA-024: FF 20 | Standard |  | Dependent on ENG-220 completed by both engineering team | delayed or incorrect impact acreages/needing to revise analysis, cost/schedule | PMP includes QA and coordination roles and steps
PER.BA | BA-003 | Permit | Strategize with USFWS and Reclamation on Surveys, Impacts & Mitigation | 171 | 2020-01-02 | 2020-08-31 | 121 |  | BA-030: FS | Standard |  | USFWS and Reclamation agrees to no or minimal surveys for BA | Higher mitigation cost/phased approach to consultation | Early coordination with Sites, ROW team and stakeholders to identify if surveys can be done for key species
PER.BA | BA-010 | Permit | Mitigation Planning | 202 | 2020-04-14 | 2021-01-29 | 14 | VP-095: FS | BA-00-00: SS, BA-030: FS, BA-024: FF, BA-025: FF | Standard |  | mitigation is available to meet needs of the project | Not having mitigation packet for PD for document and permit applications | Start mitigation process before 9/1/2020
PER.BA | BA-015 | Permit | Adaptive Management Plan | 202 | 2020-04-14 | 2021-01-29 | 17 | VP-095: FS | BA-030: FS | Standard
PER.BA | BA-019 | Permit | Confirm Federal Scope of Action (ESA) | 38 | 2020-04-14 | 2020-06-05 | 68 | VP-095: FS | BA-024: FS, BA-020: FS, 404-003: FF, BA-001: FS | Standard |  | This is a critical milestone that will determine approach for Section 7 consultation | Section 10 HCP process/USACE lead/schedule and cost implications | Develop an approach based on other projects to define action area with Reclamation
PER.BA | BA-020 | Permit | Permitting Construction Project Description | 16 | 2020-06-08 | 2020-06-29 | 68 | BA-019: FS | BA-024: FS | Standard
PER.BA | BA-022 | Permit | Permitting Operations Project Description | 20 | 2020-10-13 | 2020-11-09 | 9 | OP-290: FF, OP-300: FF | BA-025: FS | Standard |  | Assumes modeling can be completed within the schedule that will define operating criteria that is likely to be permitted by NMFS | operation changes, cost and schedule, higher mitigation costs | PMP to include conflict resolution process and timeframes to meet schedule
PER.BA | BA-024 | Permit | Prepare Construction Analysis | 97 | 2020-09-11 | 2021-01-29 | 17 | VP-070: FS, BA-001: FF 20, BA-019: FS, PDE-50: FS, BA-020: FS, BA-010: FF | BA-030: FS | Standard | add ENG-220
PER.BA | BA-025 | Permit | Prepare Operations Analysis | 60 | 2020-11-10 | 2021-02-05 | 9 | VP-095: FS, BA-022: FS, BA-010: FF, OP-290: FS, OP-300: FS | CES-190: SS 36, BA-030: FS | Standard
PER.BA | BA-030 | Permit | Finalize Admin Draft BA | 20 | 2021-02-08 | 2021-03-05 | 12 | BA-010: FS, BA-015: FS, BA-024: FS, BA-003: FS, BA-025: FS | BA-035: FS, BA-032: FF | Standard
PER.BA | BA-032 | Permit | Submit Final Admin Draft BA | 0 |  | 2021-03-05 | 12 | BA-030: FF | BA-035: FS | Standard
PER.BA | BA-035 | Permit | Independent Review Draft BA (Cal Days) | 30 | 2021-03-06 | 2021-04-04 | 18 | BA-030: FS, BA-032: FS | BA-055: SS, BA-057: FS | 7-Day Workweek | Needs to come after internal review
PER.BA | BA-055 | Permit | Reclamation, Legal, and Work Group Review | 30 | 2021-03-06 | 2021-04-04 | 18 | BA-035: SS | BA-057: FS, BA-075: FS | 7-Day Workweek
PER.BA | BA-057 | Permit | Revise Admin Draft BA | 30 | 2021-04-05 | 2021-05-14 | 14 | BA-055: FS, BA-035: FS | BA-075: FS, CES-030: FS, CES-210: FS, BA-060: FS | Standard
PER.BA | BA-060 | Permit | Submit Revised Admin Draft BA to Reclamation | 0 |  | 2021-05-14 | 32 | BA-057: FS | BA-075: FS | Standard
PER.BA | BA-075 | Permit | Final Reclamation and Solicitor Office Review | 30 | 2021-05-15 | 2021-06-13 | 47 | BA-055: FS, BA-057: FS, BA-060: FS | BA-1110: FS, BA-100: FF | 7-Day Workweek
PER.BA | BA-100 | Permit | Reclamation Submit BA to USFWS & NMFS | 0 |  | 2021-06-14 | 34 | BA-075: FF | BA-00-00: FF, BA-1110: FS | Standard
| BO Incidental Take Authorization |  |  | 135 | 2021-06-14 | 2021-10-26 | 48 |  |  | 7-Day Workweek
PER.BSA | BA-1110 | Permit | BO Incidental Take Authorization | 135 | 2021-06-14 | 2021-10-26 | 48 | BA-075: FS, BA-100: FS | ENG-399: FS | 7-Day Workweek
| ITP- CESA (Sec 2081) Operations |  |  | 292 | 2020-09-29 | 2021-11-19 | 14
PER.Ops | CES-180 | Permit | Operations Project Description | 30 | 2020-09-29 | 2020-11-09 | 45 | OP-230: FF, OP-290: FF, OP-300: FF | CES-190: FS, CES-00-10: SS | Standard |  | Assumes modeling can be completed within the schedule that will define operating criteria that is likely to be permitted by CDFW | operation changes, cost and schedule, higher mitigation costs | PMP to include conflict resolution process and timeframes to meet schedule
PER.Ops | CES-190 | Permit | Prepare Operations Analysis | 30 | 2021-01-05 | 2021-02-15 | 9 | BA-025: SS 36, CES-180: FS | CES-200: FS | Standard
PER.Ops | CES-200 | Permit | Mitigation Planning | 30 | 2021-02-16 | 2021-03-29 | 9 | CES-190: FS | 404-035: SS | Standard
PER.Ops | CES-210 | Permit | Prepare Draft ITP Application | 60 | 2021-05-17 | 2021-08-10 | 14 | VP-095: FS, BA-057: FS | CES-220: FS, CES-230: FS | Standard
PER.Ops | CES-220 | Permit | Legal Review of Draft ITP App | 30 | 2021-08-11 | 2021-09-09 | 20 | CES-210: FS | CES-240: FS | 7-Day Workweek
PER.Ops | CES-230 | Permit | Work Group Review of Draft ITP App | 30 | 2021-08-11 | 2021-09-09 | 20 | CES-210: FS | CES-240: FS | 7-Day Workweek
PER.Ops | CES-240 | Permit | Revise Draft ITP Application | 20 | 2021-09-09 | 2021-10-07 | 14 | CES-230: FS, CES-220: FS | CES-250: FS | Standard
PER.Ops | CES-250 | Permit | Authority Board Approval of ITP App | 30 | 2021-10-07 | 2021-11-18 | 14 | CES-240: FS | CES-260: FF 1 | Standard
PER.Ops | CES-260 | Permit | Submit ITP Application to CDFW | 0 |  | 2021-11-19 | 14 | CES-250: FF 1 | CES-00-10: FF, ENG-399: FS | Standard
| ITP- CESA (Sec 2081) Construction |  |  | 292 | 2020-09-29 | 2021-11-19 | 370
PER.Con | CES-015 | Permit | Initial Desktop Analysis | 30 | 2020-09-29 | 2020-11-09 | 572 | ENG-220: FS, VP-095: FS | CES-00-00: SS, CES-020: FS | Standard
PER.Con | CES-020 | Permit | Prepare Terrestrial Analysis | 30 | 2020-11-10 | 2020-12-23 | 572 | CES-015: FS | CES-025: FS | Standard
PER.Con | CES-025 | Permit | Mitigation Planning | 30 | 2020-12-24 | 2021-02-05 | 572 | CES-020: FS |  | Standard
PER.Con | CES-030 | Permit | Prepare Draft ITP Application | 60 | 2021-05-17 | 2021-08-10 | 14 | VP-095: FS, BA-057: FS | CES-040: FS, CES-060: FS | Standard
PER.Con | CES-040 | Permit | Legal Review of Draft ITP App | 30 | 2021-08-11 | 2021-09-09 | 20 | CES-030: FS | CES-070: FS | 7-Day Workweek
PER.Con | CES-060 | Permit | Work Group Review of Draft ITP App | 30 | 2021-08-11 | 2021-09-09 | 20 | CES-030: FS | CES-070: FS | 7-Day Workweek
PER.Con | CES-070 | Permit | Revise Draft ITP Application | 20 | 2021-09-09 | 2021-10-07 | 14 | CES-060: FS, CES-040: FS | CES-080: FS | Standard
PER.Con | CES-080 | Permit | Authority Board Approval of ITP App | 30 | 2021-10-07 | 2021-11-18 | 14 | CES-070: FS | CES-090: FF 1 | Standard
PER.Con | CES-090 | Permit | Submit ITP Application to CDFW | 0 |  | 2021-11-19 | 14 | CES-080: FF 1 | CES-00-00: FF, ENG-399: FS | Standard
| Section 106 |  |  | 318 | 2020-08-28 | 2021-11-30 | 365
PER.106 | 106-000 | Permit | Confirmation of Section 106 Federal Lead Agency | 0 |  | 2020-09-08 | 676 | 404-003: FS |  | Standard |  | This is a critical milestone that will determine approach for Section 106 consultation | change of federal lead agency, schedule | Develop an approach with Reclamation to confirm they have an undertaking
PER.106 | 106-001 | Permit | Prepare SHPO Initiation Package | 20 | 2020-08-28 | 2020-09-25 | 9 | PDE-60: FS | 106-00-00: SS, 106-002: FS | Standard
PER.106 | 106-002 | Permit | Authority/Reclamation/Integration Reviews | 10 | 2020-09-28 | 2020-10-09 | 9 | 106-001: FS | 106-003: FS | Standard
PER.106 | 106-003 | Permit | Management/Work Group Reviews | 10 | 2020-10-12 | 2020-10-23 | 9 | 106-002: FS | 106-004: FS | Standard
PER.106 | 106-004 | Permit | Revisions | 10 | 2020-10-26 | 2020-11-06 | 9 | 106-003: FS | 106-005: FF 5 | Standard
PER.106 | 106-005 | Permit | Reclamation Submits to SHPO | 0 |  | 2020-11-13 | 9 | 106-004: FF 5 | 106-006: FS | Standard
PER.106 | 106-006 | Permit | SHPO Review and comments | 30 | 2020-11-14 | 2020-12-13 | 17 | 106-005: FS | 106-021: FS | 7-Day Workweek
PER.106 | 106-021 | Permit | Prepare Consultation Information Package | 15 | 2020-12-14 | 2021-01-05 | 12 | 106-006: FS | 106-022: FS | Standard
PER.106 | 106-022 | Permit | Authority/Reclamation/Integration Reviews | 10 | 2021-01-06 | 2021-01-19 | 12 | 106-021: FS | 106-023: FS | Standard
PER.106 | 106-023 | Permit | Management/Work Group Reviews | 10 | 2021-01-20 | 2021-02-02 | 12 | 106-022: FS | 106-024: FS | Standard
PER.106 | 106-024 | Permit | Revisions | 10 | 2021-02-03 | 2021-02-16 | 12 | 106-023: FS | 106-025: FS, 106-032: FS | Standard
PER.106 | 106-025 | Permit | Reclamation Distributes to SHPO and Invited Consulting Parties | 5 | 2021-02-17 | 2021-02-23 | 23 | 106-024: FS | 106-026: FS, 106-033: FS | Standard
PER.106 | 106-026 | Permit | Parties Accept Invitation for Consulting Party Status | 30 | 2021-02-24 | 2021-03-25 | 45 | 106-025: FS | 106-052: FS | 7-Day Workweek
PER.106 | 106-032 | Permit | Arrange Meeting Logistics and Prepare Materials | 20 | 2021-02-17 | 2021-03-16 | 12 | 106-024: FS | 106-042: FS 6 | Standard
PER.106 | 106-033 | Permit | Conduct Meetings | 10 | 2021-02-24 | 2021-03-09 | 23 | 106-025: FS | 106-042: FS | Standard
PER.106 | 106-042 | Permit | Authority/Reclamation/Integration Reviews | 10 | 2021-03-25 | 2021-04-07 | 12 | 106-032: FS 6, 106-033: FS | 106-043: FS | Standard
PER.106 | 106-043 | Permit | Management/Work Group Reviews | 10 | 2021-04-08 | 2021-04-21 | 12 | 106-042: FS | 106-044: FS, 106-052: FS | Standard
PER.106 | 106-044 | Permit | Revisions | 10 | 2021-04-22 | 2021-05-05 | 26 | 106-043: FS | 106-061: FS | Standard
PER.106 | 106-052 | Permit | Circulate Draft PA to SHPO and Consulting Parties | 5 | 2021-04-22 | 2021-04-28 | 12 | 106-043: FS, 106-026: FS | 106-053: FS | Standard
PER.106 | 106-053 | Permit | Deadline for Comments on Draft PA | 30 | 2021-04-29 | 2021-05-28 | 16 | 106-052: FS | 106-061: FS | 7-Day Workweek
PER.106 | 106-061 | Permit | Prepare Draft Final PA | 20 | 2021-05-28 | 2021-06-28 | 9 | 106-053: FS, 106-044: FS | 106-062: FS | Standard
PER.106 | 106-062 | Permit | Authority/Reclamation/Integration Reviews | 10 | 2021-06-28 | 2021-07-13 | 9 | 106-061: FS | 106-063: FS | Standard
PER.106 | 106-063 | Permit | Management/Work Group Reviews | 10 | 2021-07-13 | 2021-07-27 | 9 | 106-062: FS | 106-064: FS | Standard
PER.106 | 106-064 | Permit | Revisions | 10 | 2021-07-27 | 2021-08-10 | 9 | 106-063: FS | 106-072: FS | Standard
PER.106 | 106-072 | Permit | Circulate Draft Final PA to SHPO and Consulting Parties | 5 | 2021-08-10 | 2021-08-17 | 9 | 106-064: FS | 106-071: SS, 106-073: FS | Standard
PER.106 | 106-073 | Permit | Deadline for Comments on Draft Final PA | 30 | 2021-08-18 | 2021-09-16 | 13 | 106-072: FS | 106-071: FF, 106-081: FS | 7-Day Workweek
PER.106 | 106-081 | Permit | Prepare Final PA | 15 | 2021-09-16 | 2021-10-07 | 9 | 106-073: FS | 106-082: FS | Standard
PER.106 | 106-082 | Permit | Authority/Reclamation/Integration Reviews | 10 | 2021-10-07 | 2021-10-21 | 9 | 106-081: FS | 106-083: FS | Standard
PER.106 | 106-083 | Permit | Management/Work Group Reviews | 10 | 2021-10-21 | 2021-11-04 | 9 | 106-082: FS | 106-084: FS | Standard
PER.106 | 106-084 | Permit | Revisions | 10 | 2021-11-04 | 2021-11-18 | 9 | 106-083: FS | 106-091: FS, 106-092: FS | Standard
PER.106 | 106-091 | Permit | Consult with SHPO and Consulting Parties on Final PA | 5 | 2021-11-18 | 2021-11-29 | 10 | 106-084: FS | 106-093: FS | Standard
PER.106 | 106-092 | Permit | Circulate Final PA to SHPO and Consulting Parties for Signatures | 5 | 2021-11-18 | 2021-11-29 | 9 | 106-084: FS | 106-093: FF 1 | Standard
PER.106 | 106-093 | Permit | Deadline for Signatures on Final PA | 0 |  | 2021-11-30 | 13 | 106-092: FF 1, 106-091: FS | 106-00-00: FF, ENG-399: FS | 7-Day Workweek
| Water Rights |  |  | 684 | 2020-08-27 | 2023-05-08 | 0
PER.Water R | WR-005 | Permit | Water Availability Analysis & Planning/Coordination with State/Local | 210 | 2020-08-27 | 2021-06-24 | 12 | WP-130: FS | WR-025: FS | Standard
PER.Water R | WR-025 | Permit | Prepare Water Right Application | 121 | 2021-07-09 | 2021-12-31 | 2 | PDE-60: FS, EIR-070: FS, WR-005: FS | WR-035: FS, WR-00-00: SS | Standard
PER.Water R | WR-035 | Permit | QA/QC and Legal Review of Draft Water Right Application | 15 | 2021-12-31 | 2022-01-24 | 2 | WR-025: FS | WR-045: FS | Standard
PER.Water R | WR-045 | Permit | Revise Draft Water Rights Application | 25 | 2022-01-24 | 2022-02-28 | 2 | WR-035: FS | WR-055: FS | Standard
PER.Water R | WR-055 | Permit | Work Group Review of Draft Water Right | 10 | 2022-02-28 | 2022-03-14 | 2 | WR-045: FS | WR-065: FS | Standard
PER.Water R | WR-065 | Permit | Resolve Work Group Comments | 10 | 2022-03-14 | 2022-03-28 | 2 | WR-055: FS | WR-075: FS | Standard
PER.Water R | WR-075 | Permit | Authority Approval of Water Right Appl, Submittal to SWRCB | 1 | 2022-03-28 | 2022-03-29 | 2 | WR-065: FS | WR-085: FS | Standard
PER.Water R | WR-085 | Permit | Submit Water Right Application | 0 |  | 2022-03-29 | 2 | WR-075: FS | WR-095: FS | Standard
PER.Water R | WR-095 | Permit | SWRCB Review of Water Right Application | 60 | 2022-03-30 | 2022-05-28 | 2 | WR-085: FS | WR-105: FS | 7-Day Workweek
PER.Water R | WR-105 | Permit | Receive Protests to Application | 44 | 2022-05-31 | 2022-08-01 | 0 | WR-095: FS | WR-115: FS, WR-115: FF | Standard
PER.Water R | WR-115 | Permit | Resolve Protests and Schedule Protest Hearing | 80 | 2022-08-02 | 2022-11-22 | 0 | WR-105: FS, WR-105: FF | WR-125: FS, WR-155: FS | Standard
PER.Water R | WR-125 | Permit | Notice Water Rights Hearing | 22 | 2022-11-23 | 2022-12-27 | 0 | WR-115: FS, EIR-130: FS | WR-135: FS, WR-145: FS 22 | Standard
PER.Water R | WR-135 | Permit | Conduct In-House Mock Water Right Hearing | 15 | 2022-12-28 | 2023-01-18 | 7 | WR-125: FS | WR-145: FS | Standard
PER.Water R | WR-145 | Permit | Conduct Water Right Hearing | 1 | 2023-01-30 | 2023-01-30 | 0 | WR-125: FS 22, WR-135: FS | WR-155: FS | Standard
PER.Water R | WR-155 | Permit | Negotiate Permit Terms | 44 | 2023-01-31 | 2023-03-31 | 0 | WR-115: FS, WR-145: FS | WR-165: FS | Standard
PER.Water R | WR-165 | Permit | SWRCB Prepare Draft Permit and CEQA Findings | 21 | 2023-04-03 | 2023-05-01 | 0 | WR-155: FS | WR-175: FS | Standard
PER.Water R | WR-175 | Permit | SWRCB Issue Water Right Permit | 5 | 2023-05-02 | 2023-05-08 | 0 | WR-165: FS | WR-185: FF | Standard
PER.Water R | WR-185 | Permit | Water Right Permit | 0 |  | 2023-05-08 | 0 | WR-175: FF | WR-00-00: FF | Standard
| Section 404 |  |  | 414 | 2020-04-14 | 2021-11-30 | 9
PER.404 | 404-001 | Permit | Agreement with Reclamation for LEDPA Analysis | 15 | 2020-04-14 | 2020-05-04 | 25 | VP-070: FS | 404-003: FS, 404-00-00: SS | Standard |  | Reclamation & USACE agree to LEDPA and 408 requirements for REIS | schedule | Separate NEPA doc for USACE
PER.404 | 404-003 | Permit | USACE LEDPA & NEPA , 404/408 and WD Approach | 88 | 2020-05-05 | 2020-09-08 | 25 | WP-020: FS, VP-070: FS, BA-019: FF, 404-001: FS | 404-050: FS, 404-010: FS, 401-130: FS, 401-120: FS, 106-000: FS | Standard
PER.404 | 404-010 | Permit | Desktop Wetland Delineation Analysis (includes Waters of the State) | 150 | 2020-09-29 | 2021-04-30 | 11 | 404-003: FS, ENG-220: FS | 404-050: FS, 404-020: FF 1, 401-130: FS | Standard
PER.404 | 404-020 | Permit | Submit Delineation to USACE | 0 |  | 2021-05-03 | 11 | 404-010: FF 1 | 404-030: FS | Standard
PER.404 | 404-025 | Permit | Pre-Application Meeting | 1 | 2021-06-01 | 2021-06-01 | 53 | 404-030: SS 27 | 404-050: FS | Standard
PER.404 | 404-030 | Permit | Preliminary Wetland Delineation Acceptance | 90 | 2021-05-04 | 2021-08-01 | 15 | 404-020: FS | 404-050: FS, 401-130: FS, 404-025: SS 27 | 7-Day Workweek
PER.404 | 404-035 | Permit | Compensatory Mitigation Plan | 161 | 2021-02-16 | 2021-10-01 | 9 | CES-200: SS | 404-060: FS | Standard
PER.404 | 404-050 | Permit | Prepare Draft 404 Application | 42 | 2021-08-02 | 2021-09-29 | 11 | 404-003: FS, 404-010: FS, 404-030: FS, 404-025: FS | 404-060: FS | Standard
PER.404 | 404-060 | Permit | Authority/Integration/Work Group Review of Draft 404 | 20 | 2021-10-04 | 2021-10-29 | 9 | 404-050: FS, 404-035: FS | 404-070: FS | Standard
PER.404 | 404-070 | Permit | Prepare Final 404 Application | 20 | 2021-11-01 | 2021-11-30 | 9 | 404-060: FS | 404-120: FS | Standard
PER.404 | 404-120 | Permit | Submit 404 Application | 0 |  | 2021-11-30 | 9 | 404-070: FS | 404-00-00: FF, ENG-399: FS | Standard
| Section 408 |  |  | 600 | 2020-04-14 | 2022-08-23 | 179 |  |  | Standard
PER.408 | 408-005 | Permit | Coordinate with CVFPB and USACE | 20 | 2020-04-14 | 2020-05-11 | 466 | VP-070: FS | 408-00-00: SS, 408-010: FS, 408-130: FS | Standard
PER.408 | 408-010 | Permit | Assume Start of 50% Design of 408 Jurisdictional Features | 0 |  | 2021-06-28 | 179 | 408-005: FS, ENG-390: FS | 408-130: FS | Standard
PER.408 | 408-130 | Permit | Prepare Draft Encroachment Permit/408 Request w/Engineering Team | 129 | 2021-06-29 | 2021-12-31 | 179 | 408-005: FS, 408-010: FS | 408-135: FS | Standard
PER.408 | 408-135 | Permit | Continue Draft Encroachment Permit/408 Request w/Engineering Team | 124 | 2022-01-04 | 2022-06-27 | 179 | 408-130: FS | 408-140: FS | Standard
PER.408 | 408-140 | Permit | Authority/Integration/Work Group Review of Draft | 20 | 2022-06-28 | 2022-07-26 | 179 | 408-135: FS | 408-150: FS | Standard
PER.408 | 408-150 | Permit | Prepare Encroachment Permit/408 Request | 20 | 2022-07-27 | 2022-08-23 | 179 | 408-140: FS | 408-160: FS | Standard |  | 65% drawings are available | schedule | move permit to later timeframe
PER.408 | 408-160 | Permit | Submit Encroachment Permit/408 Request | 0 |  | 2022-08-23 | 179 | 408-150: FS | 408-00-00: FF | Standard
| Section 401 Water Quality |  |  | 309 | 2020-09-09 | 2021-11-24 | 11 |  |  | Standard
PER.401 | 401-120 | Permit | Coordinate with RWQCB and SWRCB | 84 | 2020-09-09 | 2021-01-08 | 154 | 404-003: FS | 401-00-00: SS, 401-130: FS | Standard
PER.401 | 401-130 | Permit | Prepare Draft 401 Application | 42 | 2021-08-02 | 2021-09-29 | 11 | 404-003: FS, 404-010: FS, 404-030: FS, WP-130: FS, 401-120: FS | 401-140: FS | Standard
PER.401 | 401-140 | Permit | Authority/Integration/Work Group Review of Draft 401 | 20 | 2021-09-30 | 2021-10-27 | 11 | 401-130: FS | 401-150: FS | Standard
PER.401 | 401-150 | Permit | Prepare Final 401 Application | 20 | 2021-10-28 | 2021-11-24 | 11 | 401-140: FS | 401-160: FS | Standard
PER.401 | 401-160 | Permit | Submit 401 Application | 0 |  | 2021-11-24 | 11 | 401-150: FS | 401-00-00: FF, ENG-399: FS | Standard
| Engineering |  |  | 508 | 2020-01-02 | 2021-12-30 | 344 |  |  | Standard
| Feasibility-Level Geotech |  |  | 508 | 2020-01-02 | 2021-12-30 | 344 |  |  | Standard
Eng.Geo | GSR-000 | Geo | Continuted Geotechnical Support for Reclamation | 171 | 2020-01-02 | 2020-08-31 | 344 |  | GPP-00-00: SS, GSR-010: FS | Standard
Eng.Geo | GSR-010 | Geo | Geotechnical Permitting & Planning, Right of Access | 61 | 2020-09-01 | 2020-11-25 | 344 | WP-130: FS, GSR-000: FS | GSR-020: FS | Standard
Eng.Geo | GSR-020 | Geo | Conduct Geotechnical Field Investigation | 85 | 2020-11-30 | 2021-03-30 | 344 | GSR-010: FS | GSR-030: SS 42 | Standard
Eng.Geo | GSR-030 | Geo | Data Evaluation and Prepare Geotechnical Data Reports | 107 | 2021-01-29 | 2021-06-29 | 344 | GSR-020: SS 42 | GSR-040: FS -22, GPP-00-00: FF | Standard
Eng.Geo | GSR-040 | Geo | Data Gap Assessment and Preliminary Planning for Design Level Inv for Preferred Alt | 149 | 2021-05-28 | 2021-12-30 | 344 | GSR-030: FS -22 |  | Standard
| Support of Project Description |  |  | 449 | 2020-03-24 | 2021-12-30 | 344 |  |  | Standard
Eng.Des | ENG-110 | Eng | Engineering Consultants Brought On Board (complete prior to Sept 1) | 0 |  | 2020-03-24 | 14 | RCB-20-038: FS, PA-030: FS | ENG-120: FS | Standard
Eng.Des | ENG-120 | Eng | Coordination of CADD and GIS Standards | 20 | 2020-03-25 | 2020-04-21 | 14 | RCB-20-038: FS, ENG-110: FS | ENG-190: FS | Standard
Eng.Des | ENG-130 | Eng | Coordination to Identify Alternatives for EIR/EIS & Related Studies | 5 | 2020-04-14 | 2020-04-20 | 4 | RCB-20-038: FS, VP-095: FS | ENG-190: FS, PDE-40: FS | Standard
Eng.Des | ENG-140 | Eng | Coordination to Finalize Storage & Conveyance Capacities | 5 | 2020-03-25 | 2020-03-31 | 29 | RCB-20-038: FS, OP-005: FS | ENG-300: FS, ENG-190: FS | Standard
Eng.Des | ENG-150 | Eng | Gather Data from Prior Draft EIR/EIS | 10 | 2020-03-25 | 2020-04-07 | 19 | RCB-20-038: FS | ENG-160: FF, ENG-300: FS | Standard
Eng.Des | ENG-160 | Eng | Prepare Project Base Map | 20 | 2020-03-25 | 2020-04-21 | 9 | ENG-150: FF, RCB-20-038: FS | ENG-170: SS, ENG-180: FS | Standard
Eng.Des | ENG-170 | Eng | Prepare Basis of Feasibility Design | 10 | 2020-03-25 | 2020-04-07 | 24 | ENG-160: SS | ENG-190: FS | Standard
Eng.Des | ENG-180 | Eng | Conduct Field Reviews (as needed) | 5 | 2020-04-22 | 2020-04-28 | 9 | ENG-160: FS | ENG-190: FS | Standard
Eng.Des | ENG-190 | Eng | Complete Feasibility Level Design | 85 | 2020-04-29 | 2020-08-27 | 9 | ENG-180: FS, ENG-170: FS, ENG-120: FS, ENG-130: FS, ENG-140: FS | ENG-200: FF, ENG-210: FS, PDE-60: FS | Standard
Eng.Des | ENG-200 | Eng | Develop CADD Drawings of Key Features | 85 | 2020-04-29 | 2020-08-27 | 9 | ENG-190: FF | ENG-210: FS, ENG-220: FS, PDE-60: FS | Standard
Eng.Des | ENG-210 | Eng | Provide Information on Key Project Features & Facilities | 21 | 2020-08-28 | 2020-09-28 | 128 | ENG-200: FS, ENG-190: FS | ENG-380: FS | Standard
Eng.Des | ENG-220 | Eng | Convert Drawings to GIS Geodatabase File Format to Support Environmental & Permitting | 21 | 2020-08-28 | 2020-09-28 | 11 | ENG-200: FS | ENG-230: FS, BA-001: FS, CES-015: FS, 404-010: FS, EIR-019: FF | Standard
Eng.Des | ENG-230 | Eng | Support to Environmental and Permitting Team | 318 | 2020-09-29 | 2021-12-30 | 344 | ENG-220: FS |  | Standard
Eng.Des | ENG-233 | Eng | Engineering Support for Alternative A | 131 | 2020-06-03 | 2020-12-08 | 613 | RCB-20-038: FS, PDE-40: FS |  | Standard
Eng.Des | ENG-236 | Eng | Engineering Support for Modified Alternative A | 131 | 2020-06-03 | 2020-12-08 | 613 | RCB-20-038: FS, PDE-40: FS |  | Standard
| Authority Feasibility Report |  |  | 326 | 2020-03-25 | 2021-07-06 | 111 |  |  | Standard
| Cost Estimate, Feasibility, Constructability |  |  | 246 | 2020-03-25 | 2021-03-12 | 191 |  |  | Standard
Fea.Ana | ENG-240 | Eng | Identify Project Objectives | 11 | 2020-03-25 | 2020-04-08 | 126 | RCB-20-038: FS | ENG-250: FS, ENG-00-00: SS | Standard
Fea.Ana | ENG-250 | Eng | Feasibility Project Description | 0 |  | 2020-08-27 | 27 | PDE-60: FF, ENG-240: FS, OP-070: FS | ENG-300: FS 11, ENG-270: FS 25, ENG-330: FS | Standard
Fea.Ana | ENG-260 | Eng | Obtain Operations Simulation Results of Preferred Option | 0 |  | 2020-11-09 | 13 | OP-315: FF | ENG-300: FS, ENG-310: FS | Standard
Fea.Ana | ENG-270 | Eng | Develop Costs Associated with Mitigation Measures | 15 | 2020-10-05 | 2020-10-23 | 27 | ENG-250: FS 25 | ENG-280: FS, ENG-290: FS, ENG-380: FS | Standard
Fea.Ana | ENG-280 | Eng | Develop Class 4 Cost Estimate (State Feasibility) | 42 | 2020-10-26 | 2020-12-24 | 27 | ENG-270: FS | ENG-300: FF | Standard
Fea.Ana | ENG-290 | Eng | Risk and Uncertainty Assessment | 20 | 2020-10-26 | 2020-11-20 | 49 | ENG-270: FS | ENG-300: FF | Standard
Fea.Ana | ENG-300 | Eng | Confirm Project Benefits | 45 | 2020-11-10 | 2021-01-15 | 13 | ENG-250: FS 11, ENG-140: FS, ENG-150: FS, ENG-260: FS, ENG-280: FF, ENG-290: FF | ENG-320: FS | Standard
Fea.Ana | ENG-310 | Eng | Project Benefits Consist with the Ops Plan | 41 | 2020-11-10 | 2021-01-11 | 17 | ENG-260: FS | ENG-370: FS, ENG-320: FS | Standard
Fea.Ana | ENG-320 | Eng | Cost Allocation | 20 | 2021-01-18 | 2021-02-12 | 13 | ENG-310: FS, ENG-300: FS | ENG-370: FS, ENG-350: FS, ENG-360: FS | Standard
Fea.Ana | ENG-330 | Eng | Technical Feasibility | 20 | 2020-08-28 | 2020-09-25 | 93 | ENG-250: FS | ENG-340: FS 15, ENG-380: FS | Standard
Fea.Ana | ENG-340 | Eng | Obtain the Finding of Env Feasibility with Mitigation | 21 | 2020-10-19 | 2020-11-16 | 93 | ENG-330: FS 15 | ENG-380: FS | Standard
Fea.Ana | ENG-350 | Eng | Economic Feasibility | 5 | 2021-02-15 | 2021-02-19 | 28 | ENG-320: FS | ENG-380: FS | Standard
Fea.Ana | ENG-360 | Eng | Financial Feasibility | 20 | 2021-02-15 | 2021-03-12 | 13 | ENG-320: FS | ENG-380: FS | Standard
Fea.Ana | ENG-370 | Eng | Constructability | 20 | 2021-02-15 | 2021-03-12 | 13 | ENG-320: FS, ENG-310: FS | ENG-380: FS | Standard
Fea.Ana | ENG-400 | Eng | Develop DSOD Engagement Plan | 20 | 2020-08-27 | 2020-09-24 | 308 | WP-130: FS | ENG-399: FS | Standard
Fea.Ana | ENG-404 | Eng | Coordinate on a Geotechnical Investigation Plan | 20 | 2020-08-27 | 2020-09-24 | 308 | WP-130: FS | ENG-399: FS | Standard
Fea.Ana | ENG-406 | Eng | Coordinate to Develop Geotechnical Permitting Plan | 20 | 2020-08-27 | 2020-09-24 | 308 | WP-130: FS | ENG-399: FS | Standard
Fea.Ana | ENG-410 | Eng | Develop Program Design/Construction/Permit Implementation Plan | 20 | 2020-08-27 | 2020-09-24 | 308 | WP-130: FS | ENG-399: FS | Standard
Fea.Ana | ENG-420 | Eng | Develop Sites Local Operations Model (LOM) | 63 | 2020-08-27 | 2020-11-24 | 265 | WP-130: FS | ENG-399: FS | Standard
| Feasibility Report |  |  | 80 | 2021-03-15 | 2021-07-06 | 6 |  |  | Standard
Fea.Repo | ENG-380 | Eng | Prepare Draft Feasibility Report | 30 | 2021-03-15 | 2021-04-23 | 13 | ENG-270: FS, ENG-210: FS, ENG-350: FS, ENG-340: FS, ENG-360: FS, ENG-330: FS, ENG-370: FS | ENG-390: FS, ENG-385: FS | Standard
Fea.Repo | ENG-385 | Eng | Work Group Review | 5 | 2021-04-26 | 2021-04-30 | 13 | ENG-380: FS | ENG-390: FS | Standard
Fea.Repo | ENG-390 | Eng | Prepare Final Feasibility Report | 33 | 2021-05-12 | 2021-06-28 | 6 | ENG-380: FS, ENG-385: FS, OP-350: FF, OP-360: FF | ENG-395: FS, ENG-392: FS, ENG-00-00: FF, 408-010: FS | Standard
Fea.Repo | ENG-392 | Eng | Reservoir Committee and Board Approval | 5 | 2021-06-29 | 2021-07-06 | 6 | ENG-390: FS | ENG-395: FS | Standard
| Prop 1 |  |  | 106 | 2021-07-13 | 2021-12-13 | 1
| CWC Feasibility Review |  |  | 152 | 2021-07-13 | 2021-12-11 | 2 |  |  | 7-Day Workweek
Prop1.Rev | ENG-395 | Eng | CWC Review | 152 | 2021-07-13 | 2021-12-11 | 2 | ENG-390: FS, ENG-392: FS, EIR-080: FS | ENG-399: FS | 7-Day Workweek
| CWC Determination |  |  | 0 | 2021-12-13 | 2021-12-13 | 1 |  |  | Standard
Prop1.State | ENG-399 | Eng | State Determination of Feasibility | 0 |  | 13-Dec-21* | 1 | ENG-395: FS, EIR-120: FS, ENG-420: FS, ENG-410: FS, ENG-406: FS, ENG-404: FS, ENG-400: FS, OP-070: FS, 106-093: FS, CES-090: FS, CES-260: FS, 404-120: FS, 401-160: FS, OP-330: FS, BA-1110: FS |  | Standard
| Organizational Assessment |  |  | 171 | 2020-01-02 | 2020-08-31 | 681 |  |  | Standard
Org Ass | OA-000 | ONG | Organizational Assessment Direction | 171 | 2020-01-02 | 2020-08-31 | 681 |  |  | Standard
| Communications & Gov't Affairs |  |  | 509 | 2020-01-02 | 2021-12-31 | 343 |  |  | Standard
Comm | CG-000 | Com | Communication & Government Affairs | 171 | 2020-01-02 | 2020-08-31 | 343 |  | CG-10: FS | Standard
Comm | CG-10 | Com | Communication & Government Affairs | 338 | 2020-09-01 | 2021-12-31 | 343 | CG-000: FS |  | Standard
| Ongoing Business |  |  | 509 | 2020-01-02 | 2021-12-31 | 343
Busines | OB-00-20 | ONG | Contract Amendments | 20 | 2020-01-02 | 2020-01-29 | 832 |  |  | Standard
Busines | OB-010 | ONG | Accounts Payable & Accounts Receivable | 171 | 2020-01-02 | 2020-08-31 | 343 |  | OB-012: FS | Standard
Busines | OB-012 | ONG | Accounts Payable & Accounts Receivable | 338 | 2020-09-01 | 2021-12-31 | 343 | OB-010: FS |  | Standard
Busines | OB-022 | ONG | Revise Service Area Task Orders for Approval | 20 | 2020-02-04 | 2020-03-02 | 10 | WP-015: FS | RCB-20-030: FS | Standard
Busines | OB-032 | ONG | Prepare 4Q2019 CWC invoice | 17 | 16-Jan-20* | 2020-02-07 | 825 |  | OB-00-30: SS | Standard
Busines | OB-033 | ONG | Prepare Q12020 CWC invoice | 18 | 16-Jan-20* | 2020-02-10 | 824 |  | OB-00-30: FF | Standard
Busines | OB-040 | ONG | Monthly Board/Res Comm Support | 171 | 2020-01-02 | 2020-08-31 | 343 |  | OB-042: FS | Standard
Busines | OB-042 | ONG | Monthly Board/Res Comm Support | 338 | 2020-09-01 | 2021-12-31 | 343 | OB-040: FS |  | Standard
Busines | OB-052 | ONG | Quarterly Reporting | 509 | 2020-01-02 | 2021-12-31 | 343 |  |  | Standard
Busines | OB-062 | ONG | Annual Reporting | 509 | 2020-01-02 | 2021-12-31 | 343 |  |  | Standard
Busines | OB-200 | ONG | Real Estate Landowner Coordination | 171 | 2020-01-02 | 2020-08-31 | 681 |  |  | Standard
| Financial Assistance Agreement |  |  | 55 | 2020-01-14 | 2020-03-30 | 35 |  |  | Standard
Busines.Fin App | FAA-005 | Fin | Prepare Draft FA Scope and Form 424 | 15 | 2020-01-14 | 2020-02-03 | 35 | VP-001: FS 5 | FAA-010: FS, FAA-00-00: SS | Standard
Busines.Fin App | FAA-010 | Fin | Review Scope with USBR | 5 | 2020-02-04 | 2020-02-10 | 35 | FAA-005: FS | FAA-015: FS | Standard
Busines.Fin App | FAA-015 | Fin | Prepare Budget Estimates, Narrative and Form 424A/B, SFLLL | 15 | 2020-02-11 | 2020-03-02 | 35 | FAA-010: FS | FAA-020: FS | Standard
Busines.Fin App | FAA-020 | Fin | Review with USBR | 10 | 2020-03-03 | 2020-03-16 | 35 | FAA-015: FS | FAA-025: FS | Standard
Busines.Fin App | FAA-025 | Fin | Finalize Draft FA | 10 | 2020-03-17 | 2020-03-30 | 35 | FAA-020: FS | RCB-20-050: FS, FAA-00-00: FF | Standard
| Plan of Finance |  |  | 319 | 2020-04-30 | 2021-08-02 | 448 |  |  | Standard
Busines.Finan | POF-005 | Fin | Plan of Finance Update 1 (Update Affordability) | 0 | 30-Apr-20* |  | 767 |  | POF-00-00: SS | Standard
Busines.Finan | POF-010 | Fin | Plan of Finance (Fin Feas) | 0 | 01-Mar-21* |  | 557 |  |  | Standard
Busines.Finan | POF-015 | Fin | Plan of Finance (WIFIA Loan) | 0 | 01-Apr-21* |  | 534 |  |  | Standard
Busines.Finan | POF-020 | Fin | WIFIA/LOI | 0 | 30-Jun-21* |  | 471 |  |  | Standard
Busines.Finan | POF-025 | Fin | Plan of Finance (Home Board Pkg) | 0 |  | 02-Aug-21* | 448 |  | POF-00-00: FF | Standard
| WIFIA Loan Application |  |  | 75 | 2020-01-20 | 2020-05-01 | 11 |  |  | Standard
Busines.WIFIA | WL-005 | Fin | Prepare Initial Loan Application | 20 | 20-Jan-20* | 2020-02-14 | 11 |  | WL-010: FS, WL-00-00: SS | Standard
Busines.WIFIA | WL-010 | Fin | Review Loan Application | 35 | 2020-02-17 | 2020-04-03 | 11 | WL-005: FS | WL-015: FS | Standard
Busines.WIFIA | WL-015 | Fin | Prepare Loan Application for Facilities | 20 | 2020-04-06 | 2020-05-01 | 11 | WL-010: FS | RCB-20-050: FS, WL-00-00: FF | Standard
| Risk Assessment |  |  | 195 | 2020-02-25 | 2020-11-30 | 619 |  |  | Standard
Busines.Risk | RA-005 | ONG | Risk Analysis of Recommend Option Meeting | 40 | 2020-02-25 | 2020-04-20 | 764 | VP-013: FS | RA-010: FS, RA-00-1B: SS | Standard
Busines.Risk | RA-010 | ONG | Prepare Cost Risk Update | 10 | 2020-04-21 | 2020-05-04 | 764 | RA-005: FS | RA-00-1B: FF | Standard
Busines.Risk | RA-020 | ONG | Prepare RA | 66 | 2020-08-26 | 30-Nov-20* | 619 |  | RA-030: FS, RA-00-2A: SS | Standard
Busines.Risk | RA-030 | ONG | Submit Admin Final RA | 0 |  | 30-Nov-20* | 619 | RA-020: FS | RA-00-2A: FF | Standard
| General Counsel |  |  | 509 | 2020-01-02 | 2021-12-31 | 343 |  |  | Standard
Busines.Gen Cou | GC-000 | ONG | General Counsel | 171 | 2020-01-02 | 2020-08-31 | 343 |  | GC-10: FS | Standard
Busines.Gen Cou | GC-10 | ONG | General Counsel | 338 | 2020-09-01 | 2021-12-31 | 343 | GC-000: FS |  | Standard
| Cost of Year Deliveries |  |  | 51 | 2020-01-02 | 2020-03-12 | 2 |  |  | Standard
Busines.Cost YD | CYD-005 | Ops | Prepare Progress Report | 30 | 2020-01-02 | 2020-02-12 | 2 |  | CYD-015: FS, CYD-010: FS, CYD-00-00: SS | Standard
Busines.Cost YD | CYD-010 | Ops | In-progress Briefing | 1 | 2020-02-13 | 2020-02-13 | 3 | CYD-005: FS | RCB-20-020: FF | Standard
Busines.Cost YD | CYD-015 | Ops | Prepare Final Report | 20 | 2020-02-13 | 2020-03-11 | 2 | CYD-005: FS | CYD-020: FS | Standard
Busines.Cost YD | CYD-020 | Ops | In-progress Briefing | 1 | 2020-03-12 | 2020-03-12 | 2 | CYD-015: FS | RCB-20-030: FF, CYD-00-00: FF | Standard
| Goverance Meetings |  |  | 238 | 2020-01-14 | 2020-12-18 | 605 |  |  | Standard
| Board Materials Uploaded |  |  | 234 | 2020-01-14 | 2020-12-14 | 1 |  |  | Standard
Gov.Web | RCB-20-010 | Gov | January 2020 Meeting Materials Due | 0 |  | 14-Jan-20* | 0 | WP-005: FS | RCB-20-014: FS 2, RCB-20-020: FS 25 | Standard
Gov.Web | RCB-20-020 | Gov | February 2020 Meeting Materials Due | 0 |  | 18-Feb-20* | 0 | WP-015: FS, CYD-010: FF, WP-020: FS, WP-040: FF, RCB-20-010: FS 25 | RCB-20-024: FS 2, RCB-20-030: FS 9 | Standard
Gov.Web | RCB-20-030 | Gov | March 2020 Meeting Materials Due | 0 |  | 13-Mar-20* | 1 | OB-022: FS, CYD-020: FF, VP-025: FS, RCB-20-020: FS 9, WP-095: FS | RCB-20-034: FS 2, RCB-20-040: FS 18, WP-110: FS | Standard
Gov.Web | RCB-20-040 | Gov | April 2020 Meeting Materials Due | 0 |  | 13-Apr-20* | 0 | VP-090: FF, RCB-20-030: FS 18, VP-095: FS | RCB-20-044: FS 2, PA-020: FF -4, PA-120: FF -4, RCB-20-050: FS 25 | Standard
Gov.Web | RCB-20-050 | Gov | May 2020 Meeting Materials Due | 0 |  | 18-May-20* | 0 | FAA-025: FS, WL-015: FS, RCB-20-040: FS 25 | RCB-20-054: FS 2, RCB-20-060: FS 19 | Standard
Gov.Web | RCB-20-060 | Gov | June Meeting Materials Due | 0 |  | 15-Jun-20* | 1 | RCB-20-050: FS 19 | RCB-20-064: FS 2, RCB-20-070: FS 18 | Standard
Gov.Web | RCB-20-070 | Gov | July Meeting Materials Due | 0 |  | 10-Jul-20* | 1 | OP-020: FS, RCB-20-060: FS 18, PA-150: FS | RCB-20-074: FS 2, RCB-20-080: FS 26 | Standard
Gov.Web | RCB-20-080 | Gov | August Meeting Materials Due | 0 |  | 17-Aug-20* | 1 | RCB-20-070: FS 26 | RCB-20-084: FS 2, RCB-20-090: FS 18 | Standard
Gov.Web | RCB-20-090 | Gov | September Meeting Materials Due | 0 |  | 11-Sep-20* | 1 | RCB-20-080: FS 18 | RCB-20-094: FS 2, RCB-20-100: FS 21 | Standard
Gov.Web | RCB-20-100 | Gov | October Meeting Materials Due | 0 |  | 12-Oct-20* | 1 | RCB-20-090: FS 21 | RCB-20-104: FS 2, RCB-20-110: FS 24 | Standard
Gov.Web | RCB-20-110 | Gov | November Meeting Materials Due | 0 |  | 13-Nov-20* | 1 | RCB-20-100: FS 24 | RCB-20-114: FS 2, RCB-20-120: FS 19 | Standard
Gov.Web | RCB-20-120 | Gov | December Meeting Materials Due | 0 |  | 14-Dec-20* | 1 | RCB-20-110: FS 19 | RCB-20-124: FS | Standard
| Reservoir Committee Meetings |  |  | 233 | 2020-01-17 | 2020-12-15 | 606 |  |  | Standard
Gov.ResCom | RCB-20-014 | Gov | January 2020 Reservoir Committee Meeting | 1 | 2020-01-17 | 2020-01-17 | 3 | RCB-20-010: FS 2 | RCB-20-018: FS 2 | Standard
Gov.ResCom | RCB-20-024 | Gov | February 2020 Reservoir Committee Meeting | 1 | 2020-02-21 | 2020-02-21 | 1 | RCB-20-020: FS 2 | RCB-20-028: FS 2, WP-060: FS, WP-070: FS, WP-090: FS | Standard
Gov.ResCom | RCB-20-034 | Gov | March 2020 Reservoir Committee Meeting | 1 | 2020-03-18 | 2020-03-18 | 9 | RCB-20-030: FS 2 | RCB-20-038: FS 3 | Standard
Gov.ResCom | RCB-20-044 | Gov | April 2020 Reservoir Committee Meeting | 1 | 2020-04-16 | 2020-04-16 | 8 | RCB-20-040: FS 2 | RCB-20-048: FS 2, PA-130: FS | Standard
Gov.ResCom | RCB-20-054 | Gov | May 2020 Reservoir Committee Meeting | 1 | 2020-05-21 | 2020-05-21 | 748 | RCB-20-050: FS 2 | RCB-20-058: FS 2 | Standard
Gov.ResCom | RCB-20-064 | Gov | June 2020 Reservoir Committee Meeting | 1 | 2020-06-18 | 2020-06-18 | 60 | RCB-20-060: FS 2 | RCB-20-068: FS 2, WP-120: FF | Standard
Gov.ResCom | RCB-20-074 | Gov | July 2020 Reservoir Committee Meeting | 1 | 2020-07-15 | 2020-07-15 | 710 | RCB-20-070: FS 2 | RCB-20-078: FS 3 | Standard
Gov.ResCom | RCB-20-084 | Gov | August 2020 Reservoir Committee Meeting | 1 | 2020-08-20 | 2020-08-20 | 12 | RCB-20-080: FS 2 | RCB-20-088: FS 2, PA-160: FS 4 | Standard
Gov.ResCom | RCB-20-094 | Gov | September 2020 Reservoir Committee Meeting | 1 | 2020-09-16 | 2020-09-16 | 666 | RCB-20-090: FS 2 | RCB-20-098: FS 3 | Standard
Gov.ResCom | RCB-20-104 | Gov | October 2020 Reservoir Committee Meeting | 1 | 2020-10-15 | 2020-10-15 | 646 | RCB-20-100: FS 2 | RCB-20-108: FS 2 | Standard
Gov.ResCom | RCB-20-114 | Gov | November 2020 Reservoir Committee Meeting | 1 | 2020-11-18 | 2020-11-18 | 623 | RCB-20-110: FS 2 | RCB-20-118: FS 1 | Standard
Gov.ResCom | RCB-20-124 | Gov | December 2020 Reservoir Committee Meeting | 1 | 2020-12-15 | 2020-12-15 | 605 | RCB-20-120: FS | RCB-20-128: FS 2 | Standard
| Authority Board Meetings |  |  | 233 | 2020-01-22 | 2020-12-18 | 605 |  |  | Standard
Gov.Board | RCB-20-018 | Gov | January 2020 Authority Board Meeting | 1 | 2020-01-22 | 2020-01-22 | 3 | RCB-20-014: FS 2 | PA-010: FS, WP-040: FS 3, WP-055: FS 3 | Standard
Gov.Board | RCB-20-028 | Gov | February 2020 Authority Board Meeting | 1 | 2020-02-26 | 2020-02-26 | 89 | RCB-20-024: FS 2 | WP-025: FF | Standard
Gov.Board | RCB-20-038 | Gov | March 2020 Authority Board Meeting | 1 | 2020-03-24 | 2020-03-24 | 9 | RCB-20-034: FS 3 | ENG-120: FS, ENG-130: FS, ENG-140: FS, ENG-150: FS, ENG-160: FS, ENG-233: FS, ENG-236: FS, ENG-240: FS, ENG-110: FS | Standard
Gov.Board | RCB-20-048 | Gov | April 2020 Authority Board Meeting | 1 | 2020-04-21 | 2020-04-21 | 773 | RCB-20-044: FS 2 |  | Standard
Gov.Board | RCB-20-058 | Gov | May 2020 Authority Board Meeting | 1 | 2020-05-27 | 2020-05-27 | 748 | RCB-20-054: FS 2 |  | Standard
Gov.Board | RCB-20-068 | Gov | June 2020 Authority Board Meeting | 1 | 2020-06-23 | 2020-06-23 | 729 | RCB-20-064: FS 2 |  | Standard
Gov.Board | RCB-20-078 | Gov | July 2020 Authority Board Meeting | 1 | 2020-07-21 | 2020-07-21 | 710 | RCB-20-074: FS 3 |  | Standard
Gov.Board | RCB-20-088 | Gov | August 2020 Authority Board Meeting | 1 | 2020-08-25 | 2020-08-25 | 685 | RCB-20-084: FS 2 |  | Standard
Gov.Board | RCB-20-098 | Gov | September 2020 Authority Board Meeting | 1 | 2020-09-22 | 2020-09-22 | 666 | RCB-20-094: FS 3 |  | Standard
Gov.Board | RCB-20-108 | Gov | October 2020 Authority Board Meeting | 1 | 2020-10-20 | 2020-10-20 | 646 | RCB-20-104: FS 2 |  | Standard
Gov.Board | RCB-20-118 | Gov | November 2020 Authority Board Meeting | 1 | 2020-11-20 | 2020-11-20 | 623 | RCB-20-114: FS 1 |  | Standard
Gov.Board | RCB-20-128 | Gov | December 2020 Authority Board Meeting | 1 | 2020-12-18 | 2020-12-18 | 605 | RCB-20-124: FS 2 |  | Standard

## Cost
WP Amend Tasks | Activity ID | Activity Name | Ori Dur | Start | Finish | Total Float | Budgeted Total Cost | Assumptions | Risk | Mitigation
Total |  |  | 852 | 2020-01-02 | 2023-05-08 | 0 | 9770000
Environmental |  |  | 552 | 2020-01-02 | 2022-03-03 | 779 | 3450000
Value Planning Analysis |  |  | 37 | 2020-01-02 | 2020-02-21 | 15 | 0
1B | VP-007 | Qualitative Env Screening | 37 | 2020-01-02 | 2020-02-21 | 15 | 0
Determine Needs |  |  | 56 | 2020-02-11 | 2020-04-28 | 9 | 0
1B | PDE-10 | Environmental Planning Needs | 56 | 2020-02-11 | 2020-04-28 | 9 | 0
Components |  |  | 47 | 2020-04-14 | 2020-06-18 | 60 | 0
1B | PDE-40 | Identify Alternatives for EIR/EIS | 30 | 2020-04-21 | 2020-06-02 | 4 | 0
1B | PDE-45 | Identify Project-Level vs Program Components (Planning) | 47 | 2020-04-14 | 2020-06-18 | 60 | 0
Develop Project Description |  |  | 85 | 2020-04-29 | 2020-08-27 | 9 | 0
1B | PDE-50 | Develop Project Description Construction | 85 | 2020-04-29 | 2020-08-27 | 9 | 0
Project Description Complete |  |  | 0 | 2020-08-27 | 2020-08-27 | 9 | 0
1B | PDE-60 | Project Description | 0 |  | 2020-08-27 | 9 | 0
Work Plan & Outline |  |  | 148 | 2020-02-11 | 2020-09-08 | 4 | 0
1B | EIR-001 | Prepare EIR/EIS Work Plan | 46 | 2020-02-11 | 2020-04-14 | 38 | 0
1B | EIR-010 | Prepare Annotated Outline | 68 | 2020-06-03 | 2020-09-08 | 4 | 0
Draft EIR/EIS |  |  | 213 | 2020-09-09 | 2021-07-12 | 2 | 2800000
2A | EIR-019 | Prepare Revised Draft EIR/S (Construction) | 80 | 2020-09-09 | 2021-01-04 | 4 | 0
2A | EIR-020 | Prepare Revised Draft EIR (Operations) | 65 | 2021-01-05 | 2021-04-05 | 4 | 0
2A | EIR-025 | Prepare Cumulative and Climate Change Sections | 20 | 2021-02-10 | 2021-03-09 | 23 | 0
2A | EIR-030 | Authority/Reclamation/Integration Review of Admin Draft EIR | 10 | 2021-04-06 | 2021-04-19 | 4 | 0
2A | EIR-040 | Revise Draft EIR | 20 | 2021-04-20 | 2021-05-17 | 4 | 0
2A | EIR-050 | Work Group & Legal Review of Revised Draft EIR | 30 | 2021-05-18 | 2021-06-16 | 4 | 0
2A | EIR-060 | Resolve Work Group Comments | 15 | 2021-06-16 | 2021-07-08 | 2 | 0
2A | EIR-070 | Authority Approval of Revised Draft EIR | 1 | 2021-07-08 | 2021-07-09 | 2 | 0
2A | EIR-080 | Submit Revised Draft EIR | 0 |  | 2021-07-12 | 2 | 0
Public Review |  |  | 90 | 2021-07-13 | 2021-10-10 | 15 | 0
2A | EIR-090 | Public Review Period | 90 | 2021-07-13 | 2021-10-10 | 15 | 0
Summary Report |  |  | 33 | 2021-10-11 | 2021-11-24 | 11 | 150000
2A | EIR-100 | Approach to Response to Comments | 10 | 2021-10-11 | 2021-10-22 | 11 | 0
2A | EIR-110 | Prepare Summary Report | 22 | 2021-10-25 | 2021-11-23 | 11 | 0
2A | EIR-120 | Draft EIR Summary Report Submittal to CWC | 0 |  | 2021-11-24 | 11 | 0
Response to Comments |  |  | 90 | 2021-10-25 | 2022-03-03 | 185 | 500000 | budget is thru 12/31/21
2A | EIR-130 | Response to Comments | 90 | 2021-10-25 | 2022-03-03 | 185 | 0
Permitting |  |  | 852 | 2020-01-02 | 2023-05-08 | 0 | 6320000
Value Planning Analysis |  |  | 37 | 2020-01-02 | 2020-02-21 | 15 | 0
1B | VP-006 | Qualitative Permit Screening | 37 | 2020-01-02 | 2020-02-21 | 15 | 0
Determine Needs |  |  | 56 | 2020-02-11 | 2020-04-28 | 9 | 0
1B | PDE-20 | Permitting Needs | 56 | 2020-02-11 | 2020-04-28 | 9 | 0
1B | PDE-35 | Water Rights Needs (Reg Items/Study) | 46 | 2020-02-11 | 2020-04-14 | 19 | 0
Components |  |  | 47 | 2020-04-14 | 2020-06-18 | 60 | 0
1B | PDE-47 | Identify Project-Level vs Program Components (Permitting) | 47 | 2020-04-14 | 2020-06-18 | 60 | 0
Biological Assessment |  |  | 369 | 2020-01-02 | 2021-06-14 | 34 | 2300000
2A | BA-001 | Initial Desktop Analysis | 60 | 2020-09-29 | 2020-12-23 | 22 | 0
2A | BA-003 | Strategize with USFWS and Reclamation on Surveys, Impacts & Mitigation | 171 | 2020-01-02 | 2020-08-31 | 121 | 0
1B | BA-010 | Mitigation Planning | 202 | 2020-04-14 | 2021-01-29 | 14 | 800000 | work starts in 2A; 1B is <40 hrs
1B | BA-015 | Adaptive Management Plan | 202 | 2020-04-14 | 2021-01-29 | 17 | 400000 | work starts in 2A; 1B is <40 hrs
1B | BA-019 | Confirm Federal Scope of Action (ESA) | 38 | 2020-04-14 | 2020-06-05 | 68 | 0
1B | BA-020 | Permitting Construction Project Description | 16 | 2020-06-08 | 2020-06-29 | 68 | 0
2A | BA-022 | Permitting Operations Project Description | 20 | 2020-10-13 | 2020-11-09 | 9 | 0
2A | BA-024 | Prepare Construction Analysis | 97 | 2020-09-11 | 2021-01-29 | 17 | 0
2A | BA-025 | Prepare Operations Analysis | 60 | 2020-11-10 | 2021-02-05 | 9 | 0
2A | BA-030 | Finalize Admin Draft BA | 20 | 2021-02-08 | 2021-03-05 | 12 | 0
2A | BA-032 | Submit Final Admin Draft BA | 0 |  | 2021-03-05 | 12 | 0
2A | BA-035 | Independent Review Draft BA (Cal Days) | 30 | 2021-03-06 | 2021-04-04 | 18 | 0
2A | BA-055 | Reclamation, Legal, and Work Group Review | 30 | 2021-03-06 | 2021-04-04 | 18 | 0
2A | BA-057 | Revise Admin Draft BA | 30 | 2021-04-05 | 2021-05-14 | 14 | 0
2A | BA-060 | Submit Revised Admin Draft BA to Reclamation | 0 |  | 2021-05-14 | 32 | 0
2A | BA-075 | Final Reclamation and Solicitor Office Review | 30 | 2021-05-15 | 2021-06-13 | 47 | 0
2A | BA-100 | Reclamation Submit BA to USFWS & NMFS | 0 |  | 2021-06-14 | 34 | 0
BO Incidental Take Authorization |  |  | 135 | 2021-06-14 | 2021-10-26 | 48 | 0
2A | BA-1110 | BO Incidental Take Authorization | 135 | 2021-06-14 | 2021-10-26 | 48 | 0
ITP- CESA (Sec 2081) Operations |  |  | 292 | 2020-09-29 | 2021-11-19 | 14 | 400000
2A | CES-180 | Operations Project Description | 30 | 2020-09-29 | 2020-11-09 | 45 | 0
2A | CES-190 | Prepare Operations Analysis | 30 | 2021-01-05 | 2021-02-15 | 9 | 0
2A | CES-200 | Mitigation Planning | 30 | 2021-02-16 | 2021-03-29 | 9 | 0
2A | CES-210 | Prepare Draft ITP Application | 60 | 2021-05-17 | 2021-08-10 | 14 | 0
2A | CES-220 | Legal Review of Draft ITP App | 30 | 2021-08-11 | 2021-09-09 | 20 | 0
2A | CES-230 | Work Group Review of Draft ITP App | 30 | 2021-08-11 | 2021-09-09 | 20 | 0
2A | CES-240 | Revise Draft ITP Application | 20 | 2021-09-09 | 2021-10-07 | 14 | 0
2A | CES-250 | Authority Board Approval of ITP App | 30 | 2021-10-07 | 2021-11-18 | 14 | 0
2A | CES-260 | Submit ITP Application to CDFW | 0 |  | 2021-11-19 | 14 | 0
ITP- CESA (Sec 2081) Construction |  |  | 292 | 2020-09-29 | 2021-11-19 | 370 | 250000
2A | CES-015 | Initial Desktop Analysis | 30 | 2020-09-29 | 2020-11-09 | 572 | 0
2A | CES-020 | Prepare Terrestrial Analysis | 30 | 2020-11-10 | 2020-12-23 | 572 | 0
2A | CES-025 | Mitigation Planning | 30 | 2020-12-24 | 2021-02-05 | 572 | 0
2A | CES-030 | Prepare Draft ITP Application | 60 | 2021-05-17 | 2021-08-10 | 14 | 0
2A | CES-040 | Legal Review of Draft ITP App | 30 | 2021-08-11 | 2021-09-09 | 20 | 0
2A | CES-060 | Work Group Review of Draft ITP App | 30 | 2021-08-11 | 2021-09-09 | 20 | 0
2A | CES-070 | Revise Draft ITP Application | 20 | 2021-09-09 | 2021-10-07 | 14 | 0
2A | CES-080 | Authority Board Approval of ITP App | 30 | 2021-10-07 | 2021-11-18 | 14 | 0
2A | CES-090 | Submit ITP Application to CDFW | 0 |  | 2021-11-19 | 14 | 0
Section 106 |  |  | 318 | 2020-08-28 | 2021-11-30 | 365 | 1020000
2A | 106-000 | Confirmation of Section 106 Federal Lead Agency | 0 |  | 2020-09-08 | 676 | 0
2A | 106-001 | Prepare SHPO Initiation Package | 20 | 2020-08-28 | 2020-09-25 | 9 | 0
2A | 106-002 | Authority/Reclamation/Integration Reviews | 10 | 2020-09-28 | 2020-10-09 | 9 | 0
2A | 106-003 | Management/Work Group Reviews | 10 | 2020-10-12 | 2020-10-23 | 9 | 0
2A | 106-004 | Revisions | 10 | 2020-10-26 | 2020-11-06 | 9 | 0
2A | 106-005 | Reclamation Submits to SHPO | 0 |  | 2020-11-13 | 9 | 0
2A | 106-006 | SHPO Review and comments | 30 | 2020-11-14 | 2020-12-13 | 17 | 0
2A | 106-021 | Prepare Consultation Information Package | 15 | 2020-12-14 | 2021-01-05 | 12 | 0
2A | 106-022 | Authority/Reclamation/Integration Reviews | 10 | 2021-01-06 | 2021-01-19 | 12 | 0
2A | 106-023 | Management/Work Group Reviews | 10 | 2021-01-20 | 2021-02-02 | 12 | 0
2A | 106-024 | Revisions | 10 | 2021-02-03 | 2021-02-16 | 12 | 0
2A | 106-025 | Reclamation Distributes to SHPO and Invited Consulting Parties | 5 | 2021-02-17 | 2021-02-23 | 23 | 0
2A | 106-026 | Parties Accept Invitation for Consulting Party Status | 30 | 2021-02-24 | 2021-03-25 | 45 | 0
2A | 106-032 | Arrange Meeting Logistics and Prepare Materials | 20 | 2021-02-17 | 2021-03-16 | 12 | 0
2A | 106-033 | Conduct Meetings | 10 | 2021-02-24 | 2021-03-09 | 23 | 0
2A | 106-042 | Authority/Reclamation/Integration Reviews | 10 | 2021-03-25 | 2021-04-07 | 12 | 0
2A | 106-043 | Management/Work Group Reviews | 10 | 2021-04-08 | 2021-04-21 | 12 | 0
2A | 106-044 | Revisions | 10 | 2021-04-22 | 2021-05-05 | 26 | 0
2A | 106-052 | Circulate Draft PA to SHPO and Consulting Parties | 5 | 2021-04-22 | 2021-04-28 | 12 | 0
2A | 106-053 | Deadline for Comments on Draft PA | 30 | 2021-04-29 | 2021-05-28 | 16 | 0
2A | 106-061 | Prepare Draft Final PA | 20 | 2021-05-28 | 2021-06-28 | 9 | 0
2A | 106-062 | Authority/Reclamation/Integration Reviews | 10 | 2021-06-28 | 2021-07-13 | 9 | 0
2A | 106-063 | Management/Work Group Reviews | 10 | 2021-07-13 | 2021-07-27 | 9 | 0
2A | 106-064 | Revisions | 10 | 2021-07-27 | 2021-08-10 | 9 | 0
2A | 106-072 | Circulate Draft Final PA to SHPO and Consulting Parties | 5 | 2021-08-10 | 2021-08-17 | 9 | 0
2A | 106-073 | Deadline for Comments on Draft Final PA | 30 | 2021-08-18 | 2021-09-16 | 13 | 0
2A | 106-081 | Prepare Final PA | 15 | 2021-09-16 | 2021-10-07 | 9 | 0
2A | 106-082 | Authority/Reclamation/Integration Reviews | 10 | 2021-10-07 | 2021-10-21 | 9 | 0
2A | 106-083 | Management/Work Group Reviews | 10 | 2021-10-21 | 2021-11-04 | 9 | 0
2A | 106-084 | Revisions | 10 | 2021-11-04 | 2021-11-18 | 9 | 0
2A | 106-091 | Consult with SHPO and Consulting Parties on Final PA | 5 | 2021-11-18 | 2021-11-29 | 10 | 0
2A | 106-092 | Circulate Final PA to SHPO and Consulting Parties for Signatures | 5 | 2021-11-18 | 2021-11-29 | 9 | 0
2A | 106-093 | Deadline for Signatures on Final PA | 0 |  | 2021-11-30 | 13 | 0
Water Rights |  |  | 684 | 2020-08-27 | 2023-05-08 | 0 | 0
2A | WR-005 | Water Availability Analysis & Planning/Coordination with State/Local | 210 | 2020-08-27 | 2021-06-24 | 12 | 0
2A | WR-025 | Prepare Water Right Application | 121 | 2021-07-09 | 2021-12-31 | 2 | 0
2A | WR-035 | QA/QC and Legal Review of Draft Water Right Application | 15 | 2021-12-31 | 2022-01-24 | 2 | 0
2A | WR-045 | Revise Draft Water Rights Application | 25 | 2022-01-24 | 2022-02-28 | 2 | 0
2A | WR-055 | Work Group Review of Draft Water Right | 10 | 2022-02-28 | 2022-03-14 | 2 | 0
2A | WR-065 | Resolve Work Group Comments | 10 | 2022-03-14 | 2022-03-28 | 2 | 0
2A | WR-075 | Authority Approval of Water Right Appl, Submittal to SWRCB | 1 | 2022-03-28 | 2022-03-29 | 2 | 0
2A | WR-085 | Submit Water Right Application | 0 |  | 2022-03-29 | 2 | 0
2A | WR-095 | SWRCB Review of Water Right Application | 60 | 2022-03-30 | 2022-05-28 | 2 | 0
2A | WR-105 | Receive Protests to Application | 44 | 2022-05-31 | 2022-08-01 | 0 | 0
2A | WR-115 | Resolve Protests and Schedule Protest Hearing | 80 | 2022-08-02 | 2022-11-22 | 0 | 0
2A | WR-125 | Notice Water Rights Hearing | 22 | 2022-11-23 | 2022-12-27 | 0 | 0
2A | WR-135 | Conduct In-House Mock Water Right Hearing | 15 | 2022-12-28 | 2023-01-18 | 7 | 0
2A | WR-145 | Conduct Water Right Hearing | 1 | 2023-01-30 | 2023-01-30 | 0 | 0
2A | WR-155 | Negotiate Permit Terms | 44 | 2023-01-31 | 2023-03-31 | 0 | 0
2A | WR-165 | SWRCB Prepare Draft Permit and CEQA Findings | 21 | 2023-04-03 | 2023-05-01 | 0 | 0
2A | WR-175 | SWRCB Issue Water Right Permit | 5 | 2023-05-02 | 2023-05-08 | 0 | 0
2A | WR-185 | Water Right Permit | 0 |  | 2023-05-08 | 0 | 0
Section 404 |  |  | 414 | 2020-04-14 | 2021-11-30 | 9 | 500000
1B | 404-001 | Agreement with Reclamation for LEDPA Analysis | 15 | 2020-04-14 | 2020-05-04 | 25 | 0
1B | 404-003 | USACE LEDPA & NEPA , 404/408 and WD Approach | 88 | 2020-05-05 | 2020-09-08 | 25 | 0
2A | 404-010 | Desktop Wetland Delineation Analysis (includes Waters of the State) | 150 | 2020-09-29 | 2021-04-30 | 11 | 0
2A | 404-020 | Submit Delineation to USACE | 0 |  | 2021-05-03 | 11 | 0
2A | 404-025 | Pre-Application Meeting | 1 | 2021-06-01 | 2021-06-01 | 53 | 0
2A | 404-030 | Preliminary Wetland Delineation Acceptance | 90 | 2021-05-04 | 2021-08-01 | 15 | 0
2A | 404-035 | Compensatory Mitigation Plan | 161 | 2021-02-16 | 2021-10-01 | 9 | 0
2A | 404-050 | Prepare Draft 404 Application | 42 | 2021-08-02 | 2021-09-29 | 11 | 0
2A | 404-060 | Authority/Integration/Work Group Review of Draft 404 | 20 | 2021-10-04 | 2021-10-29 | 9 | 0
2A | 404-070 | Prepare Final 404 Application | 20 | 2021-11-01 | 2021-11-30 | 9 | 0
2A | 404-120 | Submit 404 Application | 0 |  | 2021-11-30 | 9 | 0
Section 408 |  |  | 600 | 2020-04-14 | 2022-08-23 | 179 | 400000
2A | 408-005 | Coordinate with CVFPB and USACE | 20 | 2020-04-14 | 2020-05-11 | 466 | 0
2A | 408-010 | Assume Start of 50% Design of 408 Jurisdictional Features | 0 |  | 2021-06-28 | 179 | 0
2A | 408-130 | Prepare Draft Encroachment Permit/408 Request w/Engineering Team | 129 | 2021-06-29 | 2021-12-31 | 179 | 0
2A | 408-135 | Continue Draft Encroachment Permit/408 Request w/Engineering Team | 124 | 2022-01-04 | 2022-06-27 | 179 | 0
2A | 408-140 | Authority/Integration/Work Group Review of Draft | 20 | 2022-06-28 | 2022-07-26 | 179 | 0
2A | 408-150 | Prepare Encroachment Permit/408 Request | 20 | 2022-07-27 | 2022-08-23 | 179 | 0
2A | 408-160 | Submit Encroachment Permit/408 Request | 0 |  | 2022-08-23 | 179 | 0
Section 401 Water Quality |  |  | 309 | 2020-09-09 | 2021-11-24 | 11 | 250000
2A | 401-120 | Coordinate with RWQCB and SWRCB | 84 | 2020-09-09 | 2021-01-08 | 154 | 0
2A | 401-130 | Prepare Draft 401 Application | 42 | 2021-08-02 | 2021-09-29 | 11 | 0
2A | 401-140 | Authority/Integration/Work Group Review of Draft 401 | 20 | 2021-09-30 | 2021-10-27 | 11 | 0
2A | 401-150 | Prepare Final 401 Application | 20 | 2021-10-28 | 2021-11-24 | 11 | 0
2A | 401-160 | Submit 401 Application | 0 |  | 2021-11-24 | 11 | 0
Operations |  |  | 486 | 2020-01-02 | 2021-11-29 | 10 | 0
Value Planning Analysis |  |  | 37 | 2020-01-02 | 2020-02-21 | 15 | 0
1B | VP-008 | Qualitative Ops Screening | 37 | 2020-01-02 | 2020-02-21 | 15 | 0
Determine Needs |  |  | 10 | 2020-02-11 | 2020-02-24 | 55 | 0
1B | PDE-30 | Operations Needs | 10 | 2020-02-11 | 2020-02-24 | 55 | 0
Develop Project Description |  |  | 0 | 2020-06-12 | 2020-06-12 | 62 | 0
1B | PDE-55 | Project Description Operations Criteria | 0 |  | 2020-06-12 | 62 | 0
Value Planning Operations |  |  | 71 | 2020-01-02 | 2020-04-10 | 0 | 0
1B | OP-005 | Value Planning Model | 37 | 2020-01-02 | 2020-02-21 | 0 | 0
1B | OP-007 | Stony Creek Evaluation | 37 | 2020-01-02 | 2020-02-21 | 0 | 0
1B | OP-010 | Shasta Exchanges Post-Processing and Draft TM | 37 | 2020-01-02 | 2020-02-21 | 0 | 0
1B | OP-015 | Value Planning TM/Document | 20 | 2020-02-03 | 2020-02-28 | 6 | 0
1B | OP-020 | Storage to Release Ratios Table | 15 | 2020-02-10 | 2020-02-28 | 6 | 0
1B | OP-070 | Reclamation Feasibility Complete (Milestone) | 0 |  | 10-Apr-20* | 0 | 0
Refine Operational Parameters |  |  | 89 | 2020-02-10 | 2020-06-12 | 6 | 0
1B | OP-110 | Notched Fremont Weir | 44 | 2020-02-10 | 2020-04-09 | 6 | 0
1B | OP-120 | Model Reclamation with No-Storage | 44 | 2020-04-10 | 2020-06-11 | 6 | 0
1B | OP-130 | Confirm Shasta Exchange | 44 | 2020-02-10 | 2020-04-09 | 6 | 0
1B | OP-140 | Confirm Sutter Bypass | 44 | 2020-02-10 | 2020-04-09 | 6 | 0
1B | OP-150 | Confirm Voluntary Agreement Weir Notching | 44 | 2020-02-10 | 2020-04-09 | 6 | 0
1B | OP-160 | Confirm Delta Water Quality | 44 | 2020-02-10 | 2020-04-09 | 6 | 0
1B | OP-170 | Confirm Sacramento River Mortality | 44 | 2020-02-10 | 2020-04-09 | 6 | 0
1B | OP-180 | Determine Baseline | 44 | 2020-02-10 | 2020-04-09 | 6 | 0
1B | OP-190 | Confirm CVP/SWP Integration | 44 | 2020-02-10 | 2020-04-09 | 6 | 0
1B | OP-200 | Confirm Participation Demands Updated | 44 | 2020-02-10 | 2020-04-09 | 6 | 0
1B | OP-210 | Confirm Refinements | 44 | 2020-04-10 | 2020-06-11 | 6 | 0
1B | OP-220 | Finalize Operational Criteria | 0 |  | 2020-06-12 | 6 | 0
Full Operations Analysis |  |  | 104 | 2020-06-15 | 2020-11-09 | 40 | 0
2A | OP-230 | CalSim | 104 | 2020-06-15 | 2020-11-09 | 6 | 0
2A | OP-240 | DSM2-Hydro | 104 | 2020-06-15 | 2020-11-09 | 40 | 0
2A | OP-250 | USRWQM | 104 | 2020-06-15 | 2020-11-09 | 40 | 0
2A | OP-260 | SALMOD | 104 | 2020-06-15 | 2020-11-09 | 40 | 0
2A | OP-270 | IOS | 104 | 2020-06-15 | 2020-11-09 | 40 | 0
2A | OP-280 | DSM2-Qual | 104 | 2020-06-15 | 2020-11-09 | 40 | 0
2A | OP-290 | OBAN | 104 | 2020-06-15 | 2020-11-09 | 9 | 0
2A | OP-300 | Fish Mortality Models | 104 | 2020-06-15 | 2020-11-09 | 9 | 0
2A | OP-310 | Power | 104 | 2020-06-15 | 2020-11-09 | 40 | 0
2A | OP-315 | Economics | 104 | 2020-06-15 | 2020-11-09 | 13 | 0
Coordination |  |  | 350 | 2020-07-14 | 2021-11-29 | 10 | 0
2A | OP-320 | Documentation for EIR/EIS and BA/ITP | 40 | 2020-11-10 | 2021-01-08 | 65 | 0
2A | OP-330 | Ongoing Support to EPP, Engineering, & Financial | 350 | 2020-07-14 | 2021-11-29 | 10 | 0
2A | OP-340 | Cumulative and Climate Change | 62 | 2020-11-10 | 2021-02-09 | 23 | 0
2A | OP-350 | Bridging Simulation | 126 | 2020-11-10 | 2021-05-10 | 40 | 0
2A | OP-360 | Ops Support for Local Feasibility - Water Commission | 160 | 2020-11-10 | 2021-06-28 | 6 | 0
Cost of Year Deliveries |  |  | 51 | 2020-01-02 | 2020-03-12 | 2 | 0
1B | CYD-005 | Prepare Progress Report | 30 | 2020-01-02 | 2020-02-12 | 2 | 0
1B | CYD-010 | In-progress Briefing | 1 | 2020-02-13 | 2020-02-13 | 3 | 0
1B | CYD-015 | Prepare Final Report | 20 | 2020-02-13 | 2020-03-11 | 2 | 0
1B | CYD-020 | In-progress Briefing | 1 | 2020-03-12 | 2020-03-12 | 2 | 0
Engineering |  |  | 508 | 2020-01-02 | 2021-12-30 | 344 | 0
Value Planning Analysis |  |  | 44 | 2020-01-02 | 2020-03-03 | 4 | 0
1B | VP-001 | Refine Value Planning Options | 3 | 2020-01-02 | 2020-01-06 | 4 | 0
1B | VP-002 | Screen Value Planning Options | 20 | 2020-01-07 | 2020-02-03 | 4 | 0
1B | VP-013 | Prepare Costs For Value Planning Alternatives | 15 | 2020-02-04 | 2020-02-24 | 4 | 0
1B | VP-015 | Screen Alternatives | 2 | 2020-03-02 | 2020-03-03 | 4 | 0
1B | VP-020 | Recommend Preferred Option | 0 |  | 2020-03-03 | 4 | 0
Value Planning Report |  |  | 42 | 2020-02-14 | 2020-04-13 | 0 | 0
1B | VP-025 | Value Planning Draft Report | 21 | 2020-02-14 | 2020-03-13 | 0 | 0
1B | VP-070 | Preferred Project | 21 | 2020-03-16 | 2020-04-13 | 0 | 0
1B | VP-090 | Value Planning Final Report | 17 | 2020-03-20 | 2020-04-13 | 0 | 0
Preferred Project |  |  | 0 | 2020-04-13 | 2020-04-13 | 0 | 0
1B | VP-095 | Approve Preferred Project | 0 |  | 2020-04-13 | 0 | 0
Determine Needs |  |  | 46 | 2020-02-11 | 2020-04-14 | 19 | 0
1B | PDE-25 | Engineering Needs | 46 | 2020-02-11 | 2020-04-14 | 19 | 0
Components |  |  | 65 | 2020-04-14 | 2020-07-15 | 714 | 0
1B | PDE-42 | Determine Preliminary Project Construction Sequencing | 30 | 2020-06-03 | 2020-07-15 | 42 | 0
| PDE-46 | Identify Program-Level vs Program Components (Planning) | 47 | 2020-04-14 | 2020-06-18 | 732 | 0
Support of Project Description |  |  | 449 | 2020-03-24 | 2021-12-30 | 344 | 0
1B | ENG-110 | Engineering Consultants Brought On Board (complete prior to Sept 1) | 0 |  | 2020-03-24 | 14 | 0
1B | ENG-120 | Coordination of CADD and GIS Standards | 20 | 2020-03-25 | 2020-04-21 | 14 | 0
1B | ENG-130 | Coordination to Identify Alternatives for EIR/EIS & Related Studies | 5 | 2020-04-14 | 2020-04-20 | 4 | 0
1B | ENG-140 | Coordination to Finalize Storage & Conveyance Capacities | 5 | 2020-03-25 | 2020-03-31 | 29 | 0
1B | ENG-150 | Gather Data from Prior Draft EIR/EIS | 10 | 2020-03-25 | 2020-04-07 | 19 | 0
1B | ENG-160 | Prepare Project Base Map | 20 | 2020-03-25 | 2020-04-21 | 9 | 0
1B | ENG-170 | Prepare Basis of Feasibility Design | 10 | 2020-03-25 | 2020-04-07 | 24 | 0
1B | ENG-180 | Conduct Field Reviews (as needed) | 5 | 2020-04-22 | 2020-04-28 | 9 | 0
1B | ENG-190 | Complete Feasibility Level Design | 85 | 2020-04-29 | 2020-08-27 | 9 | 0
1B | ENG-200 | Develop CADD Drawings of Key Features | 85 | 2020-04-29 | 2020-08-27 | 9 | 0
1B | ENG-210 | Provide Information on Key Project Features & Facilities | 21 | 2020-08-28 | 2020-09-28 | 128 | 0
1B | ENG-220 | Convert Drawings to GIS Geodatabase File Format to Support Environmental & Permitting | 21 | 2020-08-28 | 2020-09-28 | 11 | 0
2A | ENG-230 | Support to Environmental and Permitting Team | 318 | 2020-09-29 | 2021-12-30 | 344 | 0
1B | ENG-233 | Engineering Support for Alternative A | 131 | 2020-06-03 | 2020-12-08 | 613 | 0
1B | ENG-236 | Engineering Support for Modified Alternative A | 131 | 2020-06-03 | 2020-12-08 | 613 | 0
Cost Estimate, Feasibility, Constructability |  |  | 246 | 2020-03-25 | 2021-03-12 | 191 | 0
1B | ENG-240 | Identify Project Objectives | 11 | 2020-03-25 | 2020-04-08 | 126 | 0
1B | ENG-250 | Feasibility Project Description | 0 |  | 2020-08-27 | 27 | 0
2A | ENG-260 | Obtain Operations Simulation Results of Preferred Option | 0 |  | 2020-11-09 | 13 | 0
2A | ENG-270 | Develop Costs Associated with Mitigation Measures | 15 | 2020-10-05 | 2020-10-23 | 27 | 0
2A | ENG-280 | Develop Class 4 Cost Estimate (State Feasibility) | 42 | 2020-10-26 | 2020-12-24 | 27 | 0
2A | ENG-290 | Risk and Uncertainty Assessment | 20 | 2020-10-26 | 2020-11-20 | 49 | 0
2A | ENG-300 | Confirm Project Benefits | 45 | 2020-11-10 | 2021-01-15 | 13 | 0
2A | ENG-310 | Project Benefits Consist with the Ops Plan | 41 | 2020-11-10 | 2021-01-11 | 17 | 0
2A | ENG-320 | Cost Allocation | 20 | 2021-01-18 | 2021-02-12 | 13 | 0
2A | ENG-330 | Technical Feasibility | 20 | 2020-08-28 | 2020-09-25 | 93 | 0
2A | ENG-340 | Obtain the Finding of Env Feasibility with Mitigation | 21 | 2020-10-19 | 2020-11-16 | 93 | 0
2A | ENG-350 | Economic Feasibility | 5 | 2021-02-15 | 2021-02-19 | 28 | 0
2A | ENG-360 | Financial Feasibility | 20 | 2021-02-15 | 2021-03-12 | 13 | 0
2A | ENG-370 | Constructability | 20 | 2021-02-15 | 2021-03-12 | 13 | 0
2A | ENG-400 | Develop DSOD Engagement Plan | 20 | 2020-08-27 | 2020-09-24 | 308 | 0
2A | ENG-404 | Coordinate on a Geotechnical Investigation Plan | 20 | 2020-08-27 | 2020-09-24 | 308 | 0
2A | ENG-406 | Coordinate to Develop Geotechnical Permitting Plan | 20 | 2020-08-27 | 2020-09-24 | 308 | 0
2A | ENG-410 | Develop Program Design/Construction/Permit Implementation Plan | 20 | 2020-08-27 | 2020-09-24 | 308 | 0
2A | ENG-420 | Develop Sites Local Operations Model (LOM) | 63 | 2020-08-27 | 2020-11-24 | 265 | 0
Feasibility Report |  |  | 80 | 2021-03-15 | 2021-07-06 | 6 | 0
2A | ENG-380 | Prepare Draft Feasibility Report | 30 | 2021-03-15 | 2021-04-23 | 13 | 0
2A | ENG-385 | Work Group Review | 5 | 2021-04-26 | 2021-04-30 | 13 | 0
2A | ENG-390 | Prepare Final Feasibility Report | 33 | 2021-05-12 | 2021-06-28 | 6 | 0
2A | ENG-392 | Reservoir Committee and Board Approval | 5 | 2021-06-29 | 2021-07-06 | 6 | 0
CWC Feasibility Review |  |  | 152 | 2021-07-13 | 2021-12-11 | 2 | 0
2A | ENG-395 | CWC Review | 152 | 2021-07-13 | 2021-12-11 | 2 | 0
CWC Determination |  |  | 0 | 2021-12-13 | 2021-12-13 | 1 | 0
2A | ENG-399 | State Determination of Feasibility | 0 |  | 13-Dec-21* | 1 | 0
Geotech |  |  | 508 | 2020-01-02 | 2021-12-30 | 344 | 0
Feasibility-Level Geotech |  |  | 508 | 2020-01-02 | 2021-12-30 | 344 | 0
1B | GSR-000 | Continuted Geotechnical Support for Reclamation | 171 | 2020-01-02 | 2020-08-31 | 344 | 0
2A | GSR-010 | Geotechnical Permitting & Planning, Right of Access | 61 | 2020-09-01 | 2020-11-25 | 344 | 0
2A | GSR-020 | Conduct Geotechnical Field Investigation | 85 | 2020-11-30 | 2021-03-30 | 344 | 0
2A | GSR-030 | Data Evaluation and Prepare Geotechnical Data Reports | 107 | 2021-01-29 | 2021-06-29 | 344 | 0
2A | GSR-040 | Data Gap Assessment and Preliminary Planning for Design Level Inv for Preferred Alt | 149 | 2021-05-28 | 2021-12-30 | 344 | 0
Communications & Gov't Affairs |  |  | 509 | 2020-01-02 | 2021-12-31 | 343 | 0
Communications & Gov't Affairs |  |  | 509 | 2020-01-02 | 2021-12-31 | 343 | 0
1B | CG-000 | Communication & Government Affairs | 171 | 2020-01-02 | 2020-08-31 | 343 | 0
2A | CG-10 | Communication & Government Affairs | 338 | 2020-09-01 | 2021-12-31 | 343 | 0
Work Plan |  |  | 168 | 2020-01-02 | 2020-08-26 | 12 | 0
Work Plan Amend 1B (complete prior to Sept 1) |  |  | 40 | 2020-01-02 | 2020-02-26 | 89 | 0
1B | WP-005 | Incorporate Comments from Dec Res Comm Mtg | 9 | 02-Jan-20* | 2020-01-14 | 0 | 0
1B | WP-015 | Prepare Final Work Plan | 14 | 2020-01-15 | 2020-02-03 | 6 | 0
1B | WP-020 | Budget & Finance Work Group Review | 5 | 2020-02-04 | 2020-02-10 | 6 | 0
1B | WP-025 | Work Plan 1B Approved | 0 |  | 2020-02-26 | 89 | 0
Develop Schedule |  |  | 29 | 2020-01-28 | 2020-03-06 | 1 | 0
1B | WP-040 | Develop Draft Schedule thru Dec 31, 2021 | 13 | 2020-01-28 | 2020-02-13 | 3 | 0
1B | WP-060 | Develop Final Schedule through Dec 2021 | 10 | 2020-02-24 | 2020-03-06 | 1 | 0
Work Plan Scope Document |  |  | 29 | 2020-01-28 | 2020-03-06 | 1 | 0
1B | WP-050 | Draft Work Plan Task List | 13 | 2020-01-28 | 2020-02-13 | 7 | 0
1B | WP-070 | Final Work Plan Scope Document | 10 | 2020-02-24 | 2020-03-06 | 1 | 0
Work Plan Budget |  |  | 29 | 2020-01-28 | 2020-03-06 | 1 | 0
1B | WP-035 | Budget Scenarios and Assumptions | 2 | 2020-02-11 | 2020-02-12 | 8 | 0
1B | WP-055 | Draft Work Plan Budget | 13 | 2020-01-28 | 2020-02-13 | 7 | 0
1B | WP-090 | Final Work Plan Budget | 10 | 2020-02-24 | 2020-03-06 | 1 | 0
Amendment 2 |  |  | 121 | 2020-03-09 | 2020-08-26 | 12 | 0
1B | WP-095 | Final Amendment 2 Work Plan | 5 | 2020-03-09 | 2020-03-13 | 1 | 0
1B | WP-110 | Develop Task Orders (Sep 2020 to Dec 2021) | 51 | 2020-03-16 | 2020-05-26 | 77 | 0
1B | WP-120 | Work Plan 2 Approved | 0 |  | 2020-06-18 | 60 | 0
1B | WP-130 | Start of Amend 2 | 0 |  | 2020-08-26 | 12 | 0
Financial |  |  | 501 | 2020-01-14 | 2021-12-31 | 343 | 0
Execute Participation Agreement 1B (complete prior to Sept 1) |  |  | 95 | 2020-01-23 | 2020-06-04 | 70 | 0
1B | PA-010 | Amend Task Orders | 26 | 2020-01-23 | 2020-02-27 | 28 | 0
1B | PA-020 | Final Participation Agreement Amendment 1B | 15 | 2020-03-18 | 2020-04-08 | 70 | 0
1B | PA-030 | Engineering Task Orders (HC, HR) | 30 | 2020-01-23 | 2020-03-04 | 28 | 0
1B | PA-040 | Amendment 1B Exhibit B | 5 | 2020-04-01 | 2020-04-08 | 70 | 0
1B | PA-050 | Executed 1B | 0 |  | 2020-06-04 | 70 | 0
Execute Participation Agreement 2 |  |  | 114 | 2020-03-18 | 2020-08-26 | 12 | 0
1B | PA-120 | Draft Participation Agreement Amend 2 for Home Board Review | 15 | 2020-03-18 | 2020-04-08 | 15 | 0
1B | PA-130 | Home Board Review - Determine Participation Level | 44 | 2020-04-17 | 2020-06-18 | 8 | 0
1B | PA-140 | Rebalance Participation | 8 | 2020-06-19 | 2020-06-30 | 8 | 0
1B | PA-150 | Final Participation Agreement Amend 2 with Exhibits | 0 |  | 2020-06-30 | 8 | 0
1B | PA-160 | Execute Amendment 2 | 0 |  | 2020-08-26 | 12 | 0
Execute Successor Participation Agreement 2 |  |  | 106 | 2021-08-02 | 2021-12-31 | 343 | 0
2A | A1000 | Execute Successor Agreement | 106 | 02-Aug-21* | 2021-12-31 | 343 | 0
Value Planning Analysis |  |  | 4 | 2020-02-25 | 2020-02-28 | 4 | 0
1B | VP-014 | Affordability Analysis | 4 | 2020-02-25 | 2020-02-28 | 4 | 0
Financial Assistance Agreement |  |  | 55 | 2020-01-14 | 2020-03-30 | 35 | 0
1B | FAA-005 | Prepare Draft FA Scope and Form 424 | 15 | 2020-01-14 | 2020-02-03 | 35 | 0
1B | FAA-010 | Review Scope with USBR | 5 | 2020-02-04 | 2020-02-10 | 35 | 0
1B | FAA-015 | Prepare Budget Estimates, Narrative and Form 424A/B, SFLLL | 15 | 2020-02-11 | 2020-03-02 | 35 | 0
1B | FAA-020 | Review with USBR | 10 | 2020-03-03 | 2020-03-16 | 35 | 0
1B | FAA-025 | Finalize Draft FA | 10 | 2020-03-17 | 2020-03-30 | 35 | 0
Plan of Finance |  |  | 319 | 2020-04-30 | 2021-08-02 | 448 | 0
1B | POF-005 | Plan of Finance Update 1 (Update Affordability) | 0 | 30-Apr-20* |  | 767 | 0
2A | POF-010 | Plan of Finance (Fin Feas) | 0 | 01-Mar-21* |  | 557 | 0
2A | POF-015 | Plan of Finance (WIFIA Loan) | 0 | 01-Apr-21* |  | 534 | 0
2A | POF-020 | WIFIA/LOI | 0 | 30-Jun-21* |  | 471 | 0
2A | POF-025 | Plan of Finance (Home Board Pkg) | 0 |  | 02-Aug-21* | 448 | 0
WIFIA Loan Application |  |  | 75 | 2020-01-20 | 2020-05-01 | 11 | 0
1B | WL-005 | Prepare Initial Loan Application | 20 | 20-Jan-20* | 2020-02-14 | 11 | 0
1B | WL-010 | Review Loan Application | 35 | 2020-02-17 | 2020-04-03 | 11 | 0
1B | WL-015 | Prepare Loan Application for Facilities | 20 | 2020-04-06 | 2020-05-01 | 11 | 0
Business Management |  |  | 509 | 2020-01-02 | 2021-12-31 | 343 | 0
Organizational Assessment |  |  | 171 | 2020-01-02 | 2020-08-31 | 681 | 0
1B | OA-000 | Organizational Assessment Direction | 171 | 2020-01-02 | 2020-08-31 | 681 | 0
Ongoing Business |  |  | 509 | 2020-01-02 | 2021-12-31 | 343 | 0
1B | OB-00-20 | Contract Amendments | 20 | 2020-01-02 | 2020-01-29 | 832 | 0
1B | OB-010 | Accounts Payable & Accounts Receivable | 171 | 2020-01-02 | 2020-08-31 | 343 | 0
2A | OB-012 | Accounts Payable & Accounts Receivable | 338 | 2020-09-01 | 2021-12-31 | 343 | 0
1B | OB-022 | Revise Service Area Task Orders for Approval | 20 | 2020-02-04 | 2020-03-02 | 10 | 0
1B | OB-032 | Prepare 4Q2019 CWC invoice | 17 | 16-Jan-20* | 2020-02-07 | 825 | 0
1B | OB-033 | Prepare Q12020 CWC invoice | 18 | 16-Jan-20* | 2020-02-10 | 824 | 0
1B | OB-040 | Monthly Board/Res Comm Support | 171 | 2020-01-02 | 2020-08-31 | 343 | 0
2A | OB-042 | Monthly Board/Res Comm Support | 338 | 2020-09-01 | 2021-12-31 | 343 | 0
2A | OB-052 | Quarterly Reporting | 509 | 2020-01-02 | 2021-12-31 | 343 | 0
2A | OB-062 | Annual Reporting | 509 | 2020-01-02 | 2021-12-31 | 343 | 0
1B | OB-200 | Real Estate Landowner Coordination | 171 | 2020-01-02 | 2020-08-31 | 681 | 0
Risk Assessment |  |  | 195 | 2020-02-25 | 2020-11-30 | 619 | 0
1B | RA-005 | Risk Analysis of Recommend Option Meeting | 40 | 2020-02-25 | 2020-04-20 | 764 | 0
1B | RA-010 | Prepare Cost Risk Update | 10 | 2020-04-21 | 2020-05-04 | 764 | 0
2A | RA-020 | Prepare RA | 66 | 2020-08-26 | 30-Nov-20* | 619 | 0
2A | RA-030 | Submit Admin Final RA | 0 |  | 30-Nov-20* | 619 | 0
General Counsel |  |  | 509 | 2020-01-02 | 2021-12-31 | 343 | 0
1B | GC-000 | General Counsel | 171 | 2020-01-02 | 2020-08-31 | 343 | 0
2A | GC-10 | General Counsel | 338 | 2020-09-01 | 2021-12-31 | 343 | 0

## HDR Breakdown
Task | ICF Est Budget (2/28/20) | HDR Program Management Percent | HDR Technical and Strategy Percent
Biological Assessment/Biological Opinion | 1100000
Mitigation Plan | 800000
Adaptive Management Plan | 400000
Section 106 Programmatic Agreement | 1020000
ITP – Section 2081 Permit-Operations | 400000
ITP – Section 2081 Permit- Construction | 250000
Section 404 Permit
Section 408 Permit
Section 401 Permit
Water Right Permit