## SITES
Activity ID | Activity Name | Remaining Duration | % Complete | Start | Finish | Total Float | Predecessors | Successors | ICF comments | HDR Additional Comments
SITES PROJECT |  | 2411 | 16.78% | 02-Jan-20 A | 1930-01-28 | 0
PHASES |  | 318 | 0% | 2020-11-30 | 2022-02-17 | -35
MS-004-P1b | Ph 2 Amend 1B Complete | 0 | 0% |  | 30-Nov-20* | 196 | OP-00-1B, VP-00-1B, OP-00-00, CON-010, ORA-000, CG-000, TM-98 | MS-004-P2
MS-004-P2 | Ph 2 Amendment 2 | 0 | 0% |  | 17-Feb-22* | -33 | OP-490, PS-020, PS-030, MB-010, AP-012, INV-00-30, INV-033, EXD-010, STP-010, BUS-00-00, MGT-070, RA-010, GC-020, MGT-030, MGT-040, MGT-050, MGT-060, RCB-20-128, CON-030, CON-050, CON-040, AR-040, PC-010, PC-020, PMP-010, WL-015, WL-00-010, WL-00-00, MS-004-P1b, TM-F107, FED-050, EM-00-10, GSR-040, ENG-230, ENG-590, FF-030, REP-010, TM-B99, TM-D97, TM-D99, TM-F99, TM-H99, TM-I98, TM-I99, SF-010, TM-D98 | TM-F98, TM-F97, PDC-1000
MILESTONES |  | 2411 | 0% | 2020-11-02 | 1930-01-28 | 0
MS-020-CS | WIIN Construction Start Date | 0 | 0% |  | 02-Nov-20* | 294
MS-007-PD | Preliminary Project Description Complete | 0 | 0% |  | 2020-12-28 | 2370 | PDE-60 | EIR-019
MS-001-LF | Local Funding (Go/No-go #1) | 0 | 0% |  | 2021-01-07 | 393 | PA-160 | MS-002-LF
MS-002-LF | Local Funding (Go/No-go #2) | 0 | 0% |  | 2021-02-08 | 371 | OP-320, MS-001-LF | MS-003-LF
MS-011-DE | Release Revised Draft EIR/ Supplemental Draft EIS for Public Review | 0 | 0% |  | 2021-07-21 | 2223 | EIR-080
MS-003-LF | Local Funding (Go/No-go #3) | 0 | 0% |  | 2022-02-11 | 107 | CWC-500, MS-002-LF | WP3-010
MS-250-FE | Final EIR/EIS | 0 | 0% |  | 2022-05-13 | 1441 | EIR-250, STA-140 | MS-450-RD
MS-450-RD | ROD Signed | 0 | 0% |  | 2022-09-16 | 1351 | EIR-450, MS-250-FE | MS-500-CS, EIR-460
MS-500-CS | Construction Starts | 0 | 0% |  | 2024-11-11 | 1361 | RC-100, MS-450-RD | MS-510-CC
MS-510-CC | Construction Complete | 0 | 0% |  | 2029-02-23 | 241 | CC-100, RC-100, MS-500-CS, STA-050, STA-060 | MS-600-PB
MS-600-PB | Public Benefits | 0 | 0% |  | 1930-01-28 | 0 | OPR-110, MS-510-CC
PROJECT DESCRIPTION |  | 108 | 89.81% | 11-Feb-20 A | 2021-03-31 | 2303
PDE-00-00 | Project Description | 21 | 89.81% | 11-Feb-20 A | 2020-11-30 | 1600 | PDE-10 | PDE-60 | There is not an 11/30 deliverable and this over arching time frame concludes before the constituent elements PDE 50 and PDE 55 are completed
Components |  | 108 | 0% | 14-Apr-20 A | 2021-03-31 | 2303
PDE-45 | Identify Project-Level vs Program Components (Planning) | 108 | 0% | 14-Apr-20 A | 2021-03-31 | 2303 | VP-095, MS-005-VP | EIR-019 | Modify to make dates the same and is included in the PD deliverable; add ENG -210 to the predecessor list
PDE-47 | Identify Project-Level vs Program Components (Permitting) | 21 | 78.57% | 14-Apr-20 A | 2020-11-30 | 2390 | VP-095 | EIR-019
Develop Project Description |  | 29 | 0% | 29-Apr-20 A | 2020-12-15 | 1549
PDE-50 | Develop Project Description Construction | 29 | 66.67% | 29-Apr-20 A | 2020-12-15 | 1549 | PDE-20, PDE-30, PDE-10, VP-095, PDE-25, PDE-35, VP-090 | PDE-60, BA-024, BA-022 | The next deliverable is 12/28 so these should no longer be considered separate; eng & ops predecessors need to be included
PDE-55 | Project Description Operations Criteria Complete (see Ops Tasks) | 0 | 0% |  | 2020-12-15 | -39 | VP-090, OP-220, OP-1100 | EIR-020, PDE-60
Preliminary Project Description Complete |  | 0 | 0% | 2020-12-28 | 2020-12-28 | 1580
PDE-60 | Preliminary Project Description | 0 | 0% |  | 2020-12-28 | 1580 | PDE-50, ENG-190, ENG-200, PDE-55, ENG-195, PDE-00-00, EIR-021 | EIR-019, BA-001, 106-001, WR-025, MS-007-PD | This end date should line up with PDE 00-00
OPERATIONS MODELING |  | 2133 | 0% | 15-Jun-20 A | 2029-01-03 | 278
Full Operations Analysis |  | 107 | 0% | 15-Jun-20 A | 2021-03-30 | 2304
Cost Summary |  | 107 | 0% | 15-Jun-20 A | 2021-03-30 | -40
OP-$-445 | EIR/EIS Operations Analysis (Cost) | 107 | 0% | 15-Jun-20 A | 2021-03-30 | -40 | OP-410, OP-446
OP-$-452 | Fisheries Modeling (life cycle) (Cost) | 30 | 0% | 2020-11-24 | 2021-01-04 | 21 | OP-1070, OP-0620
OP-$-455 | Cumulative Analysis | 91 | 0% | 2020-11-24 | 2021-03-30 | -40 | OP-1070 | OP-446 | Where is the modeling output tasks for cumulative and climate change so that it is included in the EIR/S schedule for these 2 chapters?
OP-$-315 | Economics | 36 | 0% | 2020-11-24 | 2021-01-12 | 15 | OP-1070, OP-0700, OP-0710
OP-$-460 | Climate Change Analysis | 91 | 0% | 2020-11-24 | 2021-03-30 | -40 | OP-1070 | OP-446 | Where is the modeling output tasks for cumulative and climate change so that it is included in the EIR/S schedule for these 2 chapters?
OP-$-500 | Mercury Modeling | 36 | 0% | 2020-11-24 | 2021-01-12 | 15 | OP-1070, OP-0670
Operations Analysis |  | 17 | 0% | 26-Oct-20 A | 2020-11-24 | 2394
OP-1030 | Second model runs with updated diversion criteria | 10 | 0% | 26-Oct-20 A | 2020-11-13 | -41 | OP-1020 | OP-1040, OP-1050
OP-1040 | Review second run results | 2 | 0% | 2020-11-16 | 2020-11-17 | -41 | OP-1030 | OP-1060
OP-1050 | Preferred diversion criteria (or range) and define negotiating strategy | 2 | 0% | 2020-11-16 | 2020-11-17 | 2399 | OP-1030
OP-1060 | Prep for 2nd mtg with CDFW | 2 | 0% | 2020-11-17 | 2020-11-18 | -41 | OP-1040 | OP-1070
OP-1070 | CDFW Meeting 2 (2-3 hour mtg) | 1 | 0% | 2020-11-23 | 2020-11-23 | -41 | OP-1060, RCB-20-118 | OP-1100, OP-0690, OP-0600, OP-0610, OP-0620, OP-0630, OP-0640, OP-0650, OP-0660, OP-0670, OP-0680, OP-0700, OP-0710, OP-$-452, OP-$-500, OP-$-455, OP-$-460, OP-$-315 | Change to 12/2
OP-1100 | Diversion Criteria Finalized | 1 | 0% | 2020-11-24 | 2020-11-24 | -39 | OP-1020, OP-1070, OP-1080, OP-1090 | PDE-55, BA-022 | Move to date of CDFW Mtg #2 if the expectation is that we will receive input on the call. Otherwise, needs to reflect the date that all ops criteria is finalized w/agencies. EIR-021 and the PDE tasks need to be added as a successor. The PD can't be completed w/o the operations criteria.
Modeling Suite |  | 86 | 0% | 2020-11-23 | 2021-03-30 | -39 |  |  | with the exception of power and economic all these modeling results are needed to define an operations scenario that is likely to be considered permitable by the regulatory agencies. They are also an essential part of the effects analysis that will help define the operations described in the project descriptions (PDE 00-00)
OP-0690 | Power (LTGen, SWP_Power, & Sites_Power) | 33 | 0% | 2020-11-23 | 2021-01-12 | 14 | OP-425, OP-1070 | OP-446 | When is CalSim completed?
OP-0600 | USRDOM | 27 | 0% | 2020-11-23 | 2021-01-04 | 20 | OP-1070 | OP-446, BA-025
OP-0610 | HEC-5Q & RecTemp | 27 | 0% | 2020-11-23 | 2021-01-04 | 20 | OP-1070 | OP-446, BA-025
OP-0620 | Fish Mortality (Anderson & Martin) | 27 | 0% | 2020-11-23 | 2021-01-04 | 20 | OP-1070 | OP-446, OP-$-452, BA-025
OP-0630 | SALMOD, SalMort, &RecMort | 27 | 0% | 2020-11-23 | 2021-01-04 | 20 | OP-1070 | OP-446, BA-025
OP-0640 | DSM2 (Hydro &Qual) | 27 | 0% | 2020-11-23 | 2021-01-04 | 20 | OP-1070 | OP-446, BA-025
OP-0650 | IOS &DPM (Cramer) | 27 | 0% | 2020-11-23 | 2021-01-04 | 20 | OP-1070 | OP-446, BA-025
OP-0660 | OBAN (QEDA) | 27 | 0% | 2020-11-23 | 2021-01-04 | -4 | OP-1070 | OP-320, OP-446, BA-025
OP-0670 | Mercury (RBI) | 33 | 0% | 2020-11-23 | 2021-01-12 | 14 | OP-1070 | OP-446, OP-$-500
OP-0680 | Reservoir Water Quality | 33 | 0% | 2020-11-23 | 2021-01-12 | 14 | OP-1070 | OP-446
OP-0700 | Water Supply Economic (SWAP &CWEST) (as needed) | 33 | 0% | 2020-11-23 | 2021-01-12 | 14 | OP-1070 | OP-446, OP-$-315
OP-0710 | Water Quality Economics (BAWQM & LCRBWQM) as needed) | 33 | 0% | 2020-11-23 | 2021-01-12 | 14 | OP-1070 | OP-446, OP-$-315
OP-446 | Full Operations Analysis Complete | 0 | 0% |  | 2021-03-30 | -39 | OP-0600, OP-0610, OP-0620, OP-0630, OP-0640, OP-0650, OP-0660, OP-0670, OP-0680, OP-0690, OP-0700, OP-0710, OP-$-455, OP-$-460, EIR-020 | CES-090, OP-450, CFS-010, OP-480, OP-$-445, ENG-390, CFS-020 | What does this include and how did this jump from 1/12 to 3/30? As I read this, the output needed for the WQ/Aquatics analysis will not be complete until after the Admin Draft EIR/S and | Spranza, John: To IC'f point, this has been extended to 03/30/21 and that date needs to be trued up with the EIR/EIS scheule which then feeds the effects analysis and so on.
EIR/EIS AND BA/ITP Documentation |  | 164 | 0% | 2021-01-04 | 2021-08-26 | 2164
OP-320 | Appendices for EIR/EIS | 25 | 0% | 2021-01-04 | 2021-02-08 | -4 | OP-0660 | EIR-035, EIR-020, MS-002-LF, EIR-023, OP-450 | See Mike's comment bubble. is this a rolling deliverable? If not, there is not enough time to cross check the text for the Admin Draft EIR/S
OP-450 | BA/ITP and Water Rights Modeling Support | 62 | 0% | 2021-04-01 | 2021-06-28 | 2164 | OP-446, OP-320 | OP-360
OP-360 | Appendices for BA/ITP | 42 | 0% | 2021-06-29 | 2021-08-26 | 2164 | OP-450
Operations Plan, Ver 1 |  | 232 | 0% | 2021-01-04 | 2021-11-23 | 27
OP-470 | Operations Plan, Version 1 | 232 | 0% | 04-Jan-21* | 2021-11-23 | 24 |  | OP-475, OP-480, ENG-390, CFS-010, CFS-020 | How does this relate to the operations plan included in the EIR/EIS and BA?
OP-475 | Support Development of Ops Plan Ver 1 Documentation | 192 | 0% | 2021-03-01 | 2021-11-23 | 27 | OP-470 | OP-490
Operational Agreements |  | 232 | 0% | 2021-03-31 | 2022-02-17 | -35
OP-480 | Support Operational Agreements | 232 | 0% | 2021-03-31 | 2022-02-17 | -35 | OP-446, OP-470 | OP-490
OP-490 | Support for Operational Agreements Documentation | 192 | 0% | 2021-05-26 | 2022-02-17 | -35 | OP-480, OP-475 | MS-004-P2
Bridging Analysis for CWC/WSIP Benefits |  | 94 | 0% | 2021-04-01 | 2021-08-12 | -28
CFS-010 | CWC/WSIP Operations Modeling | 65 | 0% | 2021-04-01 | 2021-07-01 | 1 | OP-446, OP-0230, OP-470 | CFS-020
CFS-020 | CWC/WSIP Fisheries Modeling (life cycle) | 21 | 0% | 2021-05-27 | 2021-06-25 | -39 | CFS-010, OP-0230, OP-446, OP-470 | CFS-030
CFS-030 | CWC/WSIP Documentation and Appendices | 31 | 0% | 2021-06-30 | 2021-08-12 | -39 | CFS-020 | CWC-391, ENG-300
Final Sites-Reclamation Operating Agreement |  | 328 | 0% | 2021-07-22 | 2022-11-14 | 1862
FO-1000 | Final Sites-Reclamation Operating Agreement | 328 | 0% | 2021-07-22 | 2022-11-14 | 1862 | EIR-080, POF-040, POF-510, POF-570
Final Sites-DWR Operating Agreement |  | 328 | 0% | 2021-07-22 | 2022-11-14 | 1862
FO-1010 | Final Sites-DWR Operating Agreement | 328 | 0% | 2021-07-22 | 2022-11-14 | 1862 | EIR-080, POF-040, POF-510, POF-530
Final TCCA Facility Use Agreement |  | 328 | 0% | 2021-07-22 | 2022-11-14 | 1862
FO-1020 | Final TCCA Facility Use Agreement | 328 | 0% | 2021-07-22 | 2022-11-14 | 1862 | EIR-080, POF-040, POF-510
Final GCID Facility Use Agreement |  | 328 | 0% | 2021-07-22 | 2022-11-14 | 1862
FO-1030 | Final GCID Facility Use Agreement | 328 | 0% | 2021-07-22 | 2022-11-14 | 1862 | EIR-080, POF-040, POF-510
Final CBDA Facility Use Agreement |  | 328 | 0% | 2021-07-22 | 2022-11-14 | 1862
FO-1040 | Final CBDA Facility Use Agreement | 328 | 0% | 2021-07-22 | 2022-11-14 | 1862 | EIR-080, POF-040, POF-510
Operations Plan, Version 2 |  | 370 | 0% | 2021-07-22 | 2022-12-21 | 1853 |  |  | How does this relate to the operations plan included in the EIR/EIS and BA?
FO-1050 | Operations Plan, Version 2 | 370 | 0% | 2021-07-22 | 2022-12-21 | 1853 | EIR-080
Annual Operating Plan Process and Procedures |  | 519 | 0% | 2021-10-19 | 2023-10-13 | 1641
FO-1060 | Annual Operating Plan Processes and Procedures | 519 | 0% | 2021-10-19 | 2023-10-13 | 1641 | EIR-100 | FO-1070
Develop Organizational Operating Roles and Responsibilities |  | 519 | 0% | 2021-10-19 | 2023-10-13 | 1641
FO-1070 | Develop Organizational Operating Roles and Responsibilities | 519 | 0% | 2021-10-19 | 2023-10-13 | 1641 | FO-1060
Provide Operations Input on Response to Comments and Final EIR/EIS |  | 20 | 0% | 2022-03-21 | 2022-04-15 | 2031
FO-1080 | Provide Operations Input on Response to Comments and Final EIR/EIS | 20 | 0% | 2022-03-21 | 2022-04-15 | 2031 | EIR-100, EIR-110, EIR-214 |  | Is this dependent on OP-470 or FO -1050? If the latter, the end date for this activity preceeds the end dates for needed inputs.
Member Portal/Accounting System |  | 0 | 0% | 2029-01-03 | 2029-01-03 | 278
FO-1100 | Member Portal/Accounting System | 0 | 0% |  | 03-Jan-29* | 278
Operations Support |  | 717 | 0% | 2021-11-12 | 2024-08-13 | 1424
OS-1120 | Operations Support for Permitting | 105 | 0% | 2021-11-12 | 2022-04-08 | 1445 | BA-1110, STA-110
OS-1130 | Operations Support for Water Rights | 26 | 0% | 2023-03-15 | 2023-04-19 | 1424 | WR-165, WR-175
OS-1150 | Develop Sites-Specific Model | 344 | 0% | 2023-04-20 | 2024-08-13 | 1424 | WR-175
Task Management - Work Group-Res Comm-Authority Support |  | 339 | 0% | 28-Aug-20 A | 2022-02-17 | -35
TM-D98 | Operations Task Management | 321 | 0% | 28-Aug-20 A | 2022-02-17 | -33 | WP2-130 | MS-004-P2
TM-D99 | Operations Expenses | 321 | 0% | 01-Sep-20 A | 2022-02-17 | -33 |  | MS-004-P2
TM-D97 | Operations Work Group Support | 339 | 0% | 13-Oct-20 A | 2022-02-17 | -35 | 106-003 | MS-004-P2
EIR/EIS |  | 1060 | 2.46% | 01-Sep-20 A | 2024-11-22 | 1351
Project Description Chapter |  | 65 | 49.38% | 22-Sep-20 A | 2021-01-29 | 2346
EIR-021 | Prepare Revised Draft EIR/SDEIS Project Description Chapter | 41 | 49.38% | 22-Sep-20 A | 2020-12-28 | 1580 | EIR-015, WP2-130 | EIR-030, FED-020, ENG-290, ENG-265, EIR-480, PDE-60 | Need supporting Eng and Ops tasks added as predessors since that is what is needed to complete the PD. What is EIR-015? I don’t see it as an activity.
EIR-480 | Ad Hoc Environmental Planning and Permitting Briefing Revised Draft EIR/SDEIS Project Description | 1 | 0% | 2020-12-17 | 2020-12-17 | 2346 | EIR-021 | EIR-490
EIR-490 | Final Revised Draft EIR/SDEIS Proj. Desc. to Ad Hoc EPP Work Group, Reservoir Comm & Board for Review & Approval to Post | 15 | 0% | 2021-01-11 | 2021-01-29 | 2346 | EIR-480
Revised Draft EIR/Supplemental Draft EIS |  | 178 | 0% | 01-Sep-20 A | 2021-07-21 | 7
Prepare Administrative Revised Draft EIR/Supplemental Draft EIS |  | 111 | 0% | 01-Sep-20 A | 2021-04-15 | 7
EIR-005 | Prepare Revised Admin Draft EIR/SDEIS Summary | 111 | 0% | 01-Sep-20 A | 2021-04-15 | 7 | EIR-019 | EIR-023
EIR-019 | Prepare Revised Draft EIR/SDEIS Analysis (Construction) | 26 | 62.86% | 01-Sep-20 A | 2020-12-10 | -36 | PDE-40, PDE-60, PDE-45, PDE-42, EIR-010, WP2-120, ENG-220, WP2-130, PDE-47, OP-420, EIR-015, MS-007-PD | EIR-035, EIR-030, EIR-020, EIR-025, EIR-005, TM-E98, TM-E99, TM-E97
EIR-030 | Complete Admin Draft EIR/SDEIS | 100 | 0% | 22-Sep-20 A | 2021-03-30 | 7 | EIR-019, EIR-021 | EIR-035, EIR-500
EIR-025 | Prepare Cumulative and Climate Change Sections | 74 | 0% | 2020-12-11 | 2021-03-30 | 7 | EIR-019 | EIR-035 | Need EIR-019 replaced with modeling app predecsessor
EIR-020 | Prepare Revised Draft EIR/EIS Analysis (Operations) | 71 | 0% | 2020-12-16 | 2021-03-30 | -39 | WP2-120, OP-0230, OP-0240, OP-0250, OP-0260, PDE-55, EB-00-00, OP-320, ENG-510, EIR-019 | EIR-035, OP-446, EIR-023 | OP-446 is a predecessor not a successor. We can't start writing the analysis without modeling output to write WQ/Aquatics chapters.
EIR-023 | Status Update to Ad Hoc EPP Work Group, Reservoir Comm., and Board | 11 | 0% | 2021-04-01 | 2021-04-15 | 7 | OP-320, EIR-020, EIR-005 | FED-090, DB-100, EIR-035
Prepare Public Revised Draft EIR/Supplemental Draft EIS |  | 78 | 0% | 2021-04-01 | 2021-07-21 | 7 |  |  | Comments on this section submitted to Laurie and Linda on 11/4
EIR-035 | Authority/Reclamation/Integration Review of Admin Draft EIR/EIS | 22 | 0% | 2021-04-01 | 2021-04-30 | 7 | EIR-020, EIR-025, EIR-019, OP-320, EIR-030, EIR-023 | EIR-040, EIR-026
EIR-026 | Prepare Revised Public Draft EIR/EIS Summary | 78 | 0% | 2021-04-01 | 2021-07-21 | 7 | EIR-035 | EIR-067
EIR-040 | Incorporate comments/edits and prepare Revised Draft EIR/SEIS | 21 | 0% | 2021-05-03 | 2021-06-01 | 7 | EIR-035 | ENG-340, EIR-045
EIR-045 | Live Edit Meeting | 1 | 0% | 2021-06-02 | 2021-06-02 | 7 | EIR-040 | EIR-050
EIR-050 | Legal Review of Revised Draft EIR/SEIS | 15 | 0% | 2021-06-03 | 2021-06-23 | 7 | EIR-045 | EIR-055, EIR-060, EIR-500, EIR-060
EIR-055 | Prepare Public Revised Draft EIR/SEIS Summary | 30 | 0% | 2021-06-03 | 2021-07-15 | 9 | EIR-050 | EIR-510
EIR-500 | Authority Ad Hoc EPP Work Group, Reservoir Comm., and Board Briefing on the Public Revised Draft EIR/SDEIS | 12 | 0% | 2021-06-15 | 2021-06-30 | 14 | EIR-030, EIR-050 | EIR-060
EIR-060 | Resolve Legal Comments on Revised Draft EIR/SEIS | 9 | 0% | 2021-06-24 | 2021-07-07 | 7 | EIR-050, EIR-500, EIR-050 | EIR-065, EIR-067
EIR-065 | Live Edit Meeting | 1 | 0% | 2021-07-07 | 2021-07-07 | 7 | EIR-060 | EIR-070, EIR-067
EIR-067 | Final Editing, Formatting and Doc Production | 10 | 0% | 2021-07-08 | 2021-07-21 | 7 | EIR-060, EIR-065, EIR-026 | EIR-070, EIR-080, EIR-510
EIR-510 | Ad Hoc Environmental Planning and Permitting Work Group Final Briefing of Public Draft Revised EIR/SDEIS | 1 | 0% | 2021-07-15 | 2021-07-15 | 9 | EIR-055, EIR-067 | EIR-520
EIR-520 | Reservoir Comm Final Briefing of Public Draft Revised EIR/SDEIS & provide rec to Auth Board for release of Public Draft | 1 | 0% | 2021-07-16 | 2021-07-16 | 9 | EIR-510 | EIR-070
EIR-070 | Special Board Meeting for approval to release the Revised Draft EIR/SDEIS for Public Review | 1 | 0% | 2021-07-19 | 2021-07-19 | 9 | EIR-065, EIR-067, EIR-520 | EIR-080, POF-510
EIR-080 | Authority Release Revised Draft EIR/SDEIS and Issue Public Notices | 0 | 0% |  | 2021-07-21 | 7 | EIR-070, EIR-067 | EIR-090, CWC-450, MS-011-DE, FO-1050, FO-1000, FO-1010, FO-1020, FO-1030, FO-1040, 404-001
Public Review |  | 42 | 0% | 2021-07-22 | 2021-09-18 | 2181
EIR-090 | Public Review Period | 59 | 0% | 2021-07-22 | 2021-09-18 | 11 | EIR-080 | EIR-095, EIR-530, EIR-095
EIR-530 | Public Meetings | 15 | 0% | 2021-08-09 | 2021-08-27 | 2163 | EIR-090
Begin Preparation of the Admin Revised Final EIR/Supplemental Final EIS |  | 26 | 0% | 2021-09-20 | 2021-10-26 | 12
EIR-100 | Approach to Response to Comments | 20 | 0% | 2021-09-20 | 2021-10-18 | 12 | EIR-095 | EIR-105, FO-1080, FO-1060, EIR-210
EIR-092 | Determine Approach for EIR/EIS Response to Comments Summary | 26 | 0% | 2021-09-20 | 2021-10-26 | 12 | EIR-095 | EIR-105
EIR-095 | Categorize and Sort Comments by Topic | 20 | 0% | 2021-09-20 | 2021-10-18 | 8 | EIR-090, CWC-450, EIR-090 | EIR-100, EIR-110, EIR-092
EIR-105 | Authority/Reclamation/Legal Review | 6 | 0% | 2021-10-19 | 2021-10-26 | 12 | EIR-100, EIR-092 | EIR-540
Environmental Feasibility Report For CWC |  | 51 | 0% | 2021-09-20 | 2021-12-03 | 2098
EIR-110 | Prepare Draft Environmental Feasibility Report for CWC | 30 | 0% | 2021-09-20 | 2021-11-01 | 8 | EIR-095 | EIR-540, EIR-115, EIR-00-SR, FO-1080
EIR-00-SR | Summary Report for CWC | 51 | 0% | 2021-09-20 | 2021-12-03 | 8 | EIR-110 | EIR-120
EIR-540 | Authority review of Draft Environmental Feasibility Report for CWC | 8 | 0% | 2021-11-02 | 2021-11-12 | 8 | EIR-110, EIR-105 | EIR-115, EIR-560
EIR-115 | Ad Hoc EPP Work Group Briefing on Draft Environmental Feasibility Report | 5 | 0% | 2021-11-15 | 2021-11-19 | 8 | EIR-540, EIR-110 | EIR-550
EIR-560 | Legal Review of Draft Environmental Feasbility Report for CWC | 5 | 0% | 2021-11-15 | 2021-11-19 | 8 | EIR-540 | EIR-550
EIR-550 | Reservoir Committee Briefing on Draft Environmental Feasibility Report | 1 | 0% | 2021-11-19 | 2021-11-19 | 8 | EIR-560, EIR-115 | EIR-117
EIR-117 | Live Edit Meeting of Draft Environmental Feasibility Report for CWC | 1 | 0% | 2021-11-22 | 2021-11-22 | 8 | EIR-550 | EIR-570, EIR-580
EIR-580 | Resolve Legal Comments and prepare Final Feasibility Report for CWC | 7 | 0% | 2021-11-23 | 2021-12-03 | 8 | EIR-117 | EIR-120, EIR-570
EIR-570 | Board Briefing of Draft Environmental Feasibility Report for CWC | 1 | 0% | 2021-11-24 | 2021-11-24 | 2103 | EIR-117, EIR-580
EIR-120 | Final Environmental Feasibility Report Submittal to CWC | 0 | 0% |  | 2021-12-03 | 8 | EIR-580, EIR-00-SR | CWC-500, TM-F107
Revised Final EIR/Supplemental Final EIS |  | 149 | 0% | 2021-10-19 | 2022-05-13 | 1420
EIR-210 | Preparation of Final EIR/EIS | 92 | 0% | 2021-10-19 | 2022-03-04 | 1396 | EIR-100 | WR-125, EIR-212, STA-140, 401-120
EIR-212 | Authority/Reclamation/Integration Review of Admin Draft EIR/EIS | 15 | 0% | 2022-03-07 | 2022-03-25 | 1420 | EIR-210 | EIR-214
EIR-214 | Incorporate Authority/Reclamation/Integration Comments | 15 | 0% | 2022-03-28 | 2022-04-15 | 1420 | EIR-212 | EIR-220, FO-1080
EIR-220 | Legal Review of Final EIR/EIS | 10 | 0% | 2022-04-18 | 2022-04-29 | 1420 | EIR-214 | EIR-240
EIR-240 | Incorporate Legal Comments (including live edit meeting) | 10 | 0% | 2022-05-02 | 2022-05-13 | 1420 | EIR-220 | EIR-250
EIR-250 | Complete Final EIR/EIS | 0 | 0% |  | 2022-05-13 | 1420 | EIR-240, STA-110, STA-120 | EIR-400, MS-250-FE, EIR-300, EIR-410
NOD, Findings of Fact, Statement of Overriding Considerations, Mitigation Monitoring Program |  | 32 | 0% | 2022-04-25 | 2022-06-07 | 1423
EIR-300 | Prepare Draft Findings of Fact, Statement of Overriding Considerations, Mitigation Monitoring Program | 15 | 0% | 2022-04-25 | 2022-05-13 | 1423 | EIR-250 | EIR-330
EIR-330 | Authority and Legal Review of Findings of Fact, Statement of Overriding Considerations, Mitigation Monitoring Program | 5 | 0% | 2022-05-16 | 2022-05-20 | 1423 | EIR-300 | EIR-350
EIR-350 | Incorporate Comments and Prepare NOD, Findings, Statement of Overriding Considerations, MMRP | 5 | 0% | 2022-05-23 | 2022-05-27 | 1423 | EIR-330 | EIR-360
EIR-360 | Work Group and Reservoir Committee Briefings | 5 | 0% | 2022-06-01 | 2022-06-07 | 1423 | EIR-350 | EIR-370
Authority Certifies EIR and Approves Project and File NOD |  | 1 | 0% | 2022-06-07 | 2022-06-08 | 1423
EIR-370 | Authority Certifies EIR and Approves Project | 0 | 0% |  | 2022-06-07 | 1423 | EIR-360 | EIR-380
EIR-380 | File NOD | 0 | 0% |  | 2022-06-08 | 1423 | EIR-370 | EIR-450
ROD |  | 90 | 0% | 2022-05-16 | 2022-09-16 | 1351
EIR-410 | Prepare Draft ROD | 15 | 0% | 2022-05-16 | 2022-06-03 | 1421 | EIR-250 | EIR-420
EIR-400 | Reclamation Final EIS Process | 21 | 0% | 2022-05-16 | 2022-06-13 | 1420 | EIR-250 | EIR-440
EIR-420 | Submit Draft ROD to NEPA Team | 0 | 0% |  | 2022-06-03 | 1421 | EIR-410 | EIR-430
EIR-430 | NEPA Team Review | 5 | 0% | 2022-06-06 | 2022-06-10 | 1421 | EIR-420 | EIR-440
EIR-440 | NEPA Team Approval to Sign | 0 | 0% |  | 2022-06-13 | 1420 | EIR-430, EIR-400 | EIR-450
EIR-450 | ROD Signed | 0 | 0% |  | 2022-09-16 | 1351 | EIR-440, EIR-380, FED-090 | MS-450-RD, EIR-460
Additional NEPA/CEQA Review, if needed |  | 570 | 0% | 2022-09-19 | 2024-11-22 | 1351
EIR-460 | Additional NEPA/CEQA Documents, if needed | 570 | 0% | 2022-09-19 | 2024-11-22 | 1351 | EIR-450, MS-450-RD
Task Management - Work Group-Res Comm-Authority Support |  | 288 | 0% | 01-Sep-20 A | 2021-12-30 | -39
TM-E98 | Environmental Task Management | 288 | 0% | 01-Sep-20 A | 2021-12-30 | -39 | EIR-019 | CWC-391
TM-E97 | Environmental Work Group Support | 288 | 0% | 01-Sep-20 A | 2021-12-30 | -39 | EIR-019 | CWC-391
TM-E99 | Environmental Expenses | 288 | 0% | 01-Sep-20 A | 2021-12-30 | -39 | EIR-019 | CWC-391
PERMITTING |  | 321 | 1.4% | 14-Apr-20 A | 2022-02-17 | -33
CWC Feasibility Report |  | 321 | 0% | 30-Oct-20 A | 2022-02-17 | -33
CWC-010 | Mitigation Measure Evaluation/Cost Estimate | 288 | 0% | 30-Oct-20 A | 2021-12-30 | -39 | ENG-380 | ENG-392
TM-F107 | CWC Feasibility Report Permitting Support | 51 | 0% | 2021-12-06 | 2022-02-17 | -33 | EIR-120 | MS-004-P2
Geotechnical Field Monitoring |  | 243 | 0% | 2020-12-01 | 2021-11-18 | 17
GSR-015 | Geotechnical Field Monitoring | 243 | 0% | 2020-12-01 | 2021-11-18 | 17 | GPP-00-00 | ENG-404, ENG-406
Task Management - Work Group-Res Comm-Authority Support |  | 321 | 5.03% | 14-Apr-20 A | 2022-02-17 | -33 |  |  |  | For TM F98, 99 and 97 we are cureently only contracted through 12/31/21
TM-F98 | Permitting Task Management | 321 | 5.03% | 14-Apr-20 A | 2022-02-17 | -33 | WP2-130, BA-019, MS-004-P2 | TM-F99
TM-F99 | Permitting Expenses & Fees | 321 | 5.03% | 14-Apr-20 A | 2022-02-17 | -33 | TM-F98 | MS-004-P2
TM-F97 | Permitting Work Group Support | 321 | 5.03% | 13-Oct-20 A | 2022-02-17 | -33 | 106-003, MS-004-P2
FEDERAL PERMITS |  | 1098 | 17.26% | 14-Apr-20 A | 2025-01-15 | 1313
Phase 1 Environmental Site Assessments |  | 763 | 0% | 2022-02-14 | 2025-01-15 | 1313
FED-010 | Phase 1 Environmental Site Assessments | 763 | 0% | 2022-02-14 | 2025-01-15 | 1313 | WP3-010
U.S. Army Corps of Engineers CWA 404, Rivers and Harbors Act Section 10 |  | 591 | 0% | 05-May-20 A | 2023-02-06 | 1820
FED-020 | U.S. Army Corps of Engineers CWA 404, Rivers and Harbors Act Section 10 | 591 | 0% | 2020-11-02 | 2023-02-06 | 1820 | EIR-021 | FED-030 | predecessor sh also include 404-025
Clean Water Act Section 404 |  | 477 | 0% | 05-May-20 A | 2022-08-30 | 1934
404-003 | USACE LEDPA & NEPA , 404/408 and WD Approach on Secion 404 Application | 18 | 78.31% | 05-May-20 A | 2020-11-30 | 1764 | WP-020, VP-070, BA-019, 404-001 | 404-050, 404-010, 401-130, 401-120, 106-000, 404-00-00, 404-015 | 408 needs to be pushed to later in the schedule | Concurrent with 404-025
404-00-00 | Clean Water Act 404 Permit Application Summary | 455 | 0% | 05-May-20 A | 2022-08-30 | 1913 | 404-003 | 404-120
404-001 | Prepare LEDPA analysis | 83 | 49.08% | 01-Sep-20 A | 2021-07-21 | 2190 | VP-070, EIR-080 | 404-003 | See Mike's comment | Concurrent with 404-025
404-010 | Desktop Wetland Delineation Analysis (includes Waters of the State) | 144 | 0% | 2020-12-01 | 2021-06-28 | 1764 | 404-003, ENG-220 | 404-050, 404-020, 401-130, 404-015
404-025 | Pre-Application Meeting | 1 | 0% | 2021-02-02 | 2021-02-02 | 2227 | 404-030 | 404-050
404-015 | Aquatic Resources Mapping and Reporting | 27 | 0% | 2021-05-20 | 2021-06-28 | 1765 | 404-010, 404-003 | 404-030 |  | same as Wetland Delienation
404-020 | Submit Delineation to USACE | 0 | 0% |  | 2021-06-29 | 1764 | 404-010 | 404-030 |  | Concurrent or prior to 404-120. Suggest prior to
404-030 | Preliminary Wetland Delineation Acceptance | 90 | 0% | 2021-06-30 | 2021-09-28 | 2516 | 404-020, 404-015 | 404-050, 401-130, 404-025 |  | Original schedule showed June 2021…need to go back to that.
404-050 | Prepare Draft 404 Application | 40 | 0% | 2021-09-28 | 2021-11-24 | 2063 | 404-003, 404-010, 404-030, 404-025 | 404-060 | We will be starting the 404 after the pre-app mtg. Duration is much greater than 40 days | Start date of February 3 (day after pre-app meeting)
404-035 | Prepare Compensatory Mitigation Plan | 152 | 0% | 2021-11-23 | 2022-07-05 | 1913 | CES-200 | 404-060 |  | Original schedule showed this to be 2021 activity. This needs to accompany draft permit application . This is developed in tangent (February 2, 2021 through November 2021)
404-060 | Authority/Integration/Work Group Review of Draft 404 Application | 20 | 0% | 2022-07-06 | 2022-08-02 | 1913 | 404-050, 404-035 | 404-070 |  | This needs to be right after the draft permit application is finalized (in 2021). Needs to be consistent with original schedule of submitting 404 appliation to agency on December 22, 2021
404-070 | Prepare Final 404 Application | 20 | 0% | 2022-08-03 | 2022-08-30 | 1913 | 404-060 | 404-120
404-120 | Submit 404 Application | 0 | 0% |  | 2022-08-30 | 1913 | 404-070, 404-00-00 | CWC-510
U.S. Army Corps of Engineers Rivers and Harbors Act Section 14, Section 408 |  | 591 | 0% | 2020-11-02 | 2023-02-06 | 1820
FED-030 | U.S. Army Corps of Engineers Rivers and Harbors Act Section 14, Section 408 | 591 | 0% | 2020-11-02 | 2023-02-06 | 1820 | FED-020 | STA-030
Section 408 |  | 401 | 0% | 2020-11-02 | 2022-05-16 | 1826
408-005 | Coordinate with CVFPB and USACE on Section 408/Encroachment Permit | 66 | 0% | 2020-11-02 | 2021-02-01 | 2032 | VP-070, WP2-130 | 408-010, 408-130 | schedule needs to be modified to align w/design and encroachment permit schedule
408-00-00 | Section 408/Encroachment Permit Summary | 401 | 0% | 2020-11-02 | 2022-05-16 | 1826 | WP2-130
408-010 | Assume Start of 50% Design of 408 Jurisdictional Features | 0 | 0% |  | 2021-11-16 | 1826 | 408-005, ENG-390 | 408-130
408-130 | Prepare Draft Encroachment Permit/408 Request w/Engineering Team | 129 | 0% | 2021-11-17 | 2022-05-16 | 1826 | 408-005, 408-010 | 408-135
Section 408 Amend 3 |  | 184 | 0% | 2022-05-17 | 2023-01-27 | 1826
408-135 | Continue Draft Encroachment Permit/408 Request w/Engineering Team | 124 | 0% | 2022-05-17 | 2022-11-04 | 1826 | 408-130 | 408-140
408-140 | Authority/Integration/Work Group Review of Draft | 20 | 0% | 2022-11-07 | 2022-12-02 | 1826 | 408-135 | 408-150
408-150 | Prepare Encroachment Permit/408 Request | 40 | 0% | 2022-12-05 | 2023-01-27 | 1826 | 408-140 | 408-160
408-160 | Submit Encroachment Permit/408 Request | 0 | 0% |  | 2023-01-27 | 1826 | 408-150 | CWC-510
U.S. EPA and U.S. Army Corps of Engineers LEDPA Review |  | 591 | 0% | 2020-11-02 | 2023-02-06 | 1820
FED-040 | U.S. EPA and U.S. Army Corps of Engineers LEDPA Review | 591 | 0% | 2020-11-02 | 2023-02-06 | 1820 | WP2-130
Advisory Council on Historic Preservation NHPA Section 106 |  | 294 | 0% | 01-Sep-20 A | 2021-12-16 | 2117
106-00-00 | Section 106 Programmatic Agreement Summary | 279 | 0% | 01-Sep-20 A | 2021-12-16 | 2089 | WP2-130
FED-050 | Advisory Council on Historic Preservation NHPA Section 106 | 279 | 17.46% | 01-Sep-20 A | 2021-12-16 | 9 | 106-001 | MS-004-P2
106-006 | SHPO Review and Comments | 30 | 0% | 2020-11-02 | 2020-12-01 | 3038 | 106-003 | 106-021
106-021 | Prepare Consultation Information Package | 23 | 0% | 2020-12-01 | 2021-01-05 | 2130 | 106-006 | 106-022
106-022 | Reclamation Review | 5 | 0% | 2021-01-05 | 2021-01-12 | 2130 | 106-021 | 106-024
106-024 | Revisions | 9 | 0% | 2021-01-12 | 2021-01-26 | 2130 | 106-022 | 106-025, 106-032
106-025 | Reclamation Distributes to SHPO and Invited Consulting Parties | 5 | 0% | 2021-01-26 | 2021-02-02 | 2131 | 106-024 | 106-026, 106-033
106-032 | Arrange Meeting Logistics and Prepare Materials | 20 | 0% | 2021-01-26 | 2021-02-24 | 2130 | 106-024 | 106-042
106-033 | Conduct Meetings | 10 | 0% | 2021-02-02 | 2021-02-17 | 2131 | 106-025 | 106-042, 106-041
106-026 | Parties Accept Invitation for Consulting Party Status | 30 | 0% | 2021-02-03 | 2021-03-04 | 3048 | 106-025 | 106-052
106-041 | Prepare Draft PA | 10 | 0% | 2021-02-17 | 2021-03-03 | 2131 | 106-033 | 106-042
106-042 | Reclamation Review | 10 | 0% | 2021-03-04 | 2021-03-18 | 2130 | 106-032, 106-033, 106-041 | 106-044, 106-052
106-044 | Revisions | 15 | 0% | 2021-03-18 | 2021-04-09 | 2141 | 106-042 | 106-061
106-052 | Circulate Draft PA to SHPO and Consulting Parties | 5 | 0% | 2021-03-18 | 2021-03-25 | 2130 | 106-026, 106-042 | 106-053
106-053 | Deadline for Comments on Draft PA | 30 | 0% | 2021-03-26 | 2021-04-24 | 3033 | 106-052 | 106-061
106-061 | Prepare Draft Final PA | 25 | 0% | 2021-04-26 | 2021-05-28 | 2131 | 106-053, 106-044 | 106-062
106-062 | Reclamation Review | 10 | 0% | 2021-06-01 | 2021-06-14 | 2131 | 106-061 | 106-064
106-064 | Revisions | 10 | 0% | 2021-06-15 | 2021-06-28 | 2131 | 106-062 | 106-072
106-071 | Consult with SHPO and Consulting Parties on Draft Final PA | 27 | 0% | 2021-06-29 | 2021-08-05 | 2131 | 106-072 | 106-073
106-072 | Circulate Draft Final PA to SHPO and Consulting Parties | 5 | 0% | 2021-06-29 | 2021-07-06 | 2131 | 106-064 | 106-071, 106-073
106-073 | Deadline for Comments on Draft Final PA | 30 | 0% | 2021-07-07 | 2021-08-05 | 3030 | 106-072, 106-071 | 106-081
106-081 | Prepare Final PA | 20 | 0% | 2021-08-05 | 2021-09-02 | 2131 | 106-073 | 106-082
106-082 | Reclamation Review | 10 | 0% | 2021-09-02 | 2021-09-17 | 2131 | 106-081 | 106-084
106-084 | Revisions | 12 | 0% | 2021-09-17 | 2021-10-05 | 2131 | 106-082 | 106-091, 106-092
106-091 | Consult with SHPO and Consulting Parties on Final PA | 5 | 0% | 2021-10-05 | 2021-10-13 | 2132 | 106-084 | 106-093
106-092 | Circulate Final PA to SHPO and Consulting Parties for Signatures | 5 | 0% | 2021-10-05 | 2021-10-13 | 2131 | 106-084 | 106-093
106-093 | Deadline for Signatures on Final PA | 0 | 0% |  | 2021-10-14 | 3028 | 106-092, 106-091 | CWC-510
USFWS and NMFS ESA Section 7 |  | 365 | 35.32% | 14-Apr-20 A | 2022-03-27 | 2046
FED-060 | USFWS and NMFS ESA Section 7 | 279 | 17.46% | 01-Sep-20 A | 2021-12-16 | 2089 | WP2-130
Biological Assessment |  | 270 | 35.32% | 14-Apr-20 A | 2021-11-12 | 2045
BA-000 | Biological Assessment/Biological Opinion Summary | 257 | 35.3% | 14-Apr-20 A | 2021-11-12 | 2015
BA-011 | Mitigation Planning | 99 | 34% | 01-Sep-20 A | 2021-03-29 | 2019 | BA-010, WP2-130 | BA-057 | See Mike's comment. Mitigation planning should be driven by the effects analysis so we know what needs to be mitigated. There are only 4 working days determine a reasonable mitigation obligation. Also mitigation actions need to be included in the project descriptions to get credit for it in the sect 7 analysis
BA-016 | Adaptive Management Plan | 87 | 36.96% | 01-Sep-20 A | 2021-03-11 | 2010 | BA-015, WP2-130 | BA-030
BA-001 | Initial Desktop Analysis | 34 | 43.33% | 30-Sep-20 A | 2020-12-22 | 2005 | PDE-60, WP2-130, ENG-220, BA-019 | BA-024, CES-010
BA-024 | Prepare Construction Analysis | 68 | 29.9% | 30-Sep-20 A | 2021-02-11 | 2010 | VP-070, BA-001, BA-019, PDE-50, BA-020, BA-010, ENG-220 | BA-030
BA-022 | Permitting Operations Project Description | 16 | 20% | 19-Oct-20 A | 2020-11-24 | 2007 | PDE-50, OP-220, OP-1100 | BA-025, CES-190 | PDE-55 not 50 is the predecessor
BA-025 | Prepare Operations Analysis | 55 | 0% | 2021-01-04 | 2021-03-23 | 1983 | VP-095, BA-022, BA-010, OP-0660, OP-0650, OP-0640, OP-0630, OP-0620, OP-0610, OP-0600 | CES-190, BA-030 | OP-446 is the predecessor
BA-030 | Finalize Admin Draft BA | 19 | 0% | 2021-07-01 | 2021-07-28 | 1914 | BA-010, BA-015, BA-024, BA-025, BA-016, ENG-480 | BA-035, BA-032
BA-032 | Submit Final Admin Draft BA | 0 | 0% |  | 2021-07-28 | 1914 | BA-030 | BA-035
BA-035 | Independent Review Draft BA | 31 | 0% | 2021-07-29 | 2021-08-28 | 2725 | BA-030, BA-032 | BA-055, BA-057
BA-055 | Reclamation, Legal, and Work Group Review | 31 | 0% | 2021-07-29 | 2021-08-28 | 2725 | BA-035 | BA-057, BA-075 | Has Reclamation agreed to a 30-day review?
BA-057 | Revise Admin Draft BA | 30 | 0% | 2021-08-30 | 2021-10-12 | 1913 | BA-055, BA-035, BA-011 | BA-075, CES-030, CES-210, BA-060
BA-060 | Submit Revised Admin Draft BA to Reclamation | 0 | 0% |  | 2021-10-12 | 2015 | BA-057 | BA-075
BA-075 | Final Reclamation and Solicitor Office Review | 31 | 0% | 2021-10-13 | 2021-11-12 | 2864 | BA-055, BA-057, BA-060 | BA-1110, BA-100
BA-100 | Reclamation Submit BA to USFWS & NMFS | 0 | 0% |  | 2021-11-12 | 2864 | BA-075 | BA-1110
BO Incidental Task Authorization |  | 135 | 0% | 2021-11-12 | 2022-03-27 | 2864 |  |  | See Mike's comment on adding coordination and review periods with USFWS and NMFS
BA-1110 | BO Incidental Take Authorization | 135 | 0% | 2021-11-12 | 2022-03-27 | 2864 | BA-075, BA-100 | OS-1120, CWC-510 | Agencies rarely meet the 135 day regulatory timeline. May want to add some contingency for a longer period.
USFWS Bald Eagle Protection Act |  | 610 | 10.95% | 01-Sep-20 A | 2023-04-17 | 1758
FED-075 | USFWS Bald Eagle Protection Act (includes Pre-Application Surveys) | 610 | 10.95% | 01-Sep-20 A | 2023-04-17 | 1758 | WP2-130
U.S. Coast Guard Navigability Determination |  | 239 | 0% | 2022-02-14 | 2023-01-30 | 1812
FED-080 | U.S. Coast Guard Navigability Determination | 239 | 0% | 2022-02-14 | 2023-01-30 | 1812 | WP3-010
USBR Warren Act |  | 356 | 0% | 2021-04-16 | 2022-09-16 | 1331
FED-090 | USBR Warren Act | 356 | 0% | 2021-04-16 | 2022-09-16 | 1331 | EIR-023 | EIR-450
USBR - Land Agreement |  | 485 | 0% | 2020-11-02 | 2022-10-13 | 229
FED-100 | USBR Land Agreements | 485 | 0% | 2020-11-02 | 2022-10-13 | 229 |  | PD-100
STATE PERMITS AND AGREEMENTS |  | 2326 | 0% | 01-Sep-20 A | 2029-10-01 | 85
Caltrans Encroachment & Transportation |  | 733 | 0% | 2022-02-14 | 2025-01-08 | 1318
STA-010 | Caltrans Encroachment & Transportation | 733 | 0% | 2022-02-14 | 2025-01-08 | 1318 | WP3-010
State Lands Commission/State Lands Lease, if needed |  | 242 | 0% | 2022-02-14 | 2023-02-02 | 1809
STA-020 | State Lands Commission/State Lands lease, if needed | 242 | 0% | 2022-02-14 | 2023-02-02 | 1809 | WP3-010
Central Valley Flood Protection Board Levee Encroachment |  | 520 | 0% | 01-Sep-20 A | 2023-02-06 | 1807
STA-030 | Central Valley Flood Protection Board Levee Encroachment | 520 | 12.01% | 01-Sep-20 A | 2023-02-06 | 1807 | WP2-130, FED-030 |  | needs to synch with 408 permit schedule
SWRCB Water Rights Permit |  | 643 | 0% | 01-Sep-20 A | 2023-04-19 | 1768
WR-00-00 | Water Right Application Summary | 612 | 0% | 01-Sep-20 A | 2023-04-19 | 1756 | WR-005, WR-185
WR-005 | Water Availability Analysis & Planning/Coordination with SWRCB | 167 | 0% | 01-Sep-20 A | 2021-07-06 | 1411 | WP2-130 | WR-025, WR-00-00
WR-025 | Prepare Water Right Application | 116 | 0% | 2021-07-07 | 2021-12-22 | 1411 | PDE-60, WR-005 | WR-035
WR-035 | QA/QC and Legal Review of Draft Water Right Application | 13 | 0% | 2021-12-23 | 2022-01-12 | 1411 | WR-025 | WR-045
WR-045 | Revise Draft Water Right Application | 24 | 0% | 2022-01-13 | 2022-02-16 | 1411 | WR-035 | WR-055
WR-055 | Work Group Review of Draft Water Right Application | 9 | 0% | 2022-02-17 | 2022-03-02 | 1411 | WR-045 | WR-065
WR-065 | Resolve Work Group Comments | 10 | 0% | 2022-03-03 | 2022-03-16 | 1411 | WR-055 | WR-075
WR-075 | Authority Approval of Water Right Application, Submit to SWRCB | 1 | 0% | 2022-03-17 | 2022-03-17 | 1411 | WR-065 | WR-085
WR-085 | Submit Water Right Application | 0 | 0% |  | 2022-03-17 | 1411 | WR-075 | WR-095 |  | This should be April 2022 to allow resolution of comments.
WR-095 | SWRCB Review of Water Right Application | 60 | 0% | 2022-03-18 | 2022-05-17 | 2009 | WR-085 | WR-105
WR-105 | Receive Protests to Application | 43 | 0% | 2022-05-17 | 2022-07-18 | 1412 | WR-095 | WR-115, WR-115
WR-115 | Resolve Protests and Schedule Protest Hearing | 78 | 0% | 2022-07-19 | 2022-11-07 | 1412 | WR-105, WR-105 | WR-125, WR-155
WR-125 | Notice Water Rights Hearing | 19 | 0% | 2022-11-08 | 2022-12-07 | 1412 | WR-115, EIR-210 | WR-135, WR-145
WR-135 | Conduct In-House Mock Water Right Hearing | 14 | 0% | 2022-12-08 | 2022-12-28 | 1420 | WR-125 | WR-145
WR-145 | Conduct Water Right Hearing | 1 | 0% | 2023-01-11 | 2023-01-11 | 1412 | WR-125, WR-135 | WR-155
WR-155 | Negotiate Permit Terms | 42 | 0% | 2023-01-12 | 2023-03-14 | 1412 | WR-115, WR-145 | WR-165
WR-165 | SWRCB Prepare Draft Permit and CEQA Findings | 21 | 0% | 2023-03-15 | 2023-04-12 | 1412 | WR-155 | WR-175, OS-1130
WR-175 | SWRCB Issue Water Right Permit | 5 | 0% | 2023-04-13 | 2023-04-19 | 1412 | WR-165 | WR-185, OS-1130, OS-1150
WR-185 | Water Right Permit | 0 | 0% |  | 2023-04-19 | 1756 | WR-175 | WR-00-00
SWRCB NPDES and CWA Section 402 (Multiple permits based on construction packages and/or ROW access) |  | 1234 | 0% | 2023-10-06 | 2028-06-28 | 413
STA-150 | SWRCB NPDES and CWA Section 402 - Initial Design Review | 90 | 0% | 2023-10-06 | 2024-02-08 | 413 | PD-100 | STA-050
STA-050 | SWRCB NPDES and CWA Section 402 - Implementation | 1144 | 0% | 2024-02-09 | 2028-06-28 | 413 | PD-100, STA-150 | MS-510-CC
SWRCB Waste Discharge Requirements (Multiple permits based on constr. packages and/or ROW access) |  | 1234 | 0% | 2023-10-06 | 2028-06-28 | 413
STA-160 | SWRCB Waste Discharge Requirements - Initial Design Review | 90 | 0% | 2023-10-06 | 2024-02-08 | 413 | PD-100 | STA-060
STA-060 | SWRCB Waste Discharge Requirements - Implementation | 1144 | 0% | 2024-02-09 | 2028-06-28 | 413 | PD-100, STA-160 | MS-510-CC
RWQCB CWA Section 401 Water Quality Certification |  | 1057 | 0% | 2021-11-18 | 2025-12-05 | 1065
401-00-00 | Clean Water Act 401 Permit Application Summary | 1057 | 0% | 2021-11-18 | 2025-12-05 | 1065 | WP2-130
RWQCB CWA Section 401 Water Quality Certification - Conditional Approval |  | 165 | 0% | 2021-11-18 | 2022-07-06 | 1677 |  |  | This is with SWB not RWQCB | This is with SWB not RWQCB
401-120 | Coordinate with RWQCB and SWRCB - Conditional Approval | 84 | 0% | 2021-11-18 | 2022-03-15 | 1677 | 404-003, EIR-210 | 401-130 |  | February 2, 2020 same as 404-025
401-130 | Prepare Draft 401 Application - Conditional Approval | 41 | 0% | 2022-03-16 | 2022-05-11 | 1677 | 404-003, 404-010, 404-030, WP2-130, 401-120 | 401-140 |  | after pre-app meeting on February 2, 2021 (4040-025) through August 3, 2021
401-140 | Authority/Integration/Work Group Review of Draft 401 - Conditional Approval | 20 | 0% | 2022-05-12 | 2022-06-08 | 1677 | 401-130 | 401-150 |  | Submit August 2021
401-150 | Prepare Final 401 Application - Conditional Approval | 20 | 0% | 2022-06-09 | 2022-07-06 | 1677 | 401-140 | 401-160 |  | August 2021 through October 2021
401-160 | Submit 401 Application - Conditional Approval | 0 | 0% |  | 2022-07-06 | 1677 | 401-150 | CWC-510, 401-170 |  | Submit per original shcedule 10/29/2021
RWQCB CWA Section 401 Water Quality Certification - Reservoir Approvals During Construction |  | 280 | 0% | 2024-11-11 | 2025-12-05 | 1065
401-170 | Prepare Draft 401 Application - Final Approval During Construction | 200 | 0% | 2024-11-11 | 2025-08-15 | 1065 | RC-100, 401-160 | 401-180
401-180 | Authority/Integration/Work Group Review of Draft 401 - Final Approval During Construction | 20 | 0% | 2025-08-18 | 2025-09-12 | 1065 | 401-170 | 401-190
401-190 | Prepare Final 401 Application - Final Approval During Construction | 60 | 0% | 2025-09-15 | 2025-12-05 | 1065 | 401-180 | 401-200
401-200 | Submit 401 Application - Final Approval During Construction | 0 | 0% |  | 2025-12-05 | 1065 | 401-190 | OPR-120
DWR DSOD (Multiple permits based on construction packages and/or ROW access) |  | 221 | 0% | 2024-07-12 | 2025-05-16 | 1226
STA-130 | DWR DSOD - Initital Review Approval | 90 | 0% | 2024-07-12 | 2024-11-14 | 1357 | FD-110
STA-080 | DWR DSOD - Design Package Approvals | 200 | 0% | 2024-08-12 | 2025-05-16 | 1226 | ENG-440, FD-110
Cal OSHA Permits (Multiple permits based on construction packages and/or ROW access) |  | 1541 | 0% | 2023-11-06 | 2029-10-01 | 69
STA-170 | Cal OSHA Permits - For Construction | 200 | 0% | 2023-11-06 | 2024-08-09 | 1169 | FD-110, PD-100 | RC-100
STA-090 | Cal OSHA Implementation | 1276 | 0% | 2024-11-11 | 2029-10-01 | 69 | PD-100, RC-100 | OPR-120
CDFW Streambed Alteration |  | 547 | 0% | 01-Sep-20 A | 2022-12-06 | 1864
STA-100 | CDFW Streambed Alteration | 547 | 7.45% | 01-Sep-20 A | 2022-12-06 | 1864 | WP2-130 |  | ?? How can this be showing a % complete when its not budgeted yet - part of next phase not Amd 2 period;
CDFW Section 2081 |  | 381 | 0% | 01-Sep-20 A | 2022-04-18 | 2030
STA-110 | CDFW Section 2081 | 375 | 10.5% | 01-Sep-20 A | 2022-04-08 | 1445 | 106-001 | OS-1120, CES-010, EIR-250, STA-120 |  | This is way off. See below
ITP - CESA (Se 2081) Operations |  | 302 | 0% | 2021-02-19 | 2022-04-18 | 2030 |  |  |  | Here are the dates to use | start | stop
CES-190 | Prepare Operations Analysis - Operations | 28 | 0% | 2021-02-19 | 2021-03-30 | 2076 | BA-025, OP-0230, BA-022 | CES-200, CES-00-10 | Needs OP-446; these dates seem odd since we are already starting on the permit with the workshops | Prepare ITP Application- Operations | 2020-09-30 18:49 | 2021-08-01
CES-00-10 | Incidental Take Permit (ITP) Operations Summary - Operations | 289 | 0% | 2021-02-19 | 2022-04-18 | 2007 | CES-190, CES-260 |  | what are the summary tasks? | Prepare ITP Application- Operations | 2020-09-30 18:49 | 2021-08-01
CES-210 | Prepare Draft ITP Application - Operations | 58 | 0% | 2021-10-13 | 2022-01-07 | 1913 | VP-095, BA-057 | CES-220, CES-230, CES-200 |  | Prepare ITP Application- Operations | 2020-09-30 18:49 | 2021-08-01
CES-200 | Additional Mitigation Planning - Operations | 30 | 0% | 2021-11-23 | 2022-01-07 | 1913 | CES-190, CES-210 | 404-035 |  | Sites Review (WG, Legal, Integration, Staff) | 2021-08-01 | 2021-09-01
CES-220 | Legal Review of Draft ITP App - Operations | 30 | 0% | 2022-01-08 | 2022-02-06 | 2844 | CES-210 | CES-240 |  | Revise Application | 2021-09-01 | 2021-10-01
CES-230 | Work Group Review of Draft ITP App - Operations | 30 | 0% | 2022-01-08 | 2022-02-06 | 2844 | CES-210 | CES-240 |  | RC and Board Vote | 2021-10-01 | 2021-12-01
CES-240 | Revise Draft ITP Application - Operations | 20 | 0% | 2022-02-07 | 2022-03-07 | 2007 | CES-230, CES-220 | CES-250 |  | Submit Permit Application | 2021-12-15 | 2021-12-15
CES-250 | Authority Board Approval of ITP App - Operations | 28 | 0% | 2022-03-08 | 2022-04-15 | 2007 | CES-240 | CES-260 |  | This is November 2021, align to Board meeting
CES-260 | Submit ITP Application to CDFW - Operations | 0 | 0% |  | 2022-04-18 | 2007 | CES-250 | CWC-510, CES-00-10 |  | This date is in December 2021. Approximatly Dec 15
ITP - CESA (Se 2081) Construction |  | 380 | 0% | 30-Sep-20 A | 2022-04-15 | 2031 |  |  |  | Here are the dates to use | start | stop
CES-00-00 | Incidental Take Permit (ITP) Construction Summary - Construction | 360 | 0% | 30-Sep-20 A | 2022-04-15 | 2008 | CES-010, CES-090 |  |  | Pepare ITP Aplication - Construction | 2020-09-30 18:49 | 2021-08-01
CES-010 | Initial Desktop Analysis - Construction | 34 | 0% | 30-Sep-20 A | 2020-12-22 | 2005 | ENG-220, VP-095, STA-110, BA-001 | CES-020, CES-00-00 |  | Prepare ITP Application - Construction | 2020-09-30 18:49 | 2021-08-01
[10 empty] | Prepare ITP Application - Construction | 2020-09-30 18:49 | 2021-08-01
CES-030 | Prepare Draft ITP Application - Construction | 58 | 0% | 2021-10-13 | 2022-01-07 | 2005 | VP-095, BA-057, CES-025 | CES-040, CES-060 |  | Sites Review (WG, Legal, Integration, Staff) | 2021-08-01 | 2021-09-01
CES-025 | Mitigation Planning - Construction | 27 | 0% | 2021-11-30 | 2022-01-07 | 2005 | CES-020 | CES-030 |  | Revise Application | 2021-09-01 | 2021-10-01
CES-040 | Legal Review of Draft ITP App - Construction | 30 | 0% | 2022-01-08 | 2022-02-06 | 2845 | CES-030 | CES-070 |  | RC and Board Vote | 2021-10-01 | 2021-12-01
CES-060 | Work Group Review of Draft ITP App - Construction | 30 | 0% | 2022-01-08 | 2022-02-06 | 2845 | CES-030 | CES-070 |  | Submit Permit Application | 2021-12-15 | 2021-12-15
CES-070 | Revise Draft ITP Application - Construction | 20 | 0% | 2022-02-07 | 2022-03-07 | 2008 | CES-060, CES-040 | CES-080
CES-080 | Authority Board Approval of ITP App - Construction | 28 | 0% | 2022-03-08 | 2022-04-15 | 2008 | CES-070 | CES-090 |  | This is November 2021, align to Board meeting
CES-090 | Submit ITP Application to CDFW - Construction | 0 | 0% |  | 2022-04-15 | 2031 | CES-080, OP-446 | CES-00-00 |  | This date is in December 2021. Approximatly Dec 15
NAHC/Local Tribes AB 52 Consultation |  | 355 | 0% | 01-Sep-20 A | 2022-04-08 | 1422
STA-120 | NAHC/Local Tribes AB 52 Consultation | 355 | 15.27% | 01-Sep-20 A | 2022-04-08 | 1422 | STA-110 | EIR-250 | Stopped review here
SMARA |  | 126 | 0% | 2021-10-19 | 2022-04-22 | 1433
STA-140 | SMARA | 126 | 0% | 2021-10-19 | 2022-04-22 | 1433 | EIR-210 | MS-250-FE
LOCAL AGENCY PERMITS AND APPROVALS |  | 735 | 0% | 2020-11-02 | 2023-08-25 | 299
Colusa County |  | 400 | 0% | 2022-02-14 | 2023-08-25 | 299
Colusa County Air Pollution Control Districts |  | 400 | 0% | 2022-02-14 | 2023-08-25 | 299
LOC-010 | Colusa County Air Pollution Control Districts | 400 | 0% | 2022-02-14 | 2023-08-25 | 299 | WP3-010 | RC-100
Colusa County Public Works - Encroachments |  | 400 | 0% | 2022-02-14 | 2023-08-25 | 299
LOC-020 | Colusa County Public Works - Encroachments | 400 | 0% | 2022-02-14 | 2023-08-25 | 299 | WP3-010 | RC-100
Colusa County Transportation |  | 400 | 0% | 2022-02-14 | 2023-08-25 | 299
LOC-030 | Colusa County Transportation | 400 | 0% | 2022-02-14 | 2023-08-25 | 299 | WP3-010 | RC-100
Colusa County Public Works Building, Street Improvement, Grading Permits |  | 400 | 0% | 2022-02-14 | 2023-08-25 | 299
LOC-040 | Colusa County Public Works Building, Street Improvement, Grading Permits | 400 | 0% | 2022-02-14 | 2023-08-25 | 299 | WP3-010 | RC-100
Colusa County General Plan and Zoning |  | 400 | 0% | 2022-02-14 | 2023-08-25 | 299
LOC-050 | Colusa County General Plan and Zoning | 400 | 0% | 2022-02-14 | 2023-08-25 | 299 | WP3-010 | RC-100
Glenn County |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
Glenn County Air Pollution Control |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
LOC-100 | Glenn County Air Pollution Control | 400 | 0% | 2020-11-02 | 2022-05-13 | 634 |  | RC-100
Glenn County Public Works - Encroachments |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
LOC-110 | Glenn County Public Works - Encroachments | 400 | 0% | 2020-11-02 | 2022-05-13 | 634 |  | RC-100
Glenn County Transportation |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
LOC-120 | Glenn County Transportation | 400 | 0% | 2020-11-02 | 2022-05-13 | 634 |  | RC-100
Glenn County Public Works Building, Street Improvement, Grading Permits |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
LOC-130 | Glenn County Public Works Building, Street Improvement, Grading Permits | 400 | 0% | 2020-11-02 | 2022-05-13 | 634 |  | RC-100
Glenn County General Plan and Zoning |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
LOC-140 | Glenn County General Plan and Zoning | 400 | 0% | 2020-11-02 | 2022-05-13 | 634 |  | RC-100
Yolo County |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
Yolo County Air Pollution Control |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
LOC-50 | Yolo County Air Pollution Control | 400 | 0% | 2020-11-02 | 2022-05-13 | 634 |  | RC-100
Yolo County Public Works - Encroachments |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
LOC-60 | Yolo County Public Works - Encroachments | 400 | 0% | 2020-11-02 | 2022-05-13 | 634 |  | RC-100
Yolo County Transportation |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
LOC-70 | Yolo County Transportation | 400 | 0% | 2020-11-02 | 2022-05-13 | 634 |  | RC-100
Yolo County Public Works Building, Street Improvement, Grading Permits |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
LOC-80 | Yolo County Public Works Building, Street Improvement, Grading Permits | 400 | 0% | 2020-11-02 | 2022-05-13 | 634 |  | RC-100
Yolo County General Plan and Zoning |  | 400 | 0% | 2020-11-02 | 2022-05-13 | 634
LOC-90 | Yolo County General Plan and Zoning | 400 | 0% | 2020-11-02 | 2022-05-13 | 634 |  | RC-100
MITIGATION |  | 2411 | 0% | 28-Aug-20 A | 1930-01-28 | 0
Early Mitigation |  | 321 | 0% | 28-Aug-20 A | 2022-02-17 | -33
EM-00-10 | Summary Report for Early Mitigation/Geotech Mitigation | 321 | 0% | 28-Aug-20 A | 2022-02-17 | -33 | WP2-130 | MS-004-P2
Pre-Construction Planning |  | 410 | 0% | 2022-12-23 | 2024-08-09 | -16
MIT-010 | Pre-Construction Planning | 410 | 0% | 2022-12-23 | 2024-08-09 | -16 | PD-100, FD-110
Pre-Construction Implementation |  | 0 | 0% | 2022-08-04 | 2022-08-04 | 1953
MIT-015 | Pre-Construction Implementation | 0 | 0% | 2022-08-04 | 2022-08-04 | 1953 | FD-110, PDC-1000
Construction Monitoring |  | 1361 | 0% | 2024-11-11 | 1930-01-28 | -16
MIT-020 | Construction Monitoring | 1361 | 0% | 2024-11-11 | 1930-01-28 | -16 | CC-100, OPR-120
Post Construction Monitoring |  | 5 | 0% | 1930-01-22 | 1930-01-28 | 0
MIT-030 | Post Construction Monitoring Begins | 5 | 0% | 1930-01-22 | 1930-01-28 | 0 | OPR-110, OPR-120
FEASIBILITY LEVEL GEOTECH |  | 321 | 25.84% | 25-Mar-20 A | 2022-02-17 | 2047
Geotechnical Permitting & Planning |  | 19 | 80.78% | 25-Mar-20 A | 2020-12-01 | 2349
GPP-00-00 | Geotech Permitting & Planning -1B | 19 | 83.04% | 25-Mar-20 A | 2020-12-01 | 2349 | GSR-000 | GSR-015
GSR-010 | Work Plans for Design Level Geologic and Geotechnical Eng Investigations | 17 | 73.02% | 04-Sep-20 A | 2020-11-25 | 2351 | WP2-130, GSR-000 | GSR-020
Field Investigation |  | 95 | 3.06% | 30-Oct-20 A | 2021-03-23 | 2273
GSR-020 | Field Data Collection Work Plan and Cost Estimate | 95 | 3.06% | 30-Oct-20 A | 2021-03-23 | 2273 | GSR-010 | GSR-030, TM-I99
Data Evaluation and Reporting |  | 279 | 0% | 30-Oct-20 A | 2021-12-16 | 9
GSR-030 | Data Evaluation and Prepare Geotechnical Data Reports | 178 | 0% | 30-Oct-20 A | 2021-07-21 | 9 | GSR-020 | GSR-040
GSR-040 | Data Gap Assessment and Preliminary Planning for Design Level Inv for Preferred Alt | 243 | 0% | 2020-12-28 | 2021-12-16 | 9 | GSR-030 | MS-004-P2
Task Management - Work Group-Res Comm-Authority Support |  | 321 | 5.12% | 28-Aug-20 A | 2022-02-17 | -33
TM-I98 | Geotech Task Management | 321 | 0% | 28-Aug-20 A | 2022-02-17 | -33 | WP2-130 | MS-004-P2
TM-I99 | Geotech Fieldwork Expenses | 137 | 6.16% | 30-Oct-20 A | 2021-05-21 | 151 | GSR-020 | MS-004-P2
FEASIBILITY ENGINEERING |  | 421 | 26.35% | 01-Sep-20 A | 2022-06-13 | 1990
Engineering Support for Env and Permitting |  | 293 | 49.03% | 01-Sep-20 A | 2021-12-15 | 2118
ENG-233 | Engineering Support for Project Description for Alternative 1 | 40 | 54.55% | 01-Sep-20 A | 2020-12-31 | 2328 | RCB-20-038, PDE-40, WP2-130 | ENG-370
ENG-236 | Engineering Support for Project Description for Alternative 2 | 40 | 54.55% | 01-Sep-20 A | 2020-12-31 | 2328 | RCB-20-038, PDE-40, WP2-130 | ENG-370
ENG-230 | Provide Engineering Support to Environmental and Permitting Team Fees | 278 | 12.03% | 30-Sep-20 A | 2021-12-15 | 10 | ENG-220 | MS-004-P2
ENG-210 | Provide Information on Key Facilities to Support Env Impact Statements | 6 | 71.43% | 12-Oct-20 A | 2020-11-09 | 187 | ENG-200, ENG-190, ENG-195 | ENG-380, ENG-470, ENG-290
TRR and Funks Reservoir Engineering |  | 36 | 56.63% | 01-Sep-20 A | 2020-12-24 | 2332
ENG-500 | TRR and Funks Reservoir Engineering Summary | 36 | 56.63% | 01-Sep-20 A | 2020-12-24 | 2332
ENG-501 | TRR - Design | 36 | 56.63% | 01-Sep-20 A | 2020-12-24 | 2332 | WP2-130 | ENG-502, ENG-503, ENG-510, ENG-530, ENG-560, ENG-580, ENG-590
ENG-502 | Funks Reservoir | 36 | 56.63% | 01-Sep-20 A | 2020-12-24 | 242 | ENG-501 | CWC-500, ENG-590
ENG-503 | Geotechnical Support for Pipelines | 36 | 56.63% | 01-Sep-20 A | 2020-12-24 | 242 | ENG-501 | CWC-500
TRR and Funks Res Const Quantities |  | 20 | 48.72% | 09-Oct-20 A | 2020-12-02 | -30
ENG-510 | TRR and Funks Reservoir Construction Quantities for EIR/EIS | 20 | 48.72% | 09-Oct-20 A | 2020-12-02 | -30 | ENG-501 | ENG-550, ENG-570, EIR-020
Overhead Transmission Lines and Substation Eng |  | 40 | 54.55% | 01-Sep-20 A | 2020-12-31 | 2328
ENG-520 | Overhead Transmission Lines and Substation Lines and Substation Engineering Summary | 40 | 54.55% | 01-Sep-20 A | 2020-12-31 | 2328
ENG-530 | Overhead Transmission Lines | 40 | 54.55% | 01-Sep-20 A | 2020-12-31 | 2328 | ENG-501 | ENG-540
ENG-540 | Substations | 40 | 54.55% | 01-Sep-20 A | 2020-12-31 | 238 | ENG-530 | CWC-500
Remaining Engineering |  | 145 | 45.73% | 01-Sep-20 A | 2021-05-21 | 2266
ENG-560 | Funks Pipeline & PGP, TRR Pipeline & PGP, TCCA & GCID Facilities, Dunnigan Pipeline Eng | 44 | 50% | 01-Sep-20 A | 2020-12-31 | 249 | ENG-501 | CWC-500
ENG-580 | Evaluation of Hydro-power Energy Recovery Facilities | 145 | 23.28% | 01-Sep-20 A | 2021-05-21 | 148 | ENG-501 | CWC-500
ENG-590 | Dunnigan Pipeline CVFPB & USACE 408 Permit Support | 86 | 33.85% | 01-Sep-20 A | 2021-03-01 | 218 | ENG-501, ENG-502 | MS-004-P2
ENG-550 | OH Transmission Lines & Substations - Constr Quantities for EIR/EIS Summary | 23 | 41.03% | 09-Oct-20 A | 2020-12-02 | 2388 | ENG-510
ENG-570 | Funks Pipeline & PGP, TRR Pipeline & PGP,TCCA & GCID Facilites, Dunnigan Pipeline – Construction quantities for EIS/EIR | 23 | 41.03% | 09-Oct-20 A | 2020-12-02 | 270 | ENG-510 | CWC-500
Convert Drawings to GIS Format |  | 6 | 71.43% | 12-Oct-20 A | 2020-11-09 | -16
ENG-220 | Convert Drawings to GIS Geodatabase File Format to Support Environmental & Permitting | 6 | 71.43% | 12-Oct-20 A | 2020-11-09 | -16 | ENG-200 | ENG-230, BA-001, CES-010, 404-010, EIR-019, BA-024
Preliminary Hydraulics Modeling |  | 173 | 15.16% | 01-Sep-20 A | 2021-06-30 | 120
ENG-420 | Preliminary Hydraulics Model Summary | 164 | 0% | 01-Sep-20 A | 2021-06-30 | 114
ENG-466 | Emergency Release Flood Modeling | 80 | 35.48% | 01-Sep-20 A | 2021-02-19 | 11 | WP2-130 | ENG-480
ENG-470 | Preliminary Pipeline Hydraulic Modeling | 90 | 0% | 11-Jan-21* | 2021-05-14 | 153 | ENG-210, ENG-193 | CWC-500
ENG-480 | System Wide Hydraulic Modeling | 88 | 0% | 2021-03-01 | 2021-06-30 | 11 | ENG-466 | CWC-500, ENG-440, BA-030
DSOD Engagement |  | 282 | 8.13% | 01-Sep-20 A | 2021-11-30 | 2129
ENG-400 | Develop DSOD Engagement Plan | 80 | 35.48% | 01-Sep-20 A | 2021-02-19 | 16 | WP2-130 | ENG-440, ENG-445
ENG-445 | DSOD Fees | 20 | 0% | 2021-02-01 | 2021-03-01 | 2289 | ENG-400
ENG-440 | DSOD Engagement | 197 | 0% | 2021-03-01 | 2021-11-30 | 11 | ENG-400, ENG-480 | CWC-500, ENG-410, STA-080
Risk Workshop |  | 167 | 0% | 30-Sep-20 A | 2021-07-06 | 2201
ENG-290 | Risk and Uncertainty Assessment | 167 | 0% | 30-Sep-20 A | 2021-07-06 | 2201 | ENG-210, EIR-021
Constructability Analysis |  | 100 | 23.08% | 30-Oct-20 A | 2021-10-13 | 2132
ENG-370 | Constructability | 100 | 23.08% | 30-Oct-20 A | 2021-10-13 | 2132 | ENG-320, ENG-233, ENG-236 | ENG-380
Class IV Cost Estimate |  | 59 | 0% | 08-Sep-20 A | 2021-01-29 | 96
ENG-265 | Develop Class 4 Cost Estimate including Mitigation Measures | 59 | 0% | 08-Sep-20 A | 2021-01-29 | 96 | EIR-021 | ENG-300, ENG-320, ENG-380
Confirm Project Benefits |  | 25 | 0% | 2021-08-13 | 2021-09-17 | -39
ENG-300 | Project Benefits | 25 | 0% | 2021-08-13 | 2021-09-17 | -39 | ENG-140, ENG-150, ENG-265, CFS-030 | ENG-320
Cost Allocation |  | 14 | 0% | 2021-09-20 | 2021-10-07 | -39
ENG-320 | Cost Allocation | 14 | 0% | 2021-09-20 | 2021-10-07 | -39 | ENG-300, ENG-265 | ENG-370, ENG-350, ENG-360
Economic Feasibility |  | 13 | 0% | 2021-09-20 | 2021-10-06 | -39
ENG-350 | Prepare Economic Feasibility | 13 | 0% | 2021-09-20 | 2021-10-06 | -39 | ENG-320 | ENG-380, CWC-393
Financial Feasibility |  | 13 | 0% | 2021-09-20 | 2021-10-06 | -39
ENG-360 | Prepare Financial Feasibility | 13 | 0% | 2021-09-20 | 2021-10-06 | -39 | ENG-320 | ENG-380, CWC-393
Confirm Env Feasibility with Mitigation |  | 5 | 0% | 2021-05-03 | 2021-05-07 | 126
ENG-340 | Obtain the Finding of Env Feasibility with Mitigation | 5 | 0% | 2021-05-03 | 2021-05-07 | 126 | EIR-040 | ENG-380
Program Design/Construction/Permit Implementation Schedule |  | 89 | 0% | 2021-07-22 | 2021-11-30 | 11
ENG-410 | Develop Program Design/Construction/Permit Implementation Plan | 89 | 0% | 2021-07-22 | 2021-11-30 | 11 | ENG-406, ENG-440 | CWC-500
Geotechnical Permit Planning & Invest Plan |  | 261 | 6.48% | 30-Oct-20 A | 2021-11-18 | 17
ENG-404 | Coordinate Geotechnical Investigation Plan | 95 | 7.77% | 30-Oct-20 A | 2021-03-23 | 17 | WP2-130, GSR-015 | CWC-500, ENG-406
ENG-406 | Coordinate to Develop Geotechnical Permitting Plan | 92 | 0% | 2021-07-09 | 2021-11-18 | 17 | WP2-130, ENG-404, GSR-015 | CWC-500, ENG-410
Feasibility Report |  | 178 | 10.47% | 30-Oct-20 A | 2021-12-30 | -43
ENG-380 | Prepare Draft Feasibility Report | 117 | 15.22% | 30-Oct-20 A | 2021-10-06 | -40 | ENG-210, ENG-350, ENG-340, ENG-360, ENG-370, ENG-265 | ENG-390, ENG-385, CWC-010
ENG-385 | Work Group Review of Draft Feasibility Report | 9 | 0% | 2021-10-07 | 2021-10-20 | -39 | ENG-380 | ENG-390
ENG-390 | Prepare Final Feasibility Report | 18 | 0% | 2021-10-21 | 2021-11-16 | -39 | ENG-380, ENG-385, OP-0230, OP-446, OP-470 | ENG-392, 408-010, DLG-010
ENG-392 | Reservoir Committee and Board Approval | 29 | 0% | 2021-11-17 | 2021-12-30 | -39 | ENG-390, CWC-010 | CWC-391
Amendment 3 |  | 86 | 0% | 2022-02-14 | 2022-06-13 | 1990
ENG-450 | Project Level Survey/Mapping | 86 | 0% | 2022-02-14 | 2022-06-13 | 1990 | WP3-010
ENG-460 | Update Project Seimicity | 86 | 0% | 2022-02-14 | 2022-06-13 | 1990 | WP3-010
Task Management - Work Group-Res Com-Authority |  | 339 | 11.77% | 01-Sep-20 A | 2022-02-17 | 2072
TM-H98 | Engineering Task Management | 294 | 13.02% | 01-Sep-20 A | 2021-12-16 | 2117 | WP2-130 | TM-H99
ENG-430 | Engineering Project Coordination, Work Group Support | 294 | 13.02% | 01-Sep-20 A | 2021-12-16 | 2117 | WP2-130
TM-H99 | Engineering Expenses | 339 | 0% | 01-Sep-20 A | 2022-02-17 | -35 | TM-H98 | MS-004-P2
PROP 1 |  | 397 | 0% | 2021-07-22 | 2023-01-27 | 1826
CWC Feasibility Review |  | 109 | 0% | 2021-09-01 | 2022-02-11 | 2051
CWC-396 | Release for CWC Review Pkg 3: Environmental with Res Ops | 0 | 0% |  | 2021-09-01 | 2152 | CWC-450 | CWC-417
CWC-417 | CWC Review Pkg 3: Environmental with Res Ops | 8 | 0% | 2021-09-02 | 2021-09-14 | 2152 | CWC-396, CWC-450
CWC-393 | Release for CWC Review Pkg 2: Economic and Finance | 0 | 0% |  | 2021-10-06 | 17 | ENG-350, ENG-360 | CWC-407
CWC-407 | CWC Review Pkg 2: Economic and Finance | 29 | 0% | 2021-10-07 | 2021-11-18 | 17 | CWC-393 | CWC-500
CWC-391 | Release for CWC Review Pkg 1: Engineering | 0 | 0% |  | 2021-12-30 | -39 | ENG-392, CWC-420, CFS-030, TM-E99, TM-E97, TM-E98 | CWC-397
CWC-397 | CWC Review Pkg 1: Engineering | 29 | 0% | 2022-01-03 | 2022-02-11 | -39 | CWC-391 | CWC-500
CWC Review of Public Draft EIR/EIS |  | 30 | 0% | 2021-07-22 | 2021-09-01 | 20
CWC-450 | CWC Public Review Draft EIR/EIS | 30 | 0% | 2021-07-22 | 2021-09-01 | 20 | EIR-080 | EIR-095, CWC-417, CWC-396
CWC Determination of Feasibility |  | 0 | 0% | 2022-02-11 | 2022-02-11 | -42
CWC-500 | CWC Determination of Feasibility | 0 | 0% |  | 11-Feb-22* | -42 | CWC-397, EIR-120, ENG-410, ENG-406, ENG-404, OP-070, CWC-407, ENG-470, ENG-480, ENG-440, ENG-560, ENG-570, ENG-580, ENG-540, ENG-503, ENG-502 | MS-003-LF
CWC All Permits Acquired for Construction Funding |  | 0 | 0% | 2023-01-27 | 2023-01-27 | 1826
CWC-510 | CWC All Permits Acquired for Construction Funding | 0 | 0% |  | 2023-01-27 | 1826 | 106-093, 401-160, 404-120, 408-160, BA-1110, CES-260
RIGHT OF WAY (ROW) |  | 1426 | 0% | 2023-10-06 | 2029-03-23 | 221
Rights of Entry |  | 218 | 0% | 2023-10-06 | 2024-08-19 | 301
ROW-100 | Right of Entry Program Cost | 197 | 0% | 2023-10-06 | 2024-07-19 | 301 | ROW-130 | ROW-210
ROW-130 | Real Estate Review | 15 | 0% | 2023-10-06 | 2023-10-27 | 221 | PD-100, RE-200, RE-210, RE-220 | ROW-140, ROW-100, ROW-410, ROW-300
ROW-140 | Authority Review and Approval of Real Estate Action | 25 | 0% | 2023-10-30 | 2023-12-06 | 301 | ROW-130 | ROW-150
ROW-150 | Finalization of Real Estate Strategy and Approach | 10 | 0% | 2023-12-07 | 2023-12-20 | 301 | ROW-140 | ROW-160
ROW-160 | Negotiation Package | 15 | 0% | 2023-12-21 | 2024-01-12 | 301 | ROW-150, ROW-300 | ROW-170
ROW-170 | Initial Offer Engagement and Negotiations | 90 | 0% | 2024-01-16 | 2024-05-21 | 301 | ROW-160 | ROW-180, ROW-400
ROW-180 | Internal Approvals of Settlement | 10 | 0% | 2024-05-22 | 2024-06-05 | 301 | ROW-170 | ROW-190
ROW-190 | External Approvals of Settlement | 10 | 0% | 2024-06-06 | 2024-06-19 | 301 | ROW-180 | ROW-200
ROW-200 | Agreement and Signing | 12 | 0% | 2024-06-20 | 2024-07-05 | 301 | ROW-190 | ROW-210
ROW-210 | Payment to Landowner | 10 | 0% | 2024-07-08 | 2024-07-19 | 301 | ROW-200, ROW-100 | ROW-220
ROW-220 | Post-Signing Coordination; Land Access Coordination | 21 | 0% | 2024-07-22 | 2024-08-19 | 301 | ROW-210 | ROW-550
Acquisitions (Phased) |  | 298 | 0% | 2023-10-06 | 2024-12-09 | 1250
ROW-300 | Appraisals and Negotiations | 138 | 0% | 2023-10-06 | 2024-04-26 | 228 | ROW-130 | ROW-480, ROW-160
ROW-410 | Real Estate Review | 10 | 0% | 2023-10-06 | 2023-10-20 | 221 | ROW-130 | ROW-420
ROW-420 | Initial Engagement with Landowner | 10 | 0% | 2023-10-23 | 2023-11-03 | 221 | ROW-410 | ROW-430
ROW-430 | Valuation / Appraisal | 40 | 0% | 2023-11-06 | 2024-01-05 | 221 | ROW-420 | ROW-440
ROW-440 | Finalization of Plats and Legals | 20 | 0% | 2024-01-08 | 2024-02-05 | 221 | ROW-430 | ROW-450
ROW-400 | Acquisitions | 233 | 0% | 2024-01-16 | 2024-12-09 | 1250 | ROW-170 | ROW-570, ROW-550
ROW-450 | Appraisal Review | 20 | 0% | 2024-02-06 | 2024-03-05 | 221 | ROW-440 | ROW-460
ROW-460 | Real Estate Manager / Authority Approval | 20 | 0% | 2024-03-06 | 2024-04-02 | 221 | ROW-450 | ROW-470
ROW-470 | Finalization of Real Estate Strategy and Approach | 5 | 0% | 2024-04-03 | 2024-04-09 | 221 | ROW-460 | ROW-480
ROW-480 | Negotiation Package | 13 | 0% | 2024-04-10 | 2024-04-26 | 221 | ROW-470, ROW-300 | ROW-490
ROW-490 | Initial Offer Engagement, Negotiations, Relocation | 100 | 0% | 2024-04-29 | 2024-09-16 | 221 | ROW-480 | ROW-500
ROW-500 | Internal Approvals of Settlement | 10 | 0% | 2024-09-17 | 2024-09-30 | 221 | ROW-490 | ROW-510
ROW-510 | External Approvals of Settlement, as needed | 10 | 0% | 2024-10-01 | 2024-10-14 | 221 | ROW-500 | ROW-520
ROW-520 | Agreement and Signing | 10 | 0% | 2024-10-15 | 2024-10-28 | 221 | ROW-510 | ROW-530
ROW-530 | Deposit of Funds / Possession | 20 | 0% | 2024-10-29 | 2024-11-25 | 221 | ROW-520 | ROW-540
ROW-540 | Post-Signing Coordination | 5 | 0% | 2024-11-26 | 2024-12-02 | 221 | ROW-530 | ROW-550
ROW-550 | Finalization of Relocation | 5 | 0% | 2024-12-03 | 2024-12-09 | 221 | ROW-540, ROW-220, ROW-400 | ROW-560, RE-200, RE-210, RE-220, ROW-570
Relocation Assistance, as needed |  | 1119 | 0% | 2024-12-10 | 2029-03-23 | 221
ROW-560 | Relocation Assistance, as needed | 1119 | 0% | 2024-12-10 | 2029-03-23 | 221 | ROW-550
Acquistion Closeout and Transfer of Jurisdiction as needed |  | 90 | 0% | 2024-12-10 | 2025-04-14 | 1250
ROW-570 | Acquisition Closeout and Transfer of Jurisdiction as needed | 90 | 0% | 2024-12-10 | 2025-04-14 | 1250 | ROW-400, ROW-550
DESIGN LEVEL GEOTECH & SURVEY |  | 384 | 0% | 2022-02-14 | 2023-08-03 | 187
Design Level Survey |  | 261 | 0% | 2022-08-04 | 2023-08-03 | 29
DLG-010 | Design Level Geotech Survey | 131 | 0% | 2022-08-04 | 2023-02-02 | -16 | ENG-390, WP3-010, PDC-1000 | PD-100, DLG-110
DLG-110 | Final Level Level Geotech Survey | 130 | 0% | 2023-02-03 | 2023-08-03 | 29 | DLG-010 | FD-110
Design Level Geotech |  | 253 | 0% | 2022-02-14 | 2023-02-01 | 318
DLG-100 | Design Level Geotech | 253 | 0% | 2022-02-14 | 2023-02-01 | 318 | WP3-010 | RC-100
PRELIMINARY AND FINAL ENGINEERING |  | 1151 | 0% | 2021-04-16 | 2025-09-12 | 619
Project Delivery Method (assumes mixed contracting) |  | 253 | 0% | 2021-04-16 | 2022-04-05 | 424
DB-100 | Design Packages and Project Delivery Method Determinations (Assumes Mixed Contracting) | 253 | 0% | 2021-04-16 | 2022-04-05 | 424 | EIR-023 | PD-100
Preliminary Engineering |  | 205 | 0% | 2022-12-23 | 2023-10-05 | -16
PD-100 | Preliminary Design | 205 | 0% | 2022-12-23 | 2023-10-05 | -16 | WP3-010, DB-100, FED-100, PDC-1000, DLG-010 | D30-200, CC-100, STA-050, STA-060, STA-090, MIT-010, FD-110, STA-150, STA-160, STA-170, RB-1000, RB-1010, ROW-130
Final Engineering |  | 286 | 0% | 2023-10-06 | 2024-11-08 | 107
FD-110 | Final Design | 221 | 0% | 2023-10-06 | 2024-08-09 | -16 | PD-100, DLG-110 | STA-130, STA-080, STA-170, RC-100, CC-100, FD-120, FD-130, MIT-010, MIT-015
FD-120 | Procurement - Contractor - Dams & Reservoirs | 65 | 0% | 2024-08-12 | 2024-11-08 | -16 | FD-110 | RC-100, CC-100
FD-130 | Procurement - Contractor - Conveyance Features | 65 | 0% | 2024-08-12 | 2024-11-08 | 107 | FD-110 | CC-100
Recreation Facilities Design/Engineering |  | 506 | 0% | 2023-10-06 | 2025-09-12 | 619
D30-200 | Design of Recreation Facilities | 506 | 0% | 2023-10-06 | 2025-09-12 | 619 | PD-100 | RFC-100
CONSTRUCTION |  | 1831 | 0% | 2022-02-18 | 2029-02-23 | 241
Procurement / Design & Construction Packaging |  | 119 | 0% | 2022-02-18 | 2022-08-03 | -16
PDC-1000 | Procurement analysis for engineering & construction contracts, project delivery methods | 119 | 0% | 2022-02-18 | 2022-08-03 | -16 | MS-004-P2 | PD-100, DLG-010, MIT-015
Conveyance Features |  | 997 | 0% | 2024-11-11 | 2028-09-05 | 107
CC-100 | Final Conveyance Construction | 997 | 0% | 2024-11-11 | 2028-09-05 | 107 | PD-100, FD-110, FD-120, FD-130 | MS-510-CC, OPR-110, MIT-020
Reservoir Features |  | 1120 | 0% | 2024-11-11 | 2029-02-23 | -16
RC-100 | Dams & Reservoir Construction | 1120 | 0% | 2024-11-11 | 2029-02-23 | -16 | DLG-100, STA-170, LOC-010, LOC-020, LOC-030, LOC-040, LOC-050, LOC-50, LOC-60, LOC-70, LOC-80, LOC-90, LOC-100, LOC-110, LOC-120, LOC-130, LOC-140, FD-110, FD-120 | MS-510-CC, MS-500-CS, OPR-110, 401-170, STA-090
Recreational Features |  | 520 | 0% | 2025-09-17 | 2027-09-14 | 619
RFC-100 | Recreation Facilities Construction | 520 | 0% | 2025-09-17 | 2027-09-14 | 619 | D30-200
Roads & Bridges |  | 650 | 0% | 2023-10-06 | 2026-04-02 | 997
RB-1010 | On-boarding Design Builder - Roads & Bridges Construction | 20 | 0% | 2023-10-06 | 2023-11-02 | 997 | PD-100 | RB-1000
RB-1000 | Roads & Bridges Construction | 630 | 0% | 2023-11-03 | 2026-04-02 | 997 | PD-100, RB-1010
OPERATIONS |  | 241 | 0% | 2029-02-26 | 1930-01-28 | -16
Early Operations (Commissioning) |  | 240 | 0% | 2029-02-26 | 1930-01-25 | -16
OPR-110 | Early Operations (Commissioning) | 240 | 0% | 2029-02-26 | 1930-01-25 | -16 | RC-100, CC-100 | OPR-120, MS-600-PB, MIT-030
Full Operations Begins |  | 0 | 0% | 1930-01-28 | 1930-01-28 | -16
OPR-120 | Full Operations Begins | 0 | 0% |  | 28-Jan-30* | -16 | OPR-110, 401-200, STA-090 | MIT-020, MIT-030
PROJECT OPERATIONS AND FINANCES |  | 1071 | 18.17% | 02-Jan-20 A | 2024-12-09 | 1340
REAL ESTATE |  | 307 | 0% | 2023-10-06 | 2024-12-09 | 221
RE-200 | Real Estate Landowner Coordination | 298 | 0% | 2023-10-06 | 2024-12-09 | 221 | ROW-550 | RE-210, ROW-130
RE-210 | Real Estate Landowner Coordination | 298 | 0% | 2023-10-06 | 2024-12-09 | 221 | RE-200, ROW-550 | RE-220, ROW-130
RE-220 | Real Estate Fees | 298 | 0% | 2023-10-06 | 2024-12-09 | 221 | RE-210, ROW-550 | ROW-130
COMMUNICATIONS & GOVERNMENT AFFAIRS |  | 338 | 23.49% | 02-Jan-20 A | 2022-02-16 | 2073
CG-000 | Communication & Government Affairs | 21 | 87.72% | 02-Jan-20 A | 2020-11-30 | 196 |  | MS-004-P1b
GS-20 | Government Affairs Work Plan 2020 | 84 | 0% | 2020-11-02 | 2021-02-25 | 2073 | WP2-130 | GS-30
GS-C51 | Strategic Communications and Message Development | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | WP2-130
GS-C52 | Informational Materials and Media | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | WP2-130
GS-C53 | Comms Work Group Support/Res Comm/Authority | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | WP2-130
GS-C54 | Environmental Process Public Involvement Support | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | WP2-130
GS-C50 | Outreach Support | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | WP2-130
GS-C98 | Communications Task Management | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | WP2-130 | GS-C99
GS-C99 | Communication Expenses | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | GS-C98
GS-C60 | Outreach to NGO's | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | WP2-130
GS-30 | Government Affairs Work Plan 2021 | 254 | 0% | 2021-02-26 | 2022-02-16 | 2073 | GS-20
FUNDING |  | 338 | 0% | 02-Jan-20 A | 2022-02-16 | 2073
REC-010 | Reclamation Coordination | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | WP2-130
FF-020 | Funding Agreement Administration | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | WP2-130
FF-030 | Federal Loan Application | 234 | 0% | 2020-11-02 | 2021-09-23 | 70 | WP2-130 | MS-004-P2
SF-010 | State Funding Agreement Administration | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
Local Funding |  | 338 | 0% | 02-Jan-20 A | 2022-02-16 | 2073
REP-005 | Quarterly Reporting Amend 1B | 21 | 87.72% | 02-Jan-20 A | 2020-12-03 | 18 |  | REP-010
INV-010 | CWC Invoicing Amend 2 | 338 | 0% | 2020-11-02 | 2022-02-16 | 2073 | WP2-130
REP-010 | Quarterly Reporting Amend 2 | 249 | 0% | 2020-12-04 | 2021-12-03 | 18 | WP2-130, REP-005 | MS-004-P2
WIFIA Loan Application |  | 275 | 0% | 2020-11-02 | 2021-11-19 | 29
WL-00-00 | WIFIA Loan Application Prep | 275 | 0% | 2020-11-02 | 2021-11-19 | 29 |  | MS-004-P2
WL-005 | Prepare Initial Loan Application | 60 | 0% | 2020-12-28 | 2021-03-19 | 139 | WP2-130 | WL-010, WL-00-010
WL-00-010 | WIFIA Loan Application | 125 | 0% | 2020-12-28 | 2021-06-18 | 139 | WL-005 | MS-004-P2
WL-010 | Review Loan Application | 35 | 0% | 2021-03-22 | 2021-05-07 | 139 | WL-005 | WL-015
WL-015 | Prepare Loan Application for Facilities | 30 | 0% | 2021-05-10 | 2021-06-18 | 139 | WL-010 | MS-004-P2
GROWTH |  | 360 | 23.66% | 02-Jan-20 A | 2022-03-18 | 2051
Plan of Finance |  | 324 | 0% | 2020-11-02 | 2022-01-27 | 2087
Project Financing Work Plan |  | 29 | 0% | 2020-11-02 | 2020-12-10 | 2077
POF-001 | Plan of Finance Work Plan Summary | 29 | 0% | 2020-11-02 | 2020-12-10 | 2077
POF-010 | Project Financing Work Plan | 18 | 0% | 2020-11-02 | 2020-11-25 | 2077 | WP2-130 | POF-020
POF-020 | Internal Workshop - Financing the Work Plan | 1 | 0% | 2020-11-26 | 2020-11-26 | 2077 | POF-010 | POF-030
POF-030 | Task Order for MDA | 10 | 0% | 2020-11-27 | 2020-12-10 | 2077 | POF-020 | POF-200
Plan of Finance |  | 324 | 0% | 2020-11-02 | 2022-01-27 | 2087
POF-400 | Plan of Finance Summary | 324 | 0% | 2020-11-02 | 2022-01-27 | 2087
Use of Facilities Term Sheets |  | 193 | 0% | 2020-11-02 | 2021-07-28 | 1913
POF-040 | Term Sheet Outline | 8 | 0% | 2020-11-02 | 2020-11-11 | 1909 | ENG-190, WP2-130 | POF-060, POF-090, FO-1000, FO-1010, FO-1020, FO-1030, FO-1040, POF-520, POF-550
POF-510 | Draft Operational Term Sheets | 8 | 0% | 2021-07-19 | 2021-07-28 | 1898 | EIR-070 | FO-1000, FO-1010, FO-1020, FO-1030, FO-1040
GCID Term Sheet |  | 45 | 0% | 2020-11-12 | 2021-01-13 | 2053
POF-060 | Prepare Draft GCID Term Sheet | 20 | 0% | 2020-11-12 | 2020-12-09 | 2053 | POF-040 | POF-070
POF-070 | Review Period | 5 | 0% | 2020-12-10 | 2020-12-16 | 2053 | POF-060 | POF-080
POF-080 | Prepare Final GCID Term Sheet | 20 | 0% | 2020-12-17 | 2021-01-13 | 2053 | POF-070 | POF-200
TCCA Term Sheet |  | 45 | 0% | 2020-11-12 | 2021-01-13 | 2053
POF-090 | Prepare Draft TCCA Sheet | 20 | 0% | 2020-11-12 | 2020-12-09 | 2053 | POF-040 | POF-100
POF-100 | Review Period | 5 | 0% | 2020-12-10 | 2020-12-16 | 2053 | POF-090 | POF-110
POF-110 | Prepare Final TCCA Sheet | 20 | 0% | 2020-12-17 | 2021-01-13 | 2053 | POF-100 | POF-200
DWR Term Sheet |  | 144 | 0% | 2020-11-12 | 2021-06-01 | 1931
POF-520 | Establish initial DWR Term Sheet reflecting final model results and initiate negotiation of commercial terms | 37 | 0% | 2020-11-12 | 2021-01-01 | 1931 | POF-040 | POF-530
POF-530 | Coordinated operations DWR Term Sheet complete | 107 | 0% | 2021-01-04 | 2021-06-01 | 1931 | POF-520 | FO-1010
Reclamation Term Sheet |  | 166 | 0% | 2020-11-12 | 2021-07-01 | 1909
POF-550 | Establish initial Reclamation Term Sheet reflecting final model results and initiate negotiation of commercial terms | 37 | 0% | 2020-11-12 | 2021-01-01 | 1909 | POF-040 | POF-560
POF-560 | Coordinated operations Reclamation Term Sheet complete | 107 | 0% | 2021-01-04 | 2021-06-01 | 1909 | POF-550 | POF-570
POF-570 | Reclamation Letter of Intent for funding signed | 22 | 0% | 2021-06-02 | 2021-07-01 | 1909 | POF-560 | FO-1000
Beneficiary Pays |  | 71 | 0% | 2020-11-02 | 2021-02-08 | 2340
POF-120 | Annotated Outline | 15 | 0% | 2020-11-02 | 2020-11-20 | 2051 | WP2-130 | POF-130, POF-140, POF-150
POF-130 | Identify Modeling Needs | 5 | 0% | 2020-11-23 | 2020-11-27 | 2051 | POF-120 | POF-150, POF-190
POF-140 | Identify Cost Model Needs | 5 | 0% | 2020-11-23 | 2020-11-27 | 2070 | POF-120 | POF-150, POF-200
POF-150 | Draft for Agent Review | 15 | 0% | 2020-11-30 | 2020-12-18 | 2070 | POF-120, POF-130, POF-140 | POF-160
POF-160 | Draft for Workgroup Review | 15 | 0% | 2020-12-21 | 2021-01-08 | 2070 | POF-150 | POF-170
POF-170 | Workshop 1 - Beneficiary Pays | 1 | 0% | 2021-01-25 | 2021-01-25 | 2070 | POF-160 | POF-180, POF-220
POF-180 | Final for RC/AB Approval | 0 | 0% |  | 2021-02-08 | 2340 | POF-170
Project Costs and Schedule |  | 131 | 0% | 2020-11-30 | 2021-05-31 | 2051
POF-190 | Benefits Modeling | 50 | 0% | 2020-11-30 | 2021-02-05 | 2051 | POF-130 | POF-210, POF-270
POF-200 | Cost Model Update | 15 | 0% | 2021-01-14 | 2021-02-03 | 2053 | POF-140, POF-110, POF-080, POF-030 | POF-210
POF-220 | Annotated Outline | 10 | 0% | 2021-01-26 | 2021-02-08 | 2070 | POF-170 | POF-230
POF-210 | Financial Model Update | 20 | 0% | 2021-02-08 | 2021-03-05 | 2051 | POF-190, POF-200 | POF-230
POF-230 | Draft for Agent Review | 20 | 0% | 2021-03-08 | 2021-04-02 | 2051 | POF-220, POF-210 | POF-240
POF-240 | Draft for Workgroup Review | 20 | 0% | 2021-04-05 | 2021-04-30 | 2051 | POF-230 | POF-250
POF-250 | Workshop 2 - Costs and Benefits | 1 | 0% | 2021-05-17 | 2021-05-17 | 2051 | POF-240 | POF-260, POF-280
POF-260 | Final for RC/AB Approval | 0 | 0% |  | 2021-05-31 | 2051 | POF-250 | PA-220
Allocation of Benefits and Costs |  | 132 | 0% | 2021-02-08 | 2021-08-10 | 2209
POF-270 | Financial Model Update | 30 | 0% | 2021-02-08 | 2021-03-19 | 2111 | POF-190 | POF-280
POF-280 | Annotated Outline | 10 | 0% | 2021-05-18 | 2021-05-31 | 2070 | POF-250, POF-270 | POF-290
POF-290 | Draft Agent Review | 20 | 0% | 2021-06-01 | 2021-06-28 | 2070 | POF-280 | POF-300
POF-300 | Draft for Workshop Review | 10 | 0% | 2021-06-29 | 2021-07-12 | 2070 | POF-290 | POF-310
POF-310 | Workshop 3 - Allocation of Benefits and Costs | 1 | 0% | 2021-07-27 | 2021-07-27 | 2070 | POF-300 | POF-320, POF-330
POF-320 | Final for RC/AB Approval | 0 | 0% |  | 2021-08-10 | 2209 | POF-310
Governance and Funding |  | 61 | 0% | 2021-07-28 | 2021-10-20 | 2158
POF-330 | Annotated Outline | 10 | 0% | 2021-07-28 | 2021-08-10 | 2070 | POF-310 | POF-340
POF-340 | Draft Agent Review | 20 | 0% | 2021-08-11 | 2021-09-07 | 2070 | POF-330 | POF-350
POF-350 | Draft for Workgroup Review | 10 | 0% | 2021-09-08 | 2021-09-21 | 2070 | POF-340 | POF-360
POF-360 | Workshop 4 - Governance and Funding | 1 | 0% | 2021-10-06 | 2021-10-06 | 2070 | POF-350 | POF-370, POF-420, POF-460
POF-370 | Final for RC/AB Approval | 0 | 0% |  | 2021-10-20 | 2158 | POF-360
Plan of Finance Document |  | 70 | 0% | 2021-10-07 | 2022-01-12 | 2098
POF-420 | Annotated Outline | 20 | 0% | 2021-10-07 | 2021-11-03 | 2070 | POF-360 | POF-430, PA-410
POF-430 | Draft for Agent Review | 20 | 0% | 2021-11-04 | 2021-12-01 | 2098 | POF-420 | POF-440
POF-440 | Draft for Workgroup Review | 20 | 0% | 2021-12-02 | 2021-12-29 | 2098 | POF-430 | POF-450
POF-450 | Final for RC/AB Approval | 0 | 0% |  | 2022-01-12 | 2098 | POF-440
Water Service Agreement Term Sheet |  | 81 | 0% | 2021-10-07 | 2022-01-27 | 2087
POF-460 | Annotated Outline | 20 | 0% | 2021-10-07 | 2021-11-03 | 2087 | POF-360 | POF-470
POF-470 | Draft for Agent Review | 20 | 0% | 2021-11-04 | 2021-12-01 | 2087 | POF-460 | POF-480
POF-480 | Draft for Workgroup Review | 20 | 0% | 2021-12-02 | 2021-12-29 | 2087 | POF-470 | POF-490
POF-490 | Final for RC/AB Approval | 0 | 0% |  | 2022-01-12 | 2087 | POF-480 | POF-500
POF-500 | Workshop 5 - Plan of Finance and Water Service Agreement | 1 | 0% | 2022-01-27 | 2022-01-27 | 2087 | POF-490
Organizational Assessment |  | 84 | 84.77% | 02-Jan-20 A | 2021-02-25 | 2327
ORA-000 | Organizational Assessment Direction | 21 | 87.72% | 02-Jan-20 A | 2020-11-30 | 196 |  | MS-004-P1b
ORA-010 | Organizational Assessment | 84 | 0% | 2020-11-02 | 2021-02-25 | 2327 | WP2-130
Agreements |  | 360 | 0% | 18-Mar-20 A | 2022-03-18 | 2051
Execute Participation Agreement 2 |  | 54 | 0% | 18-Mar-20 A | 2021-01-14 | 2357
PA-00-2A | Participation Agreement Amend 2 | 54 | 0% | 18-Mar-20 A | 2021-01-14 | 2357
PA-130 | Home Board Review - Determine Participation Level | 28 | 100% | 17-Apr-20 A | 2020-12-09 | 393 | PA-120, RCB-20-044 | PA-140, PA-160
PA-160 | Execute Amendment 2 | 0 | 0% |  | 2020-12-09 | 393 | PA-130 | MS-001-LF
PA-140 | Rebalance Participation | 26 | 0% | 2020-12-10 | 2021-01-14 | 2357 | PA-130 | PA-150
PA-150 | Final Participation Agreement Amend 2 with Exhibits | 0 | 0% |  | 2021-01-14 | 2357 | PA-140 | RCB-20-070
Successor Agreement Work Plan Amend 2 |  | 131 | 0% | 2021-06-01 | 2021-11-30 | 2051
PA-210 | Successor Agreement Work Plan Summary | 131 | 0% | 2021-06-01 | 2021-11-30 | 2051
PA-220 | Develop Master Schedule through Construction | 60 | 0% | 2021-06-01 | 2021-08-23 | 2051 | POF-260 | PA-230
PA-230 | Revenue and Expense Assumptions | 40 | 0% | 2021-08-24 | 2021-10-18 | 2051 | PA-220 | PA-240
PA-240 | Workshop 6 - Successor Agreement Work Plan | 1 | 0% | 2021-10-19 | 2021-10-19 | 2051 | PA-230 | PA-300
PA-300 | Prepare Final Draft | 30 | 0% | 2021-10-20 | 2021-11-30 | 2051 | PA-240 | PA-430
Successor Agreement Amend 2 |  | 89 | 0% | 2021-10-07 | 2022-02-08 | 2051
PA-400 | Participation and Successor Agreement Summary | 89 | 0% | 2021-10-07 | 2022-02-08 | 2051
PA-410 | Coordination with Plan of Finance | 10 | 0% | 2021-10-07 | 2021-10-20 | 2070 | POF-420 | PA-420
PA-420 | Support Agreement Development | 10 | 0% | 2021-10-21 | 2021-11-03 | 2070 | PA-410 | PA-430
PA-430 | Rebalancing Support | 50 | 0% | 2021-12-01 | 2022-02-08 | 2051 | PA-420, PA-300 | PA-440
PA-440 | Execute Agreements | 0 | 0% |  | 2022-02-08 | 2051 | PA-430 | PA-450
Amendment 3 |  | 28 | 0% | 2022-02-09 | 2022-03-18 | 2051
PA-450 | Participation Invoices | 28 | 0% | 2022-02-09 | 2022-03-18 | 2051 | PA-440
WP3-010 | Start of Amend 3 (January 2, 2022) | 0 | 0% |  | 2022-02-11 | 103 | MS-003-LF | ENG-450, ENG-460, PD-100, FED-010, FED-080, STA-010, STA-020, LOC-010, LOC-020, LOC-030, LOC-040, LOC-050, DLG-010, DLG-100
PROJECT CONTROLS |  | 293 | 19.07% | 02-Jan-20 A | 2021-12-15 | 2118
Controls |  | 282 | 0% | 2020-11-02 | 2021-11-30 | 22
PC-010 | Controls | 84 | 0% | 2020-11-02 | 2021-02-25 | 220 | WP2-130 | MS-004-P2
PC-020 | Controls Initiatives | 84 | 0% | 2020-11-02 | 2021-02-25 | 220 | WP2-130 | MS-004-P2
PMP-010 | Standard Operating Procedures | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
AR-030 | 2020 Sites Project Annual Status Report | 85 | 0% | 01-Dec-20* | 2021-03-29 | 168 |  | AR-040
AR-040 | 2020 Project Operations Report | 30 | 0% | 2021-03-30 | 2021-05-10 | 168 | AR-030 | MS-004-P2
Contract Administration |  | 282 | 0% | 02-Jan-20 A | 2021-11-30 | 22
CON-010 | Contract Administration 1B | 21 | 0% | 02-Jan-20 A | 2020-11-30 | 196 |  | MS-004-P1b
CON-030 | Contract Administration and Compliance | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
CON-040 | Task Order Development Support | 84 | 0% | 2020-11-02 | 2021-02-25 | 220 | WP2-130 | MS-004-P2
CON-050 | Procurement Support | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
Work Planning and Scheduling |  | 278 | 7.76% | 02-Jan-20 A | 2021-12-15 | 10
PS-010 | Planning Scheduling 1B | 21 | 87.72% | 02-Jan-20 A | 2020-12-03 | 10 |  | PS-030, PS-020
PS-020 | Planning Scheduling | 249 | 0% | 2020-12-04 | 2021-12-03 | 18 | PS-010 | MS-004-P2
PS-030 | Master Schedule | 46 | 0% | 2021-10-07 | 2021-12-15 | 10 | PS-010 | MS-004-P2
Program Administrative Support |  | 270 | 43.99% | 02-Jan-20 A | 2021-12-03 | 18
MB-000 | Program Administrative Support 1B | 21 | 87.72% | 02-Jan-20 A | 2020-12-03 | 18 |  | MB-010
MB-010 | Program Administrative Support | 249 | 0% | 2020-12-04 | 2021-12-03 | 18 | MB-000 | MS-004-P2
Accounts Payable & Receivable |  | 270 | 44.16% | 02-Jan-20 A | 2021-12-03 | 18
AP-010 | Accounts Payable & Accounts Receivable 1B | 21 | 87.72% | 02-Jan-20 A | 2020-12-03 | 18 |  | AP-012
AP-012 | Accounts Payable & Accounts Receivable | 249 | 0% | 2020-12-04 | 2021-12-03 | 18 | AP-010 | MS-004-P2
Invoicing & Reporting |  | 21 | 0% | 16-Jan-20 A | 2020-11-30 | 283
INV-00-30 | CWC Invoicing Amend 1B | 21 | 0% | 16-Jan-20 A | 2020-11-30 | 283 | INV-032 | MS-004-P2
Cost of Year Deliveries |  | 51 | 0% | 2020-11-02 | 2021-01-11 | 2360
CYD-00-00 | Cost of Year Deliveries Summary | 51 | 0% | 2020-11-02 | 2021-01-11 | 2360
Project Management |  | 267 | 0% | 2020-11-02 | 2021-11-30 | 21
TM-B98 | Controls Task Management | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | TM-B99
TM-B99 | Controls Expenses | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | TM-B98 | MS-004-P2
MANAGEMENT |  | 267 | 19.92% | 16-Mar-20 A | 2021-11-30 | 21
Executive Director |  | 267 | 41.58% | 16-Mar-20 A | 2021-11-30 | 21
EXD-010 | Executive Director | 267 | 41.58% | 16-Mar-20 A | 2021-11-30 | 21 | WP2-130 | MS-004-P2
Strategic Planner |  | 267 | 0% | 2020-11-02 | 2021-11-30 | 21
STP-010 | Strategic Planner | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
Program Management |  | 267 | 0% | 2020-11-02 | 2021-11-30 | 21
MGT-070 | Integration Project Management | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
BUS-00-00 | Integration Business Management | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
Risk Assessment |  | 50 | 0% | 2020-11-02 | 2021-01-08 | 2361
RA-00-1B | Update Risk Assessment | 21 | 0% | 2020-11-02 | 2020-11-30 | 2390 | RA-005
RA-005 | Risk Analysis of Recommend Option Meeting | 40 | 0% | 2020-11-02 | 2020-12-25 | 254 | VP-013 | RA-010, RA-00-1B
RA-010 | Prepare Cost Risk Update | 10 | 0% | 2020-12-28 | 2021-01-08 | 254 | RA-005 | MS-004-P2
SUPPORT |  | 270 | 10.16% | 02-Jan-20 A | 2021-12-03 | 18
General Counsel |  | 270 | 29.24% | 02-Jan-20 A | 2021-12-03 | 18
GC-010 | General Counsel | 21 | 87.72% | 02-Jan-20 A | 2020-12-03 | 18 |  | GC-020
GC-020 | Water Rights Attorney | 249 | 0% | 2020-12-04 | 2021-12-03 | 18 | GC-010 | MS-004-P2
Misc Expenses |  | 267 | 0% | 2020-11-02 | 2021-11-30 | 21
MGT-030 | Rent | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
MGT-040 | Misc Vendors | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
MGT-050 | IT & GIS Support | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
MGT-060 | Document Management & Staff Support | 267 | 0% | 2020-11-02 | 2021-11-30 | 21 | WP2-130 | MS-004-P2
Res Comm/Authority Board |  | 38 | 0% | 02-Nov-20 A | 2020-12-23 | 2373
Reservoir Committee/Board Materials DUE |  | 32 | 0% | 02-Nov-20 A | 2020-12-15 | 2379
RCB-20-080 | August Meeting Materials Due | 0 | 0% |  | 02-Nov-20* | 0 | RCB-20-070 | RCB-20-084, RCB-20-090
RCB-20-110 | November Meeting Materials Due | 11 | 0% | 2020-11-02 | 16-Nov-20* | -41 | RCB-20-100 | RCB-20-114, RCB-20-120, RCB-20-138
RCB-20-120 | December Meeting Materials Due | 21 | 0% | 2020-11-17 | 15-Dec-20* | 0 | RCB-20-110 | RCB-20-124
RCB-20-138 | Prep for November Meeting | 4 | 0% | 2020-11-17 | 20-Nov-20* | -41 | RCB-20-110 | RCB-20-114, RCB-20-118
Reservoir Committee Meetings |  | 20 | 0% | 2020-11-23 | 2020-12-18 | 266
RCB-20-114 | November 2020 Reservoir Committee Meeting | 1 | 0% | 2020-11-23 | 2020-11-23 | -41 | RCB-20-110, RCB-20-138 | RCB-20-118
RCB-20-124 | December 2020 Reservoir Committee Meeting | 1 | 0% | 2020-12-18 | 2020-12-18 | 266 | RCB-20-120 | RCB-20-128
Authority Board Meetings |  | 23 | 0% | 2020-11-23 | 2020-12-23 | 266
RCB-20-118 | November 2020 Authority Board Meeting | 1 | 0% | 2020-11-23 | 2020-11-23 | -41 | RCB-20-114, RCB-20-138 | RCB-20-128, OP-1070
RCB-20-128 | December 2020 Authority Board Meeting | 1 | 0% | 2020-12-23 | 2020-12-23 | 266 | RCB-20-124, RCB-20-118 | MS-004-P2
Note on A58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This section is confusing. For EIR and EIS materials (draft anyway) we do not have until August. Confusing to group this with the BA and ITP.
Note on B193: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Timing of this compared to the release of the draft EIR/EIS is concerning. But this could become 'preferred alternative' after the public draft and during the review period.
Note on B206: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There is often, and perhaps always, an independent review as part of the 408 proces. This can take a lot of time. Hopefully this has been discussed with the USACE
Note on B250: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure I see the logic in these 'ending' in March?
Note on B264: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there no consideration of coordination during the BiOp development? Updated from the USFWS and NMFS where 'issues' can be addressed?