## ConstructionPackages_Bio
Construction Package |  | Bio Surveys or Mitigation Commitment | Protocol-Level Surveys Required | Survey Valid Shelf-Life | Survey Area (Acres) | Rough Cost | Estimated Duration | June Yr 1 | July Yr 1 | Aug Yr 1 | Sept Yr 1 | Oct Yr 1 | Nov Yr 1 | Dec Yr 1 | Jan Yr 2 | Feb Yr 2 | Mar Yr 2 | Apr Yr 2 | May Yr 2 | June Yr 2 | July Yr 2 | Aug Yr 2 | Sept Yr 2 | Oct Yr 2 | Nov Yr 2 | Dec Yr 2 | Jan Yr 3 | Feb Yr 3 | Mar Yr 3 | Apr Yr 3 | May Yr 3 | June Yr 3 | July Yr 3 | Aug Yr 3 | Sept Yr 3 | Oct Yr 3 | Nov Yr 3 | Dec Yr 3 | Jan Yr 4 | Feb Yr 4 | Mar Yr 4 | Apr Yr 4 | May Yr 4 | June Yr 4 | July Yr 4 | Aug Yr 4 | Sept Yr 4 | Oct Yr 4 | Nov Yr 4 | Dec Yr 4 | 44 | 45 | 46 | 47 | 48
Assumptions: Land agreements in place with full access (i.e., no time restrictions). Assumes 2 years for vernal pool branchiopod surveys (1 wet and 1 dry), 2 years of rare plant surveys. Acres for species surveys are likely to be less than provided and will depend on results of habitat surveys. Shelf life durations with asterisks may vary depending on agency negotiations and permit terms.
PCP_01 | Dams | Wildlife Crossing Surveys and Report |  | 5 years | TBD | TBD | 120 days
|  | Land Cover Mapping Verification and Suitable Wildlife Habitat Assessment Surveys and Report |  | 5 years | up to 7,736 acresa | TBD | 150 days
|  | CRLF habitat suitability analysis | X | 5 years* | 172 acres | TBD | 150 days
|  | Aquatic Resources Verification Survey with USACE (5-day kickoff) |  | 5 years | TBDb | TBD | 5 days
|  | Aquatic Resources Delineation Survey and Report (full survey following 5-day kickoff) |  |  | up to 8,696 acresc | TBD | 150 days
|  | Vernal Pool Branchiopod Wet Surveys and Report | X | 5 years | up to 295 acres | TBD | 120 days
|  | Vernal Pool Branchiopod Dry Surveys and Report | X | 5 years | up to 295 acres |  | 120 days
|  | Rare Plant Surveys (Spring and Summer) and Report | X | 2 years | up to 8,723 acresd | TBD | 120 days for one year, 240 days if a second year is required for completion
|  | VELB Shrub Survey and Report | X | 5 years | up to 6,652 acres | TBD | 10 days
|  | VELB Transplant |  |  | TBD | TBD | 10 days
|  | BUOW Surveys (#1-3) and Report | X | 1 year* | up to 8,379 acres | TBD | 60 days
|  | BUOW Relocation | X |  | TBD | TBD | 15 days
|  | SWHA Surveys (#1-6) and Report | X | 1 year | up to 9,000 acres including riparian and potential scattered trees in foraging | TBD | 45 days
|  | TCBB Surveys (#1-3) and Report |  | 1 year* | 45 acres | TBD | 15 days
|  | Bank Swallow Survey and Report |  | 1 year* | 170 acres | TBD | 5 days
|  | CRLF Surveys (#1-8) and Report | X | 2 years* | <172 | TBD | 200 days
|  | Badger Survey |  | 1 year* | 7,740 acres | TBD | 3 days
|  | Badger Den Collapse |  | NA |  | TBD | 5 days
|  | Bat Roosting Survey |  | 1 year* | 172 acres | TBD | 10 days
|  | Bat Roost Removal |  | NA |  | TBD | 10 days
|  | Re-consult to Reduce Impacts |  | NA |  | TBD
|  | Secure Mitigatione |  | NA |  | TBD
|  | Pre-Constrution Surveys for GGS, Birds, Mammals, and other CEQA Species |  | 30-45 days (differs by species) |  | TBD | 30-45 days (differs by species)
a | This acreage for land cover mapping verification focuses on upland riparian, blue oak woodland, oak savanna, and annual grassland areas. Minimal focus will occur for the additional 817 acres of developed/disturbed, hayfield, orchard, ornamental woodland, row crop, and ruderal land cover types in the Dam Construction Package area. The additional acreage for verification of areas mapped as aquatic resources are shown below.
b | The acreage covered during the 5-day kickoff will be based on the extent of available access in combination with the key areas that the USACE would like to review.
c | This is the currently mapped acreage of aquatic resources, but other land cover types included in the land cover mapping verification acreage above will also be part of the verification to catch any minor additional wetland areas not captured in the desktop delineation. These additional acreages are not being double counted.
d | This acreage does not include 791 acres of developed, disturbed, orchard, vineyard, row crop, hayfield, canal land cover types. These land cover types would require very limited additional survey time, because of the low potential to support special-status plants. The acreage of Keck's checkerbloom surveys are included as part of annual grassland blue oak woodland, and oak savanna special-status plant survey acreages. The acreage of palmate-bracted bird's-beak surveys are included as part of seasonal wetland and intermittent stream plant survey acreages.
e | Assumes 2 years needed to complete required mitigation and that the period will end 6 months after the conclusion of reconsultation
* | Indicates that this timeing needs to be verified
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this for shrimp? It's named confusingly similar to the delineation survey, so we should be specific. If it's about the vernal pools themselves, then it is actually part of the delineation survey and report and we don't need a separate line item. Reply: I changed this to shrimp
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: General comment - where are these shelf life requirements coming from?