## Sheet1
Deliverable | Required Timeline | Task | NODOS Timeline
Initial Action Notice |  | EIS Project Team submits Notice of Initial Determination to Pursue Action to Review Team
| 2 days | Review Team has 2 days to inquire into notice or request briefing
NOI Clearance |  | EIS Project Team submits NOI clearance materials to Review Team
| 3 business days | Review Team has 3 days to provide comments
SES with line authority approve NOI sends to OES
OES notifies Bureau when review is complete, Bureau delivers NOI to FR
| Thursday before publication | Reclamation sends FR to EPA
NOI | Friday | NOI published in FR - begins 30 day public scoping period | 2001-11-09
Draft EIS Development Briefing | 30 days after NOI | Scoping Comment Period
| 2-3 weeks before briefing | EIS Project Team schedules briefing
| one calendar week before briefing | EIS Project Team provides briefing materials one calendar week before oral briefing | 2021-05-31
|  | EIS Project Team holds oral briefing of planned DEIS development for Review Team | 2021-06-07
| 5 business days after briefing | Review Team provides feedback up to 5 business days after briefing
SES member directs EIS Project Team to continue development of DEIS
DEIS Clearance |  | EIS Project Team prepares ADEIS
| 3 weeks before ASWS briefing | EIS Project Team provides ADEIS electronic copy to SES and Solicitor | 2021-10-01
| 3 weeks before ASWS briefing - ASWS briefing | SES and Solicitor review period
| 1 week before ASWS briefing | Briefing Materials provided to ASWS | 2021-10-15
| 3 weeks before NOA date | EIS Project Team holds ASWS oral briefing | 2021-10-22
| 2 weeks before NOA date | EIS Project Team holds Review Team oral briefing | 2021-10-29
| 10 business days after briefing | Review Team provides feedback up to 10 business days after briefing
SES sign and approve DEIS for publication
| Thursday before DEIS NOA publication | Reclamation sends DEIS to EPA
Draft EIS | Friday | NOA published in FR - begins 45 day comment period | 2021-11-12
FEIS Clearance | 45 days after DEIS NOA | DEIS Comment Period Ends
EIS Project Team prepares FEIS, and ROD
| 3 weeks before ASWS briefing | EIS Project Team provides FEIS electronic copy to SES and Solicitor | 2022-01-18 | 2022-02-01
| 3 weeks before ASWS briefing - ASWS briefing | SES and Solicitor review period
| 1 week before ASWS briefing | Briefing Materials provided to ASWS | 2022-02-01
| 3 weeks before NOA date | EIS Project Team holds ASWS oral briefing | 2022-02-08
| 2 weeks before NOA date | EIS Project Team holds Review Team oral briefing | 2022-02-15
| 10 business days after briefing | Review Team provides feedback up to 10 days after briefing
SES sign and approve FEIS for publication
| Thursday before FEIS NOA publication | Reclamation sends FEIS to EPA
Final EIS | Friday | NOA published in FR- begins 30-day waiting period | 2022-03-01
ROD Clearance | 30 days after FEIS NOA | FEIS Waiting Period Ends
| 2 weeks before ROD signed | EIS Project Team sends One-page notice to Review Team | -10
| 3 business days | Review Team has 3 business days to inquire further into ROD or request oral briefing
SES approve and sign ROD
ROD |  | ROD signed | 1900-01-03
Formulas:
NODOS Timeline = [NODOS Timeline, row below]-7

## Sheet3
Impacted Waters of the United States | Temporary Impacts[1] | Permanent Impact (acres) |  | Total Proposed Mitigation
(acres)
Total
Impacts
(acres)
|  |  |  | Grasslands Mitigation Bank | In-Lieu Fee Program
|  |  |  | (2:1) | (3:1)
Ditch | 0.44 | 0.53 | 0.97 | 1.94
Ephemeral Drainage | 0.05 | 0.03 | 0.08 | - | 0.24
Fresh Emergent Wetland | 0.46 | 0.81 | 1.27 | 2.54
Lacustrine | 0.03 | 2.36 | 2.39 |  | 7.17
Seasonal Wetland | 0.42 | 0.02 | 0.44 | 0.88 | -
Intermittent Stream | 0.03 | - | 0.03 | - | 0.09
Settling Pond | - | 0.09
Settling Pond | - | - | 0.015 | 0.03 | -
(Grasslands Mitigation Bank)
Settling Pond (ILFP) | - | - | 0.075 | - | 0.225
Total | 1.43 | 3.84 | 5.27 | 5.39 | 7.725
|  |  | 2.575 | 2.695
[1] Temporary impacts are impacts that will be restored upon completion of construction. These impacts will last for the entirety of Project activities- estimated 12 years.

## Sites new
FEIS Clearance | 45 days after DEIS NOA | DEIS Comment Period Ends
EIS Project Team prepares FEIS, and draft ROD
|  | EIS Project Team provides FEIS electronic copy to SES and Solicitor | 2023-07-03
| 3 weeks before ASWS briefing - ASWS briefing | SES and Solicitor review period ends | 2023-07-14
|  | ICF backcheck ends | 2023-07-19
|  | ICF 508 compliant document delivered | 2023-08-11
| 2 weeks in advance of briefing ***policy states: to the extent practiciable, the final EIS briefing should be scheduled within 2 weeks of Bureau Execs request and a minimum of 2 weeks prior to anticipated date of pub of the final | Reclamation provides a complete admin final EIS (**508 COMPLIANT**) and draft ROD to the Departmental Review Team (DRT) and Assisstant Secretary of Water and Science (ASWS) and requests the final EIS brifing through the ASWS's Chief of Staff | 2023-08-14
| 1 week prior to briefing | Briefing Materials provided to ASWS/DRT | 2023-08-21
| 2 weeks before NOA date | EIS Project Team holds ASWS/DRT oral briefing | 2023-08-28
| 5 business days after briefing | ASWS/DRT provides feedback up to 5 days after briefing | 2023-09-04
SES sign and approve FEIS for publication
| Week before FEIS NOA publication | Reclamation sends FEIS to EPA | 2023-09-08
Final EIS | Friday | NOA published in FR- begins 30-day waiting period | 2023-09-15
ROD Clearance | 30 days after FEIS NOA | FEIS Waiting Period Ends
| 2 weeks before ROD signed | EIS Project Team sends One-page notice to Review Team
| 3 business days | Review Team has 3 business days to inquire further into ROD or request oral briefing
SES approve and sign ROD
ROD |  | ROD signed