# Proposed BA meeting topics and schedule with Reclamation

|  |  |  |  |
| --- | --- | --- | --- |
| **Week** | **Deliverable (week prior to topic)** | **Meeting topic** | **Meeting date** |
| Sept 16-20 | Action Area map, no effect/may affect table | No meeting | No meeting |
| Sept 23-27 | Delivered previous week | Action Area, no effect/may affect table | Sept 24 - done |
| Oct 21 - 25 | VP shrimp and plants (effects, AMMs, and compensatory mitigation) | No meeting | No meeting |
| Oct 28 – Nov 1 |  | VP shrimp and plants | Oct 29 - done |
| Nov 4 - 8 | cuckoo (effects, AMMs, and compensatory mitigation) | No meeting | No meeting |
| Nov 11 - 15 | CRLF (effects, AMMs, and compensatory mitigation) | cuckoo | Nov 12 |
| Nov 18 - 22 | Giant garter snake (effects, AMMs, and compensatory mitigation) | CRLF | Nov 19 |
| Dec 9 - 13 | No deliverable | Giant garter snake | Dec 10 |
| TBD | Revised sections to federal agencies | No meeting |  |
| TBD | No deliverable | Revised sections - live edit meeting | TBD |